#### UNDP Project Document

Government of Senegal, The Gambia, Guinea Bissau, Mauritania, Cape Verde

United Nations Development Programme

Adaptation to Climate Change- Responding to Coastline Change in

its human dimensions in West Africa through Integrated Coastal Area Management (ACCC)

Table of Contents

Section										                          Page

Acronyms	3

PART I: Situation Analysis	5

PART II: Strategy	18

PART III: Management Arrangements	36

PART IV: Monitoring and Evaluation Plan and Budget	44

PART V: Legal Context	50

PART I: Incremental Cost Analysis	51

PART I : Other agreements	63

PART II : Organigram of Project	63

PART III : Terms of References for key project staff and main sub-contracts	63

PART IV:  Stakeholder Involvement Plan	63

SIGNATURE PAGE	66

List of Annexes	69

## Acronyms

| ACCC | Adaptation to Climate and Coastal Change in West Africa - responding to coastline change and its human dimensions in West Africa through integrated coastal area management |
| --- | --- |
| ALM | Adaptation Learning Mechanism |
| AMCEN | African Ministerial Conference on the Environment |
| APF | Adaptation Policy Frameworks |
| CC | Climate change |
| CCLME | Canary current large marine ecosystem project |
| CCPAC | Caribbean Planning for Adaptation to Climate Change Project |
| CGE | Consultative Groups of Experts |
| COP | Conference of Parties |
| CSRP | Sub-Regional Fisheries Commission |
| DEX | Direct Execution Arrangement/ Organisation |
| DMP | Desert Margins Programme |
| GEF | Global Environment Facility |
| GOG-LME | Gulf of Guinea Large Marine Ecosystem |
| GOOS | Regional Ocean Observing and Forecasting System for Africa |
| GRBDO | Gambia River Basin Development Organisation |
| IBRD | International Bank for Reconstruction and Development |
| ICAM | Integrated Coastal Area Management |
| IOC | Intergovernmental Oceanographic Commission (of UNESCO) |
| IUCN | International Union for the Conservation of Nature |
| IW | International Waters |
| LDCs | Least Developed Countries |
| LME | Large Marine Ecosystem |
| NAPA | National Adaptation Programme of Action |
| NSC | National Steering Committee |
| NEAP | National Environmental Action Plan |
| NEPAD | New Partnership for Africa’s Development |
| NEX | National Execution Arrangement/ Organisation |
| NFP | National Focal Point |
| NPC | National Project Coordinator |
| NPD | National Project Director |
| NPMT | National Project Management Team |
| NGO | Non-governmental Organization |
| ODINAFRICA | Ocean Data and Information Network in Africa |
| OMVS | Organisation for the Valorisation of the Senegal River |
| PAP | Priority Action Programmes |
| PIR | Project Implementation Reviews |
| PRE-COI | Regional Programme for the Environment of the Indian Ocean Commission |
| RCU | Regional Coordinating Unit |
| ROOFS-Africa | Regional Ocean Observing and Forecasting System for Africa |
| RPMU | Regional Project Management Unit |
| RPSC | Regional Project Steering Committee |
| SEACAM | Secretariat for Eastern African Coastal Area Management |
| SIDS | Small Island Developing States |
| SINEPAD | Interim Secretariat for the NEPAD Environment Initiative |
| SLR | Sea Level Rise |
| SNC | Second National Communication |
| SSA | Sub-Saharan Africa |
| TRA | Threat Reduction Assessment |
| TSG | Technical Support Group |
| UNCED | United Nations Conference on Environment and Development |
| UNDP | United Nations Development Programme |
| UNDP-CO | UNDP Country Office |
| UNEP | United Nations Environment Programme |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNOPS | United Nations Organisation for Project Services |
| WWF | World Wildlife Fund |
| UNFCCC | United Nations Framework Convention on Climate Change |

##### SECTION I: Elaboration of the Narrative

## PART I: Situation Analysis

### 1.1 Introduction

- The interconnected coastal and marine environment of Mauritania, Senegal, Gambia, Guinea Bissau, and Cape Verde is a highly productive ecosystem of significant marine biological diversity. It also underpins a significant portion of livelihood opportunities of the coastal communities.  However, several assessments based on country specific National Communications to the UNFCCC, the second assessment of the Intergovernmental Panel on Climate Change as well as GEF-funded projects such as the African Process, have concluded that widespread coastal erosion due to climate change is one of the most serious anticipated environmental problems facing the region. Even though coastal erosion and sedimentation have been a reality for centuries in these countries, and are not solely a consequence of climate change due to anthropic carbon emission, both processes are strongly influenced by changes in climatic conditions. Climate change scenarios for the West African region include an anticipated increase in mean surface temperature of up to 0.5º C per decade, increased evapotranspiration, increased rainfall variability and intensity, accelerated sea level rise of around 1 m per century, any reduced coastal upwelling resulting from weakening of the Azores high and the trade winds, exacerbated by disruption from freshwater plumes of continental origin (for additional details, refer to Annex A3). The resultant shifts in the hydro-graphical and oceanic conditions due to climate change are likely to exacerbate coastal erosion and sedimentation problems in the West African region.  As all five countries are within the Canary Current Large Marine Ecosystem (and thereby aligned across an important environmental transition which is likely to be modified by sea level rise and climate change), a coastwise shift in climatic, hydro-graphical and oceanic conditions northward along the coast with global warming will be better identified and addressed by each of these countries if they understand features and processes in neighbouring states. This project is designed to foster such a collaborative effort by implementing a series of activities that lead to the improvement in the adaptive capacity to climate change of sensitive coastline ecosystems in the five countries. At the heart of the project is a combination of community based demonstration projects and UNDP & UNESCO led support to facilitate and build capacity to foster national level integration of policies that promote adaptive capacity to climate change of coastline ecosystems.

- The primary objective of the project is to maintain or strengthen ecosystem resiliency to climate change along the canary current coastline. As the West Africa coastal zone hosts a number of protected areas (PAs) containing globally significant biodiversity such as the Banc d’Arguin, Djoudj, Diawling, Saloum, etc, the project will contribute towards ensuring that global benefits in the GEF focal area of biodiversity are resilient to additional pressures of climate change. Although ecosystem integrity may be a necessary condition for the sustainability of these PAs, it alone is not sufficient.  The project makes an important contribution by ensuring that climate change concerns are better integrated with ongoing or planned activities that support ecosystem integrity including the management and use of biodiversity resources.  If adaptive measures to climate change effects including sea level rise are not supported, the biodiversity resources of these PAs are unlikely to realize, in the long term, the full benefits of measures implemented (under conventional biodiversity projects) to promote and manage globally important biodiversity resources. In particularly sensitive ecosystems, significant (and potentially irreversible) losses are likely due to climate change.  The maintenance of ecosystem stability in light of climate change is therefore a necessary condition for the management of biodiversity in the production landscape.  In promoting measures that ensure resources and management plans to ensure ecosystem integrity are resilient to likely climate change impacts, facilitating improved integrated management of coastal areas (including resources in wetlands and island ecosystems) and promoting replication based on the experiences and lessons learned, the project will contribute to the improved management and sustainable use of biological diversity of coastal and marine resources in several pilot sites in the West African region.

- The time frame for implementation of the project is four years. As of to-date, co-financing of approximately US$9,800,000 in cash, parallel-financing and in-kind contributions has been secured. Additional co-financing is expected to be confirmed through continuous bilateral discussions during implementation, and will further contribute towards country-ownership and sustainability beyond the lifetime of the contribution made by GEF SPA funds.

### 1.2 Context and global significance

- The GEF Council paper GEF/C.23/Inf.8/Rev.1 (GEF Assistance to Address Adaptation) states that:

“Adaptation to climate change is increasingly recognized as significant to the attainment of sustainable development and as essential for the achievement of many global environmental objectives. While many scientific uncertainties exist, the scope and magnitude of the risks now known to be associated with climate change represent a challenge to environmental and economic goals that must be taken into account today ... the understanding of human response to climate change is still at an early stage, with much to be learned from historical experience. However, in general it is known that [among numerous factors]  the capacity to adapt is determined by access to resources, information and technology, the skill and knowledge to use them, and the stability and effectiveness of cultural, economic, social, and governance institutions that facilitate or constrain how human systems respond. Those with the least resources have the least capacity to adapt and are the most vulnerable.”

- This Full Project entitled, ‘Adaptation to Climate Change - Responding to Coastal Change and its human dimensions in West Africa through integrated coastal area management’ (ACCC) will be implemented in Mauritania, Senegal, The Gambia, Guinea Bissau, and the Cape Verde Islands. The project will target highly vulnerable communities in the five West African countries, and assist them in increasing their capacity to adapt to long-term climate change including variability.  This will be done within the context of the SPA guidelines, so that while assisting communities to increase their adaptive capacity, global environmental benefits in the biodiversity focal area will simultaneously be made resilient to climate change as per guidelines in the SPA (GEF/C.27/Inf.10, para 26).

- Since the first studies on the impacts of climate change in Africa, it was clear that climate change will have significant consequences on coastal regions, especially on small islands and low lying coastal zones (Ibe and Awosika, 1991; Saha, 1991; Alusa and Ogallo, 1992; Hoozemans et al., 1993; Ibe and Ojo, 1994; Smith et al., 1996). This is due to the morphology of coastal regions-– mainly low lying coasts with numerous estuaries, deltas and small islands, the presence of important ecosystems (such as mangroves) that are highly sensitive to climate parameters and to the high concentration of population and economic activities along these littorals based on a high dependency of the national economies on the natural resources (beaches, fisheries resources, oil, sand).

- The main biophysical impacts of sea level rise and increased variable rainfall, as defined by the second IPCC assessment, are increased coastal erosion, more extensive coastal inundation, higher storm surge flooding, salinisation of surface and ground waters, and loss of wetlands (Bijlsma et al., 1996). Ibe and Ojo (1994) also indicated that other components of climate change could induce dramatic changes in water resources, energy resources – through inundation of oil-producing deltaic zones and modifications in dams inducing changes in hydropower production - and oceanic circulation, particularly upwellings, but also exacerbate drought and desertification. The main coastal ecosystems at risk are mangroves and coral reefs (McLean et al., 2001). Mangroves are strictly dependent on the sea level variations and also on the rainfall and salinity so it is expected that they will migrate or die if lateral shifting is not possible or if salinity is too high. However, other factors like the topography of the area but also the rate of sedimentation will be of importance in the response of mangroves to sea level rise (Bijlsma et al., 1996).

- Furthermore, Alusa and Ogallo (1992), for the Eastern African Region as well as Ibe and Ojo (1994) for the Atlantic African coast, identified the following impacts of climate change on the main economic activities present in the coastal zones:

- Fisheries will be affected through the degradation/loss of ecosystems such as mangroves which act as spawning, breeding and nursing grounds for a number of fish species, and through changes in sea surface temperature and also the intensity and location of upwellings that will modify species distribution;

- Agriculture will be affected – sometimes positively - by changes in CO2 atmospheric concentration, temperature and rainfall that will modify the geographical distribution of agro-ecological zones in relation with the sensitivity of most of the crops to climatic parameters. In the coastal zones, sea level rise will also induce a salinization of soils, surface and ground waters that will necessarily affect agricultural lands. Permanent flooding will mean a loss of agricultural lands in a number of coastal zones;

- Coastal infrastructures (such as roads and harbours) will be at risk by sea level rise induced coastal erosion and inundation. For the same reasons coastal towns and villages will be threatened and some coastal populations will be displaced;

- Tourism, which is mainly dependent on beaches (sun and sand), will be affected by an acceleration of coastal erosion due to sea level rise that will reduce the number of appropriate sites for beach-based tourism. Tourism infrastructure along the coast will also be impacted, as will a number of heritage sites.

  - These threats have been acknowledged by the Third Assessment Report of the Intergovernmental Panel on Climate Change (IPCC), which stated that “Tropical and subtropical coastlines, particularly in areas that are already under stress from human activities, are highly susceptible to global warming impacts.” (McLean et al., 2001).

  - The IPCC defines vulnerability as the degree to which individuals and systems are susceptible to or unable to cope with the adverse effects of climate change, including climate variability and extremes. This is a function of:

• 	Sensitivity, which includes the extent to which natural or social systems are sensitive to changes in weather and climate (the exposure-response relationship) and the characteristics of the population, such as the level of development and its demographic structure

• 	Exposure to the weather or climate-related hazard, including the character, magnitude, and rate of climate variation and long term change

• 	Adaptation measures in place to reduce the burden of a specific adverse outcome (the adaptation baseline), the effectiveness of which determines in part the exposure– response relationship.

  - Despite the important predicted environmental and socio-economic consequences that climate change will have on the coastal zones of sub-Saharan Africa, relatively few countries have carried out comprehensive assessments of their vulnerability to climate change (Niang-Diop, 1998). While a number of African countries have conducted vulnerability-adaptation assessments (V&A studies) in fulfilment of commitments under the United Nations Convention on Climate Change (UNFCCC), most of these studies have focused only on the impacts of sea level rise on coastal erosion and flooding (See Paragraph 87). In 1989, during the first workshop organized on the adaptive responses to sea level rise and other impacts of climate change African coastal countries presented very preliminary assessments of their vulnerability to climate change (Titus, 1990). During the second meeting organized on the vulnerability of coastal zones to sea level rise, Senegal and Nigeria presented the first quantitative results from a study funded by the US Environmental Protection Agency (Awosika et al., 1994; Niang et al., 1994). These V&A studies assessed, for different sea level rise scenarios (over specific temporal and spatial scales), the land that will be lost due to coastal erosion and flooding, the population and economic value at risk as well as the costs of two different protection options (French et al., 1995; Dennis et al., 1995). The Gambia conducted a V&A study using 3 sea-level rise scenarios  and calculated the areas of land to be lost, the population and economic value at risk but only for the Banjul-Cape St Mary area while adaptation options were only identified qualitatively (Jallow et al., 1996, 1999).

  - The coastal ecosystems of West Africa are highly significant in terms of globally important biodiversity.  WWF’s Global 200 list includes the Guinea moist forests, Upper Guinea streams and, most importantly, the Canary Current.  There is a high connectivity amongst these coastal ecosystems in this region of West Africa, which is mainly due to the nature of the sediment transport along the coast, as well as the influence of river discharges (Gambia, Senegal, Saloum, on the sediment load reaching the coastal areas). Climate change, particularly sea level rise, which is likely to affect the natural sediment transport system in this marine environment, could lead to impacts such as coastal erosion. See Table 1 below for a list of biodiversity benefits in the selected pilot regions of the participating countries.

  - According to the World Resources Institute (UNDP/UNEP/WB/WRI, 2000), the coastal zone in the countries participating in this project supports diverse and important ecosystems including rocky shores, sandy beaches, deltas, estuaries, coastal wetlands, sea grass meadows and lagoons that not only possess a rich biodiversity but also constitute important resources upon which the local economies are based. Mangroves are especially important features because they protect the coastline by moderating storm and wave impacts and because mangroves stabilize sand and soils, cycle nutrients, absorb and break down waste products, provide wildlife habitat, and maintain biodiversity. Mangroves also contribute significantly to the economies of coastal countries by providing opportunities for the harvesting of resources and increasingly for tourism.

  - In general, African coastal waters are rich in fisheries resources, which in 1997 contributed US$445,000,000 to countries’ economies (FAOSTAT 2001), with landings in estuaries and lagoons accounting for more than three-quarters of total fishery landings in Africa (IPCC 1998). In some countries, notably small island states such as Cape Verde and Seychelles, fisheries is a significant employer accounting for more than one-third of agricultural workers (FAO 1996), with artisan fishing activities being both an important source of income and source of protein for coastal communities. In addition to important economic activities such as fisheries, tourism and agriculture, crucial infrastructures (roads, ports, harbours) and cities are located in the coastal zones of sub-Saharan Africa, as well as oil, gas and other mineral reserves.

  - While erosion and accretion are natural and dynamic processes that occur globally in coastal zones, anthropogenic activities in both coastal zones and inland can alter natural patterns, which in turn impact on the capacity of coastal ecosystems to adapt. The conversion of natural coastal habitats such as wetlands and mangroves for urban or agricultural uses reduces the ability of such ecosystems to provide a natural barrier or buffer against wave action and storm surges, which results in further and increased erosion and other impacts such as flooding. The mining of sand contributes to erosion by disturbing the surface and exposing the substrate to rain, rivers and wave action. The construction of dams on rivers further inland reduces sediment flows and increases the river’s scouring potential leading to higher rates of erosion in the coastal zone (WCD, 2000).

  - Climate change and in particular sea level rise will add pressures on the coastal zones leading to a further deterioration of ecosystems, infrastructures and economic activities and may also exacerbate the scale of the current pressures by causing inundation of low-lying areas, erosion of infrastructure, displacement of populations, and contamination of freshwater sources, thus threatening the livelihoods of coastal populations and development options of all those countries where coastal areas make an important contribution to the economy.

  - In addition to pollution and the unsustainable exploitation of coastal and marine resources, coastal erosion and sea-level rise are among the most serious issues facing coastal countries in West Africa. This was also a major conclusion of the countries of the region that participated in the “GEF MSP on the Development and Protection of the Coastal and Marine Environment in Sub-Saharan Africa”.

  - The West African coast contains a wide range of ecosystems and diverse resources, including extensive mangrove forests, sandy beaches, lagoons, coastal wetlands, and plentiful fisheries . The sub-region is also characterized by frequent storm surges along the coast, and highly dynamic patterns of erosion and accretion, which makes the protection afforded by the mangroves and other coastal wetlands vitally important in stabilizing the coastal zone and enabling infrastructure and development..  The GEF has invested in several projects to conserve biodiversity in these coastal ecosystems, including:

- Senegal: Integrated marine and coastal resource management project (PIMS# 1189);

- Guinea Bissau: Coastal and Biodiversity Management Project (PIMS #1221); and

- Gambia: Integrated coastal and marine biodiversity management (PIMS #1067).

Coastline change, whether it is caused by natural or human induced factors, is a critical issue along the whole of the Western African coast, with erosion rates of 23-30m per year being recorded in some areas, and with severe social and economic consequences for the countries affected. Natural causes include changes in meteorological and oceanographic conditions (winds, waves and currents, barometric pressure), modifications of the sediment budget and sea level rise. Anthropogenic causes include mining of sand and gravel from estuaries, beaches and directly from the continental shelf, dredging activities, construction of building and other hard structures along the coasts and climate change (due to increased greenhouse gases concentrations in the atmosphere). The construction of dams has been shown to lower sediment loads in rivers that reach the coast by up to 40%, thus reducing sediment available to replace that eroded or extracted in the coastal zone.

- Climate change scenarios for the West African region anticipate increases in frequency and intensity of storm surges that will exacerbate erosion through the movement of greater amounts of coastal material. Predictions also include a rise in sea level of one metre which would result in land loss of 18000 km2 along the Western African coast, thereby affecting coastal cities including Banjul (Gambia) and Dakar (Senegal), and which would lead to a significant social problem of relocation and resettlement. The participating countries have through the National Communications process identified critical gaps in their understanding of climate change impacts, and their capacity to adapt to its consequences (refer to Annex A7 for a short overview of NC outcomes). This project will address these critical gaps and enable the participating countries to develop and implement effective adaptation strategies to address the impacts of climate change. The project will therefore establish close linkages with these and other relevant related programmes (see section 5 (Institutional Support) in Executive Summary).

- The Abidjan Convention, the GOG-LME programme and the World Bank (1995) recognise that erosion is one of the most critical coastal issues in West Africa. Annual retreat rates are very high in the sub-region, varying between 1 to 3 meters, and can be even more extreme in sensitive areas.  For example, erosion rates of 4 to 5 metres are observed in The Gambia (Bijilo and Kololi beaches) and rates as high as 20-30 meters have been recorded in Senegal (Djiffere), affecting coastal infrastructure and development. Coastal erosion has thus been recognised as a critical issue at the national level by The Gambia and Senegal in the National Reports of the GEF MSP Sub-Saharan Africa Project.

- Coastal erosion is also a significant issue in the neighbouring countries of Cape Verde, Guinea Bissau and Mauritania. In Cape Verde, coastal zones are being degraded due to over-harvesting of extraction of sand and gravel, while land degradation in the watershed also leads to coastal erosion and sedimentation. In Guinea Bissau, with its low altitude above sea level, it is estimated that the country risks losing much of its territory including mangrove coasts and islands due to the rising of sea level.  Although the population density of Mauritania’s 754 km of coastline is extremely low, urbanisation and industrialisation is increasing in some coastal areas.

- While coastal erosion has been identified as a critical issue, the countries that participated in the African Process noted that the lack of available socio-economic data has prevented an accurate estimation of the socio-economic costs of erosion. However, the fact that the coastal zone is highly populated and is the location where most economic activities take place means that the potential impacts of coastal erosion are very high in the region. For example, fish landing sites have been eroded in The Gambia, and the copra industry, which is situated on beaches and employs thousands of people, is also threatened. Also in The Gambia, cultural heritage sites such as forts and castles have been damaged or are highly threatened. In Senegal erosion has led to the destruction of a fishing factory, and of the Saloum Delta National Park guard’s house resulting in the closure of the unit in August 1989. A village was abandoned and population displaced due to erosion in Niodior and Dionewar.

- One of the activities that is seriously affected by coastal erosion, and one that is likely to intensify as climate change worsens the rates of coastal degradation, is tourism. This was strongly emphasised in the National Reports of the African Process. Poor land use planning and coastal development including insufficient set backs have led to the destruction of natural dunes and vegetation by the tourism industry itself, resulting in higher erosion rates and the destruction of coastal infrastructure, causing a decline in tourism activities in areas where beach fronts have eroded away (e.g. Senegal and The Gambia). In response, two of Gambia’s most prestigious tourist establishments, the Kairaba Beach Hotel and Senegambia Hotel, have already undertaken some expensive protection measures to protect the hotels against further beach erosion. Kairaba Beach Hotel for example has spent US$ 400,000 on sand bagging using geotextile sandbags whilst Senegambia Hotel spent about US$ 330,000 in 1998 to protect its beach by a sandbagging method". In Senegal, a tourist camp had to be displaced inside the islands due to erosion. However, new tourism opportunities were created in Djiffere due to the accretion process and the creation of beaches along the riverside.

- While climate change induced erosion is a threat to coastal activities, it is also an impact of these activities. Indeed, anthropogenic activities are a major cause of coastal erosion in the countries that consider it as a critical issue. In the causal change analysis conducted during the first phase of the African Process, anthropogenic activities were estimated to account for 70-90% of coastal erosion in Gambia. Among the activities that have a significant impact on coastal zones is the energy sector and urbanisation (including tourism). Damming for hydroelectric plants affects stream flows and sediment budgets, and the construction of oil refineries and wells, gas and oil pipelines, storage tanks with insufficient setbacks have been a main cause of erosion.

- Other major causes of erosion, indirectly linked to human activities, include global climate change and sea level rise, which have led to an increase in the strength and frequency of natural phenomena such as storms and cyclones. It is considered that storms and cyclones contribute substantially to coastline changes. Anthropogenic activities thus reinforce the effects of natural and sub-natural phenomena by reducing the natural capacity of the ecosystems to cope with natural phenomena. This is the case when natural erosion protection systems such as mangroves or marshes are overexploited and degraded.

### 1.3 Institutional, sectoral and policy context

- The project will work within the national institutional and legal framework within each of the participating countries. In targeting adaptive capacity to address long-term climate change including variability within individual communities, attention will be paid to capacity and policy gaps at local, sub-national, and national levels.  The country specific assessments, which were undertaken for each country, describe the institutional and policy context and identify such capacity and policy gaps.

- The reports of all the participating countries are included in Annex A6. These reports treat certain issues that are most relevant for the coastal management in the participating countries: legislation, threats, root causes and barriers, instutional arrangements, regulations and enforcement, erosion prone areas, activities undertaken and the problems encountered. They have been used as basic input for the ACCC project.

### 1.4 Stakeholder analysis

- Stakeholder groups have been engaged at the national and sub national levels in all five countries during the PDF phase. Additional stakeholder consultations will be undertaken as the project is implemented in each of the five countries. Table 1 outlines examples of key stakeholder groups at the 3 levels (global/regional, national, local) and their potential role in the project. For more detailed stakeholder analyses per country, see Annex A1 and A2, which contain a list of stakeholders consulted in each country and a report on the Stakeholder discussions in The Gambia.

Table 1: key stakeholder groups at the 3 levels (global/regional, national, local) and their potential role in the project.

| Level | Stakeholders | Potential role |
| --- | --- | --- |
| Global | GEF, UNDP-GEF, other IAs | Global guidance Project management Execution of funds M&E support Baseline development support Technical support Institutional support Lesson distillation and documentation |
| National (e.g., as part of an National Coordinating Committee (NSC)) | Government focal point, GEF OFP, national IA project staff, national (UNFCCC) climate change focal points, NGOs, Academics, Private sector partners, other development partners | Capacity development (trainee) Capacity development (trainer) Baseline development Support/outreach to local project participants Participation in project selection Participation in funding disbursal and management M&E |
| Local | Community members, NGOs, CBOs, local government, trade associations, others. | Capacity development (trainee) Local V&A assessment Project identification and proposal development Baseline development Implementation of adaptation activities M&E |

- Moreover, prior to the implementation of pilot/demonstration projects, targeted activities will be undertaken to raise stakeholder awareness of coastline change and climate change issues and the benefits that coastal communities can derive from strategies to address these issues within the wider context of integrated coastal area management. Subsequently, the successful implementation of the proposed pilot/demonstration projects depend on the active involvement of all stakeholders (community, governmental, non-governmental as well as private sector), and the effective supervision of implementation and subsequent monitoring. Stakeholder participation will be assured by the consultative arrangements established under the project, whereby each party stands to benefit from the implementation of agreed strategies.

- In order to ensure effective stakeholder involvement the project will establish mechanisms to empower and facilitate consultation with and between all national and local stakeholders. This will occur through the National Steering Committees that will be formed in each country as part of the implementation set up (see section below on Implementation Arrangements). The specific role of stakeholders, such as those identified above will be to:

- Undertake activities to raise stakeholders awareness of coastline change issues and the importance of implementing measures to address such issues within the wider context of integrated coastal area management

- Ensure that designed measures, strategies and guidelines are consistent with national needs, and that there is constant interaction between the regional, national and local levels to ensure that Regional Project Steering Committee work in partnership with national focal points and local stakeholders

- Place a priority on the delivery of effective capacity development activities at the regional, national and local levels, and facilitate the exchange of experiences and lessons learned at all levels.

### 1.5 Baseline analysis

- Before elaborating on the baseline for the project, it must be kept in mind that the GEF uses the same definition of an adaptation baseline to determine, in part, what may be eligible for GEF funding.  Under the SPA, there is also the normal baseline definition for global environmental benefits, meaning that there is a double baseline, though in practice there is usually a high degree of overlap between the adaptation and global environmental benefits baselines.

- GEF funds the incremental cost of those adaptation activities that generate global environmental benefits as well as the incremental cost of selected adaptation activities that are identified as high priorities by each country.  The baseline scenario for the suite of adaptation projects in each country consists of the sum of all baselines for each individual adaptation project, which cannot be known a priori.  In general terms, it can be assumed that the adaptation baseline is limited by barriers to adaptive capacity. These barriers may be technical in nature – a lack of knowledge of possible adaptation responses, for example, or institutional – for instance, inadequate community organization. Please delete this figure from all project documents.

- Adaptive barrier analysis undertaken during country consultations and regional technical workshops highlighted a variety of anthropogenic and climate-induced drivers of coastal erosion that need to be overcome in order to strengthen the resiliency of the West African coastal ecosystem to climate change.  For example, in Cape Verde and The Gambia, wide-open coastlines offer little buffer against intensive wave actions at present (and therefore is likely to pose a grave threat in a climate change future).  In addition, changes in precipitation intensity contribute to perpetuating pressures on coastal erosion. In Cape Verde, the latter is contributing to increased sedimentation from runoff requiring water conservation and other measures to reduce the speed of runoff. In the case of anthropogenic pressures on coastal ecosystem resiliency, numerous factors play a contributing role.  In Guinea Bissau, over-fishing is leading to the destruction of mangroves, and other natural barriers which are contributing to coastal erosion.  This in turn is undermining the stability of coastal ecosystems. The weak enforcement of regulations and lack of zoning (leading to unplanned human settlements) is further compromising ecosystem resiliency.  Uncontrolled sand-mining (for example, in the Gambia) and other maladaptive practices have led to over-extraction of beach sand. Eroded beaches offer in turn offer limited protection against salinity intrusion to irrigated- and marsh-lands, compromising crop productivity and exerting pressure on the biodiversity associated with marsh ecosystems.

- All projects to be funded will include (i) activities within a natural resources management context that generate global environmental benefits in biodiversity, and;  (ii) adaptation measures that provide other major development benefits i.e. water, energy, health and agriculture. But will that be enough to ensure an overall coordinated coastal area management effort relating to adaptation to CC and SRL? The following issues give a futuristic view of the region if the proposed project should not be implemented:

A. On a physical level:

- Some countries, such as Senegal and Gambia, are already experiencing rates of coastal erosion between 1-2 meters per year (refer national reports in UNDP Project Document Annex A5). Through the breaching of sand dunes due to increasingly variable rainfall and sea-level rise, flooding is frequently prevalent in low-lying coastal zones such as, for example, Nouakchott (Mauritania). Climate change, including sea-level rise will increase coastal erosion as well as lead to coastal flooding (from both an increase in ground water levels induced by sea-level rise as well as due to the likelihood of extreme events like storms).

- At present, vegetative cover along the coastline in the identified hotspots have been degraded for several (climate- and anthropogenic-driven) reasons. On the one hand, anthropogenic activities, particularly due to fuel wood demands (e.g. Guinea Bissau where mangroves are exploited to smoke fish) have reduced mangrove cover that otherwise function as a natural protective barrier to coastline erosion. Increased winds, as well as sand mining activities, have led to the shifting and/or degradation of coastal sand dunes, thereby undermining their effectiveness as physical barriers against flooding, and also as sedimentary stocks allowing for beach reorganization (e.g. Mauritania). The continuous increase in soil and water salinity (due to receding coastlines and sea-level rise in the entire region) is also contributing to the further degradation of mangroves thereby reducing their ecological role in the reproduction and handling of the coastal resources including aquaculture (e.g. Senegal). Compounded by soil acidification processes, there has been a reduction in the productivity and availability of cultivable lands. Receding coastlines from climate change, including highly variable precipitation and anticipated sea-level rise will contribute to an even greater abandonment of lower lands and consequently, increase the pressures on plateau lands which will undermine coastline ecosystem stability and escalate into inter-community conflicts.

- Existing coastal management measures include beach nourishment, the building of groynes and revetments, the banning of sand extraction from coastal areas, and the development of cracked stone as an alternative to sand for construction purposes. However, these existing or planned coastal defences are likely to prove inadequate in the face of projected SLR of up to 0.5-1 m (based on potential global mean values) by the middle and end of the 21st century. A beach nourishment project in Gambia has been of limited success at best; beaches extended by 140 m in 2003 have already lost up to 70 m to wave erosion, with 7 m of beach lost over two days in one area in early March 2006. Existing coastal protection measures are evidently inadequate as they stand, and will suffer more extensive and frequent failure as sea-levels rise. The loss of economically valuable ecosystem (biodiversity) resources in addition to coastlines housing tourist beaches, hotels, fish landing sites and other key sites will undermine livelihoods and national economies. The impacts of CC and SLR will also be exacerbated by anthropogenic drivers that reduce the resilience of coastal ecological and geomorphological systems. While some such drivers are already being addressed, greater efforts are required to increase resilience in the face of CC and SLR. Without further intervention adaptation to CC and SLR will be almost exclusively reactive and ad hoc in nature, and many communities will not be able to adapt in the timescales available to them. Consequently, without the interventions proposed through this project, the expectation is that the coastal ecosystem will be further degraded as climate change, including variable precipitation and sea-level rise manifests itself. The loss of economically valuable ecosystem (biodiversity) resources, in addition to, coastlines housing tourist beaches, hotels, fish landing sites and other key sites will undermine local livelihoods and the national economies. The impacts of climate change and sea-level rise will also be exacerbated by anthropogenic drivers which reduce the resilience of coastal ecological and geomorphological systems. Without further intervention adaptation to climate change and sea-level rise will be almost exclusively reactive and ad hoc in nature, and many communities will not be able to adapt in the timescales available to them.

B. On a policy, legislation and institutional level.

- All countries concerned have in place a suite of laws and regulations relating to environmental protection and management (see summary reports in Annex A5 in UNDP Prodoc), and have ratified relevant international environmental conventions (e.g. UNFCCC, Biodiversity, Convention on the Law of the Sea, Abidjan Convention on the Protection and Development of the Marine and Coastal Environment, Conservation of Migratory Species). Steps are being taken towards the harmonisation and integration of coastal management activities and regulations, for example by:

- Setting up an inter-ministerial committee in charge of the development of the inshore region (Mauritania);

- Inserting a section relating to “Management of the Coastal Zone, Rivers and Wetlands” in national environmental legislation (Gambia: Section 30 of NEMA Act);

- Creating a Directorate General for the Environment responsible for coordinating environmental policies and implementing a National Environmental Action Plan (Cape Verde);

- Developing a Coastal Planning Programme and undertaking coastal mapping (Guinea Bissau, with support from IUCN); and

- Developing National Adaptation Plans of Action (all countries).

- Nevertheless, there is considerable fragmentation between different government agencies and departments, and little policy integration across sectors, with departments operating independently and often in conflict with one another, resulting in maladaptive practices. Moves towards integrated watershed management and programmes such as the ICAM initiative in The Gambia do represent increasing integration in environmental management, but these tend not to include considerations of future climate change. There is awareness of climate change in government departments and agencies with mandates of environmental management, but detailed knowledge of the science of climate change is often lacking, partly due to the lack of availability of information from international scientific research programmes. As a result, awareness of climate change and SLR and their potential impacts is not matched with the capacity to design policies that can address these impacts in a meaningful fashion.70.	A number of initiatives sponsored by bodies such as UNDP, UNEP, IUCN and IBRD focus on conservation, biodiversity, rehabilitation of degraded lands, and watershed management in the five countries participating in the ACCC project. These initiatives complement the activities of national governments. In addition, UNDP has provided assistance in the preparation of National Communications and the National Adaptation Plans of Action (which are still in a very early stage). However, there has been little focus on implementing adaptation projects at the local level, or addressing the impacts of CC and SLR on coastline change. Coastal issues have been addressed through activities such as the UNDP sponsored project Combating Living Resource Depletion and Coastal Area Degradation in the Guinea Current LME through Ecosystem-based Regional Actions and the UNEP sponsored project Reduction of Environmental Impact from Coastal Tourism through Introduction of Policy Changes and Strengthening Public-Private Partnerships.

- Other regional programmes include:

- Protection of the Canary Current Large Marine Ecosystem (UNEP: all 5 countries);

- Senegal River Basin Water and Environmental Management Programme (UNDP/IBRD: Senegal and Mauritania);

- Enhancing Conservation of the Critical Network of Sites of Wetlands Required by Migratory Waterbirds on the African/Eurasian Flyways (UNEP: Mauritania, Senegal, Gambia +_others);

- Desert Margins Programme (UNEP: Senegal); and

- Biological diversity conservation (UNDP: Mauritania and Senegal).

- However, projects and programmes implemented to date have focused on addressing problems within a framework that essentially assumes “stationary” climatic conditions and generally do not factor in higher sea-levels or changes in climatic parameters. Activities under the current baseline therefore may serve to enhance biodiversity, reduce sedimentation or coastal erosion and improve livelihoods in the short term, but are likely to be undermined by climate change and its impacts in the medium to long term.  Where remedial measures have been implemented to counter coastal erosion, measures have not taken into account anticipated long-term climate change effects.  In Cape Verde, solutions to coastal erosion have been short-term and misdirected, but politically attractive (for example, temporary measures to protect a building threatened by erosion) without adequate reflection of coastal dynamics that dictates the underlying effectiveness of the response strategy.  Solutions have thus been limited to addressing the impacts rather than the root causes of vulnerability to coastline erosion, with limited, if any, consideration of climate change effects.  In The Gambia, as in most of the other countries, resource constraints have been an issue limiting the type of, and extent of, implementing long-term solutions.  Climate-resilient management of coastal ecosystems have therefore either not been promoted or have been delegated as secondary issues (where poverty related issues, such as poverty alleviation programs have taken precedence).  Insufficient human and institutional resources, lack of technical knowledge and the absence of adequate legislation have also contributed to undermining adaptive capacity to coastline erosion, and therefore coastal ecosystem resilience in the context of climate change, in all five countries.

42. Moreover, the country assessments undertaken during the preparatory phase, including stakeholder discussions, highlight fragmentation between different government agencies and departments, and little policy integration across sectors. Institutions/departments operate independently and often in conflict with one another, resulting in maladaptive practices (e.g. The Gambia). Moves towards integrated watershed management and programmes such as the Integrated Coastal Area Management initiative in The Gambia represent a step towards increasing integration in environmental management at the institutional level. However, such initiatives do not include considerations of the long-term implications of climate change in the existing planning frameworks for coastal areas. This is clearly problematic for ensuring the stability of coastal ecosystems given that coastal erosion requires system-wide and longer-term solutions in order for remedial measures to be effective.

- In addition, while there is awareness of climate change in government departments and agencies with mandates of environmental management, detailed knowledge of the science of climate change and anticipated impacts on the West African coastline is lacking and consequently not taken into account in policy formulation. Coastal zoning regulations are either non-existent or weakly enforced.   Integrating of adaptation concerns into policies and programmes will aim to sensitise policy to include climate change concerns, reducing the likelihood of maladaptive practices that exacerbate vulnerability of social, ecological and geomorphological systems to climate change, coastal erosion and sea-level rise in the name of short-term economic development.

C. Monitoring and Capacity building.

- Current expenditure on monitoring of environmental change and data collection and analysis is extremely low, and further spending is often prevented by caps on government expenditure under the terms of structural adjustment programmes. Nonetheless, limited national capacities do exist for environmental monitoring and data analysis, for example using GIS technology. Some climatic records are held government departments, focusing on a few parameters such as rainfall and temperature, but detailed records of more complex variables such as stream flow and sediment transport are few in number. While awareness of coastal hazards is high due to the proximity of settlements and livelihoods to such hazards and their impacts, appreciation of the potential impacts of CC and of projected SLR is low. Communities are therefore poorly prepared for coping with changed climatic and environmental conditions, which will increase the risk of further coastal erosion from extreme events lead to increased loss of ecosystem services in addition to mortality and economic losses. ICAM programmes and measures are currently poorly developed in all of the five participating countries, with few measures having been implemented, the relevant regulatory frameworks fragmented across different sectors and government departments, and laws often not applied or enforced.

- Despite existing weakness, the above programmes, measures and regulations do provide a foundation onto which adaptation measures may be grafted, alongside measures to strengthen ICAM targeted particularly at the institutional level. Regional programmes sponsored by agencies such as UNDP also provide a starting point for the development of ICAM.

## PART II: Strategy

### 2.1 Project Rationale and Policy Conformity

- The approach outlined here for implementing adaptation activities is designed to be part of the wider GEF priority to pilot a strategy to implement climate change adaptation activities. Financing for the ACCC project is from the new GEF Strategic Priority “Piloting an Operational Approach to Adaptation”, described in GEF Council document GEF/C.23/ Inf.8. The project lies within GEF Operation Programme 2 (Biodiversity). The time frame for implementation of the project is four years.

- This project seeks to reduce the vulnerability of coastal communities in the participating countries to the different impacts of climate change on coastal regions. An integrated approach will be adopted for the development and implementation of effective adaptation strategies. The strengthening of existing networks for monitoring sea-level and climate, as well as the improved access to data, will also be addressed. Towards this end, various regional and international expertise will be drawn on to complement the objectives of the project through the strengthening of a regional observing network for sea-level change and other ocean parameters, including the use of remote sensing in coastal areas. The project will therefore provide participating countries with not only a comprehensive understanding of their vulnerability to climate change but also go beyond prioritization of adaptation options by implementing activities that lay the foundation for an incremental strengthening of their adaptive capacities. These could then be merged in a strategy that is integrated in the national development plans. The results of this project will also be integrated in the coastal zone management plans that will take into account future trends and impacts of climate change.

- As the impacts of climate change will be felt in a context where the expertise, financial and technical resources are limited, developing adaptation capacity and technology transfer, as well as broad stakeholder involvement, is an important component during both project design and implementation. Key policy barriers will be targeted and the project will implement country driven adaptation strategies that are appropriate in the long-term as required by the SPA guidelines.

- The lack of coordination of planning mechanisms, contradictory legislation and poor communication between government departments were identified as major constraints to the sustainable development and use of the coastal environment by country experts in the first phase of the African Process. In particular, it was noted that weak inter-sectoral coordination and management has contributed to increased coastal erosion.

- This project aims at addressing these issues and contributing towards the implementation of more effective and integrated approach to coastal area management. To increase the integration of coastal area management in a sustainable way, coordination mechanisms and legislative tools need to be improved, and legal, technical and institutional capacity needs to be strengthened. Broad stakeholder involvement and public awareness also needs to be increased, and sustainable financing mechanisms need to be defined.

- Lead by UNDP-GEF, in close collaboration with UNESCO/IOC and under the direction of the GEF operational guidelines for the SPA, the project activities will be implemented according to each country’s specific conditions and priorities to address anticipated climate change impacts on coastal regions as identified during the recently concluded PDF B phase (see Country reports in Annex A5). The inclusion of a diversity of socio-economic settings, through this regional project will also provide a meaningful basis for lesson learning, replication and up-scaling. The project will focus on relatively discrete geographic regions – e.g., coastal ecosystems– to ensure synergies among projects leading to greater and more measurable impacts, but also to identify policy lessons more confidently.

- The criteria used to select pilot site and identify adaptation measures (see national reports for details on the pilot sites) are guided by GEF operational guidelines for the SPA and the GEF Instrument, which establishes the principle of incremental reasoning. This means two things – firstly, that GEF funding will be used to fund a subset of all possible adaptation interventions, namely those which satisfy the criterion of GEF funding through the provision of global environmental benefits; and secondly, that GEF funding will be only for that component which is deemed incremental in facilitating “adaptation” to climate change including variability. Consistent with the concept of incremental costs, adaptation interventions, which do not generate global environmental benefits, are expected to be funded through sources of co-financing.  While this project provides a list of potential adaptation measures to be piloted, a final decision on the type of measures to be implemented will be made during the inception meeting for the full size project (approximately in Jan/Feb 2007). The principle of incremental reasoning will be strictly adhered to in the selection of projects to be financed through SPA. Other activities that also contribute to improving adaptive capacity but do not lead to global environmental benefits will be financed through co-financing. UNDP-GEF (HQ), through its Capacity Development and Adaptation Cluster will provide the necessary guidance to ensure that the principles of the SPA guidelines are adhered to.

The GEF Alternative can be described as follows:

A. The project will increase the adaptive capacity of ecosystems through measures designed to reduce anthropogenic stresses on globally significant resources such as biodiversity habitats and threatened species of plants and animals. ACCC activities will increase the resilience of coupled social and ecological systems in the face of climatic variability and change. The amelioration of anthropogenic climate change drivers of coastline change, including measures to reduce vulnerability to future CC and SLR, will be the focus of this project. As a result of ACCC activities, it is anticipated that coastal erosion due to climate change driven factors will be reduced and that communities will be better able to plan for and adapt to climate change driven coastline change, relative to the baseline conditions. Climate-resilient sustainable livelihoods will be promoted, and these will be much less likely to be undermined by CC and SLR, securing longer-term sustainable economic development. As a result of changes to planning and construction practices and styles, coastal squeeze will be reduced. Combined with other measures to reduce stresses on ecological and geomorphological systems, ecosystems and biodiversity will be conserved, with global environmental benefits and benefits to local livelihoods. Rehabilitation and preservation of key resources such as mangroves will provide a biological reservoir, which will enable “natural” ecosystem adaptation (e.g. through range shifts) to take place. This is especially important at the extreme edge of an ecosystem’s range, as is the case for the mangroves of Senegal and Mauritania. Preservation of mangroves will sustain habitats for a large number of species, some of which are threatened at the global level.

B. Through the integration of climate change concerns into policies and programmes, the project will sensitise policy makers on the risks posed by climate change and the necessary conditions for adaptation. This will be in addition to the contribution the project will have in reducing the likelihood of maladaptive practices that exacerbate vulnerability of social, ecological and geomorphological systems to climate change, coastal erosion and sea-level rise in the name of short-term economic development. Communication between departments and agencies and between policy makers and coastal communities will be improved, with greater stakeholder involvement in policy development and implementation. Tourism, development and conservation zones will be more clearly delineated, facilitating more effective coastal zone management. Regulatory frameworks will be strengthened and enforcement mechanisms developed, resulting in reduced pressure on coastal systems by inappropriate development. There will be a greater awareness of climate change and sea-level rise in the policy community, which will encourage the inclusion of change and sea-level rise considerations into new initiatives.

C.  Through improved monitoring of coastline change, climatic trends and environmental conditions, deliberative, anticipatory adaptation initiatives can be implemented, leading to adaptation measures that will be more acceptable to communities with a greater awareness of the risks associated with CC and SLR. Regional integration of monitoring systems will provide opportunities for bilateral and multilateral cooperation in the area of adaptation and coastal zone management. Adaptation activities will build on existing ICAM related activities, and existing ICAM programmes and institutional frameworks will be strengthened through a combination of GEF funding and co-financing. The project will develop links with existing programmes (see above) in order to ensure that activities across different projects and programmes are complementary, and to avoid the unnecessary replication of activities. The project will develop ICAM within the context of existing activities, and will in turn provide an ICAM context within which ongoing activities can continue.

### 2.2 Incremental Costs

- From the SPA component of the ACCC programme budget, US$ 2,091,000 of GEF funding is earmarked for piloting projects that reduce ecosystem vulnerability and/or exposure to the impacts of climate change and SLR. These projects will build on existing ecosystem services and coastal management activities. Links will be developed with existing projects and programmes, for example the Integrated Coastal Area Management Project in The Gambia. There are few or no existing activities specifically designed to address adaptation to future climate change and SLR at the local level. The US$ 4,000,000 for this outcome will therefore represent an incremental cost on a near-zero baseline. Co-financing for this activity is also expected of about US$ 2,000,000.

- US$ 275,000 of GEF funding will be matched by US$ 4,000,000 from co-financing to build on existing national frameworks for integrating and integrating adaptation into policy.

- Co-financing for improved monitoring of coastline change, climatic trends and environmental conditions will build on existing monitoring capabilities, and the US$ 4,000,000 earmarked for this outcome will make a significant difference to the operational activities of monitoring networks, the capacity for data analysis and identifying regions where urgent action needs to be taken. GEF funding of US$550,500 will focus on awareness raising and training of community members on long term response strategies limit or adapt to coastline erosion.

### 2.3 Consistency with the objective of the GEF Operational Strategy, Focal Area(s), Operational Programme, and Strategic Priority.

- The project is consistent with the GEF strategic priority “Piloting an Operational Approach to Adaptation (SPA), as the overall objective of the Full Project is the implementation of pilot/demonstration projects that address the impacts of climate change, including the ‘implementation of restoration, protection and adaptation measures in identified hotspots and sensitive areas’ that are consistent with and integrated into national and regional policy and sustainable development planning.  Only soft interventions will be subject to GEF funding; if important public works are necessary, they will have to be financed through non-GEF funding; to this effect, an SCCF proposal is currently being elaborated. The project will generate global environmental benefits by increasing the capacity of the participating countries to design and implement sustainable strategies in the Biodiversity focal area in the face of changing climatic conditions.  This will complement existing and planned GEF interventions in the Biodiversity focal area.

- In promoting measures that set aside ecologically sensitive mangroves, fostering improved management of the resources in wetlands and island ecosystems and promoting replication based on the experiences and lessons learned, the project will contribute to the conservation and sustainable use of biological diversity of coastal and marine resources. This is consistent with OP 2 (Coastal, Marine, and Freshwater Ecosystems).

### 2.4 Fit with GEF portfolio

- The ACCC project is the first full size SPA-funded regional project that pilots and demonstrates measures to reduce vulnerability to climate change including variability at the community and national level in coastal regions. The project is important to the GEF portfolio for several reasons. Firstly, it will provide lessons in designing and implementing screening criteria for projects that are relevant to all GEF-funded community-based adaptation-related activities. Secondly, the diversity of adaptation-related activities emerging from the ACCC will provide valuable lessons on the factors that must be taken into consideration in project design when attempting to improve adaptive capacity and/or reduce vulnerability to climate change drivers. At the end of this pilot, lessons learnt will permit a more a systematic approach to integrating climate change risks in GEF focal areas such as biodiversity.

### 2.5 Project Goal, Objective, Outcomes and Outputs/activities

- The Goal of the project, dictated by the GEF Council paper GEF/C.27/Inf.10 (Operational Guidelines for the Strategic Priority “Piloting an Operational Approach to Adaptation”), is “to reduce vulnerability and to increase adaptive capacity to the adverse effects of climate change in the focal areas in which the GEF work”.  As the contribution to the goal, the Objective of the project is: to develop and pilot a range of effective coping mechanisms for reducing the impact of climate change induced coastal erosion in vulnerable regions in five countries in West Africa.

- An adaptive capacity barrier removal analysis outlined in each of the national assessments undertaken during the preparatory phase (see Annex A5) indicated the need for interventions designed to achieve three outcomes in support of the project objective.  These are:

- Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts;,

- Climate change and adaptation issues integrated into coastal area management policies and programmes;

- Enhanced monitoring of coastal erosion and capacity building in coastal management and planning

- The project outcomes are framed in the context of the eligibility criteria for SPA-funded adaptation projects.  That is, the design of this project contains the following components:

- A pilot/demonstration component that contributes to improving adaptive capacity (through demonstration activities) and leading to global environmental benefits in biodiversity

- Policy change/integration of climate change and adaptation issues into integrated coastal area management policy

- Capacity building on tools for increasing the ability to plan for, and respond to, climate change induced coastline erosion,

- Furthermore, the outcomes are consistent with the UNDP-GEF Adaptation Policy Framework philosophy that adaptation occurs through public policy-making and decisions made by stakeholders, including individuals, groups, organizations (government agencies, non-governmental organizations, and private companies) and their networks. Extensive stakeholder consultations in the participating countries, including at the pilot sites as well as national level, forms the scope and direction of this proposal. Please refer to the details in the Annexes in the UNDP Project Document (Annex A1 (for example of consultations in The Gambia) and the Country Reports in Annex A5).

To achieve the objective of the project, four Outcomes will be pursued. Outcome 4 is not really an outcome, but the establishment of an enabling environment for the project to function. It will be explained here, but not further elaborated (e.g. in the LOGFRAME or incremental costs calcultation).

OUTCOME 1: Pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts implemented.

- To counteract the problem described in the baseline, the project will increase the adaptive capacity of ecosystems through measures designed to reduce anthropogenic stresses and preserve habitats, resulting in the preservation of threatened species of plants and animals. For example, the Bijagos Archipelago in Guinea Bissau represents some 1% of the world’s bird species and is home to 11 species of primate, 85 species of reptile and 31 amphibian species. Rehabilitation of mangroves on the Islet of Porcos, also in Guinea Bissau, will extent the habitat of five species of turtle, two of which (Atlantic green and loggerhead) are threatened at the global level. Preservation of the marine environment in the vicinity of Nouakchott will preserve an important fish breeding area. The Niayes region of Senegal is home to 419 floral species, representing 20% of the known floral species of Senegal and, along with coastal areas in Mauritania, houses the most northerly mangroves along the Atlantic coast of Africa. Protection of the Niayes will sustain important bird habitats, which support threatened species such as the avocet, white pelican and Caspian swallow. A biodiversity inventory covering all the participating countries at the national and site level is presented in the Executive summary, Box 1 and Table 1 (p. 12 – 18).

- The ACCC project will support the implementation of specific demonstration measures in pilot sites that are designed to enhance the adaptive capacity of ecosystems to climate change.  In order to ensure cost effectiveness, activities will be implemented in areas that have been identified to be vulnerable to climate change, including variability, induced coastal erosion and where there is high potential to general global environmental benefits (in the biodiversity focal area).

- During the PDF-B process, several geographic regions (see table 1 Exec. Summ.) in each country were identified through an assessment on vulnerability to climate change and consultative process where pilot/demonstration activities would be implemented. The process of identification of both where to implement activities and the typology of measures that will facilitate improved adaptation followed a multi-step process guided by the principles of the Adaptation Policy Frameworks (APF):

- In each of the pilot countries, climate change vulnerability assessments were reviewed to identify those coastal regions of highest vulnerability.

- Regions having high potential to deliver global environmental benefits, based on considerations of the GEF focal areas and assessments such as the potential rates of coastal erosion and information such as levels of globally significant biodiversity was identified.

- An overlay of regions identified by these two criteria indicated priority ecosystems or landscapes adaptation projects (see Site Selection Figure 2, below, for a graphical representation of this process).  This baseline criteria was supplemented by consideration of the following additional factors: scale of erosion, importance for biodiversity, the population at risk, economic value at risk, the role of resources to the local community and national development as well as government priority (for details of the scoring results used to identify pilot regions, please refer to the Country Reports attached to Annex A5).  Additional criteria considered included issues such as the existence of social unrest, or pre-existing adaptation interventions, to ensure effectiveness of interventions and the avoidance of duplication of efforts.

- The criteria described in step (iii) were used to select within the ecosystems and landscapes identified by steps (i) and (ii) one or more locations that will serve as the focus of pilot demonstration projects.  The pilot activities will be implemented in a selection of the identified locations by UNDP CO, together with support from the Regional Project Steering Committee (supported by UNDP-GEF and UNESCO/IOC). The aggregate impact of the projects in the locations will be to improve the adaptive capacity of ecosystems to climate risks.

Output 1.1: Pilot demonstration projects reduce climate driven coastline erosion implemented.

- In addition to contributing to the reduction of current coastal erosion rates, pilot demonstration activities will be implemented to strengthen coastal ecosystem resiliency to anticipated climate change effects. Measures to be implemented are aimed at reducing the impact of climate driven increased intense wave activity, changes in the sediment budget due to changes in upwells and increasingly variable precipitation and sea-level rise. A suite of ‘soft’ demonstration measures targeted specifically at building ecosystem resilience in these anticipated climate driven effects will form the foundation of the pilot activities.

- The activities in support of the achievement of this outcome (see 1.1.1-1.1.6) will increase the resilience of coupled social and ecological systems in the face of climatic variability and change. As a result of ACCC activities, it is anticipated that coastal erosion will be reduced and that communities will be better able to plan for and adapt to coastline change. Sustainable livelihoods will be promoted, and these will be much less likely to be undermined by climate change and SLR, thereby contributing towards securing longer-term sustainable economic development. As a result of changes to coastal planning practices, coastal erosion will be reduced. Combined with other measures to reduce stresses on ecological and geomorphological systems, ecosystems and biodiversity will be conserved, with subsequent global environmental benefits and benefits to local livelihoods. Rehabilitation and preservation of mangroves will provide a biological reservoir, which will enable “natural” ecosystem adaptation (e.g. through range shifts) to take place. This is especially important at the extreme edge of an ecosystem’s range, as is the case for the mangroves of Senegal and Mauritania. Preservation of mangroves will sustain habitats for a large number of species, some of which are threatened at the global level. In this context, the specific activites are:

1.1.1	Stabilised coastal erosion through rehabilitation of indigenous vegetative cover.

1.1.2	Soil conservation measures implemented to reduce runoff (SPA funded; to be implemented in Vile das Pombas and Ribiera da Lagoa (Cape Verde); Bald Cape to Cape Point, (The Gambia)

1.1.3	Planting of local species for the stabilization of sand dunes (to be implemented in Bald Cape to Cape Point (The Gambia); Nouakchott (Mauritania).

1.1.4	Alternative livelihoods (beekeeping, ecotourism, forest management) developed (to be implemented in Allehein to Bald Cape (The Gambia); Varela Beach and Bubaque Island (Guinea Bissau); N’Diago (Mauritania)).

1.1.5	Mangrove reforestation (to be implemented in Porcos Island (Guinea Bissau); Djifère to Palmarin, Fimela, Niodor, Palmarin, Sokone namely (Senegal); N’Diago (Mauritania)).

1.1.6	Dissemination of new technologies (especially in energy) to release the pressure of degradation of ecologically important mangrove resources.

- The above activities will be supported by the following additional actions:

- Development and dissemination of project promotional and informational material.

- Conducting a project awareness raising (inception) workshop for local authority, community leadership, government departments, NGOs and other opinion leaders in the pilot area.

- Establishing an adaptation to climate change committee in each country, comprising of community leadership and representatives of relevant government departments, to guide the identification and implementation of pilot adaptation to climate change projects.

- Training of communities on the anticipated threats of climate change and potential adaptation measures that strengthen ecosystem resilience.

- Work with communities and other partners to develop and implement coastline ecosystem specific adaptation to climate change pilot projects in the selected pilot sites.

- Provide funding and technical backstopping support to approved projects.

- Regular monitoring of the pilot projects.

OUTCOME 2: Climate change and adaptation issues and coastal area management policies and programmes integrated

- SPA resources will contribute towards benefits such as improved communication between departments and agencies and between policy makers and coastal communities on climate change risks management. Without SPA resources, with greater stakeholder involvement in policy development and implementation for this purpose would not be possible. Resources will contribute towards delineating tourism, development and conservation zones, and facilitating more effective coastal zone management in the context of climate change risks management needs. Together with additional co-financing (catalyzed as a result of the SPA intervention), regulatory frameworks will be strengthened and enforcement mechanisms developed, resulting in reduced pressure on coastal systems. As a resul t of this initiative, there will be a greater awareness of climate change and sea-level rise in the policy community, which will encourage the inclusion of change and sea-level rise considerations into new initiatives.

Output 2.1	Climate change issues and coastal management activities and programmes across sectors integrated.

- Coastal erosion is triggered by, and expected to worsen due to, natural factors such as sea-level rise and increasingly variable precipitation. In addition, poor management, inappropriate land use, conflict of interests, lack of coordination between different sectors and/or levels of government also contribute to the problem.  Consequently, integrated coastal zone management is promoted as a modality to reduce the vulnerability of coastal zones to both natural and anthropogenic drivers. This has been endorsed through the Maputo and Cape Town Declarations whose signatories recognized the need for integrated coastal zone management.

- In support of institutionalizing a pragmatic approach to addressing climate, and anthropogenic driven coastal erosion, several activities have been identified (through stakeholder consultations in each country). The adaptation benefits of these activities will be in terms of contribute towards cross-sectoral integration of national policies that incorporate long term issues, such as climate change driven coastal erosion. Benefits will be realized from this project through the introduction and enforcement of specific coastal regulations that take into account climate change concerns on coastlines, improved technical knowledge and understanding of the causes and effects of climate change-induced coastline change in the participating countries and regional cooperation to share knowledge and experiences in addressing climate change impacts. These achievements are unlikely to be realized if SPA funds are not available.

- The proposed activities in support of this outcome include:

2.1.1	Development and implementation of integrated coastal and watershed management plans/programmes which take into account climate change risks.

2.1.2	Formulation and implementation of zoning regulations for sea-level rise sensitive coastal settlements (for example, to be implemented in Tanbi Wetland Complex, The Gambia).

Output 2.2	National policies and programmes to facilitate adaptation to climate change in coastal regions designed.

- The benefit of the activities in support of this output includes the development and strengthening of regulatory frameworks and enforcement capabilities to reduce climate change-induced driven impacts of coastal erosion and maladaptive practices. Significant co-financing contributions will be catalyzed for the achievement of this particular output as it is necessary that national polices also tackle non-climate change related risks. SPA resources, together with co-financing, will be used to implement the following activities:

2.2.1	Review existing national plans and policies with a view to to integrating climate change risks

2.2.2	Conduct national consultations to produce a draft action plan for addressing coastal erosion for review and implementation by policy makers.

2.2.3	Empower decentralized governmental agencies and local communities to enforce laws that will facilitate improved adaptation to climate change in coastal regions.

Without the availability of SPA resources, these activities, which specifically focus on addressing climate change risk management, would not take place.

Output 2.3	Successful community level approaches to mitigate and adapt to coastline erosion replicated.

- Currently, efforts to remediate coastal erosion in each of the countries are ad hoc and reactive. There are limited organizational structures or mechanisms to ensure coordination and avoidance of duplication. Moreover, without intervention, there is likely to be wastage of efforts and resources and minimum spill-off effects. Communities are unlikely to maximize opportunities to learn from and benefit from each other. This project, with funding from SPA & co-financing, will make an valuable contribution to facilitating adaptation in coastal regions in not only the participating countries, by ensuring the lessons learnt through the pilot activities are catalytic in areas not covered by the demonstration activities. Moreover, SPA resources will contribute towards the dissemination of lessons of this project on adaptation to coastal impacts in other parts of the word.

- The above output will be achieved by the following activities:

    - Organization of exchanges and dialogue between policy-makers as well as communities on the impacts of climate change on coastal erosion and adaptation activities.

    - Awareness-raising of pilot projects through local media and other appropriate channels.

2.3.3	Creation of focal points for communities seeking guidance on designing and implementing adaptation measures (including assisting with securing co-financing).

OUTCOME 3. Monitoring of coastal erosion and capacity building in coastal management and planning enhanced

- In the evaluation of their adaptive capacity to face the impacts of climate change, the participating countries highlighted a weakness in their human and technical resources. Moreover, countries like Guinea Bissau, expressed a need to compile monitoring data to better assess the severity of the issue of coastal erosion in light of climate change and support to facilitate the formulation and implementation of appropriate adaptation measures.  The lack of availability of information of the extent of coastline erosion and lessons from international scientific research programmes on adaptation to climate change has constrained the capacity at the national and regional level to design policies which could effectively address coastal erosion. Current expenditure on monitoring of coastal erosion and environmental change through data collection and analysis is limited (if any), and further spending is often prevented by caps on government expenditure. Nonetheless, limited national capacities do exist for environmental monitoring and data analysis, for example using GIS technology. Some climatic records are held in government departments focusing on a few parameters such as rainfall and temperature, but detailed records of more complex variables such as stream flow and sediment transport are few in number. While awareness of coastal hazards is high due to the proximity of settlements and livelihoods to such hazards and their impacts, appreciation of the potential impacts of climate change and of projected sea-level rise is low. Communities are therefore poorly prepared for coping with changed climatic and environmental conditions which will increase the risk of further coastal erosion from extreme events and lead to increased loss of ecosystem services in addition to mortality and economic losses.  ICAM programmes and measures are currently poorly developed in all of the five participating countries, with few measures having been implemented, the relevant regulatory frameworks fragmented across different sectors and government departments, and laws often not applied or enforced. However, all the countries concerned have in place a suite of laws and regulations relating to environmental protection and management (see summary country reports in Annex A5 of the UNDP Project Document), and have ratified relevant international environmental conventions (e.g. UNFCCC, Biodiversity, Convention on the Law of the Sea, Abidjan Convention on the Protection and Development of the Marine and Coastal Environment, Conservation of Migratory Species). Steps are being taken towards the harmonisation and integration of coastal management activities and regulations, for example by

- Setting up an inter-ministerial committee in charge of the development of the inshore region (Mauritania)

- Inserting a section relating to “Management of the Coastal Zone, Rivers and Wetlands” in national environmental legislation (Gambia: Section 30 of NEMA Act)

- Creating a Directorate General for the Environment responsible for coordinating environmental policies and implementing a National Environmental Action Plan (Cape Verde)

- Developing a Coastal Planning Programme and undertaking coastal mapping (Guinea Bissau, with support from IUCN).

- Developing National Adaptation Plans of Action (all countries)

- Existing coastal management measures include beach nourishment, the building of groynes and revetments, the banning of sand extraction from coastal areas, and the development of cracked stone as an alternative to sand for construction purposes. Despite existing weakness, the above programmes, measures and regulations do provide a foundation onto which adaptation measures may be integrated, alongside measures to strengthen ICAM targeted particularly at the institutional level. Regional programmes sponsored by agencies such as UNDP also provide a starting point for the development of ICAM. These programmes include

- Protection of the Canary Current Large Marine Ecosystem (UNEP: all 5 countries)

- Senegal River Basin Water and Environmental Management Programme (UNDP/IBRD: Senegal and Mauritania)

- Enhancing Conservation of the Critical Network of Sites of Wetlands Required by Migratory Waterbirds on the African/Eurasian Flyways (UNEP: Mauritania, Senegal, Gambia and others)

- Desert Margins Programme (UNEP: Senegal)

- Biological diversity conservation (UNDP: Mauritania and Senegal)

- This outcome seeks to achieve effective monitoring of coastal erosion and building capacity at the national level to implement adaptation measures. This will include project evaluations reflecting successful and sustainable project objectives and sharing of lessons learned. Results from the programme will be disseminated within and beyond the programme intervention zone through a number of existing information sharing networks, in particular, UNDP-GEF’s Adaptation Learning Mechanism (see Box 1)..

- The outputs and activities of this outcome will be guided through a regional approach by a Regional Steering Committee, led by UNESCO/\IOC. This component will be implemented, in coordination with national focal points to maximize benefits in the exchange of information, experience and expertise, and in building regional capacity for adaptation.  Adaptation activities will build on existing ICAM related activities, and existing ICAM programmes and institutional frameworks will be strengthened through a combination of GEF funding and co-financing. The project will develop links with existing programmes (see above) in order to ensure that activities across different projects and programmes are complementary, and to avoid the unnecessary replication of activities. The project will develop ICAM within the context of existing activities, and will in turn provide an ICAM context within which ongoing activities can continue.

Output 3.1	Capacity of institutions and human resources to develop and implement adaptation strategies and measures in coastal environment improved

- Output 3.1 will be the main mechanism for the delivery of capacity building activities to the participating countries. In particular, activities will contribute to the development of expertise in the application of climate and ocean models to monitor and forecast coastal erosion rates in light of changing climatic conditions. Local capacities need to be developed to identify and track underlying ecosystem resilience/vulnerability to climate change which in turn will support and catalyze improved implementation measures. The proposed activities will lead to trained local coastal resource scientists and managers in techniques relevant to promote adaptation to climate change in coastal and marine environments. Skills in climate change science, marine science, oceanography and adaptation alternatives for coastal regions are currently insufficient and must be developed.

- The proposed activities in support of the above output include:

3.1.1	Develop and implement national and regional training course and other capacity building activities in (a) Integrated Coastal Area Management and Climate Change impacts, and relevant Adaptation Techniques; (b) Integrating climate change concerns into coastal development programs and sectors.

    - Analysis of data and training in climate change science, oceanography and marine sciences to increase knowledge on reducing vulnerability to coastal erosion.

3.1.3	Establish Regional Steering Committee (RSC) to advise on measures to be implemented that will build capacity on adaptation measures in coastal regions as well as other needs of the project.

Output 3.2	Clearing-facility to capture, store, disseminate lessons and best practices  and information products established.

- Among the 5 countries, Senegal and The Gambia have already gathered some experience in addressing coastal erosion through sand dune revegetation, mangrove reforestation, coastal protection works (both “hard” structures (sea walls, groynes) as well as “soft” structures (e.g. beach nourishment)). Sharing experiences obtained through the implementation of the pilot activities through this project as well as beyond it will benefit all participating countries, and others.  It is important therefore to set up a mechanism through which this exchange of lessons learned can take place.

- This output promotes the exchange and dissemination of information, data and experiences amongst the participating countries with a view to support adaptive capacity building activities on coastline erosion from climate change.  It will contribute to the enhancement of awareness about the project, and understanding of its objectives and progress; capture of monitoring information and lessons emerging on coastal ecosystem management and innovative coastal management approaches. The clearing facility will then be used to transfer lessons and facilitate the replication of best practices. Linkages will be made with UNDP-GEF’s Adaptation Learning Mechanism so that the lessons on project design and implementation can contribute to informing and guiding future GEF project designs on climate change and coastal ecosystems in other developing countries with similar issues.

- The intended activities of this component are:

3.2.1	Web-based “clearing house” mechanism for monitoring of erosion and lessons learned established and operated

    - Project information materials including CDs, database, maps, papers, brochures, newsletters

    - Organize a forum after 2 years the implementation of this project to share lessons, exchange experiences, etc.

OUTCOME 4: Learning, evaluation, and adaptive management increased

- For effective coordination and management of the project, a mechanism should be set up. This mechanism has been described in the implementation arrangements. The running of this mechanism, its interactions with other project/programme management mechanisms in the country and with stakeholders in itself can be considered to be a form of learning and capacity building. The mechanism will ensure awarenessraising about the need for increasing adaptive capacities of communities and touched areas and for taking measures among policy makers and decision makers on various levels.

Output 4.1	Establishment of a learning mechanism for adaptive management.

- Setting up the project management mechanisms on regional and national scales, that will contribute to awarenessraising about climate change, adaptive management and the intentions of the project is an important step in creating an enabling environment for Adaptation activities. Stakeholders (be it planners, policy makers, interest groups, etc.) will have to be informed and involved in the project, to ensure a good uptake of information, changing attitudes and willingness to take action. The project management mechanisms will also ensure that lessons learned will not go to waste, but will be disseminated and documented in larger learning mechanisms, such as the Adaptation Learning Mechanism. The intended products and indicative activities of this component are:

    - Established project management mechanisms with clear mandates to promote learning for adaptation on all levels;

    - Network of stakeholders in Adaptation to Coastal Erosion established;

    - Organize periodic meetings for participating countries on training, exchanging information and views.

Output 4.2	Cooperation at the regional level in addressing climate change impacts on coastal area management enhanced.

- The countries involved in this project share a common coastline and are therefore dependent on the actions of each other to effectively address the root causes of coastal degradation. Given the similarities between the different countries concerned – either in the types of coastal zones and vegetation or in the underlying cause of coastal erosion, and experiences in combating coastal erosion, regional cooperation will be an added value in addressing the impacts of climate change in the shared coastal regions. Currently, no mechanism exists for such collaborative efforts to address coastal erosion issues.

- Cooperation among member countries will be promoted to deliver increased regional ecosystem management in light of to anticipated climate change impacts including sea-level rise. A regional network/Task Force will facilitate the exchange of information and cooperation in addressing climate change driven coastal erosion. This will include exchanging and sharing lessons on impacts and adaptation measures and raising financing to support collaborative activities in the region that reduce impacts. The proposed activities to achieve this output include:

4.2.1	Convening of regional forum between relevant coastal, urban planning and other policy makers in the participating countries.

4.2.2	Establishment of an inter-regional Task Force and/or network on adaptation to climate change impacts on coastal regions.

4.2.3	Develop cross-border adaptation initiatives through experience exchanges and development of transboundary projects and programs

### 2.6 Project Indicators, Risks and Assumptions

## Indicators

- The project indicators are discussed in detail in the Logical Framework (Refer also to Annex A4 and 5). The main indicators are:

- Number of newly constructed, rehabilitated coastal protective (soft and hard) systems. This includes for example, new number of developments with new materials/methods, set-back of new developments

- Length of coast protected, reduction in erosion rates, sediment loads, number of channels constructed, plant coverage in pilot sites (in HA), reduction in forest clearance in pilot sites, number and extent of fire belts, increase in forest cover

- Perceptions of efficacy and relevance of project outcomes, increases in household income, number and area extent of community conservation projects, number of households using new sources, wood consumption, number of stakeholder exchanges on climate change and coastal management.

- At least 25 information nodes (climate change and coastal management task force members, project staff, community members)

- Area coverage of coastal management systems, river and basin management schemes, number of plans addressing sea level rise (and climate change), number of policies & programs amended to address adaptation, and number of bilateral and multilateral adaptation relevant agreements

- Number of new sand mining sites per year (before and after project)

- GIS products that have been stored in country-selected repositories for general use by stakeholders

- Participation of governmental and private sector participants in workshops, number trained community members in management of coastal resources in the context of climate change and anthropogenic impacts

- Awareness of results of monitoring (number of media announcements on climate change and impacts on coastal regions and sea level rise)

## Risks

- The main risks for the implementation of the project are: (a) Conflict between coastal states with different political agendas results in an inability of countries participating in regional activities to cooperate at the level needed to achieve results.; (b) Pressing domestic economic and social issues such as poverty and human health issues imply that regional climate change and sea level rise impacts on coastal communities receive sub-optimal attention and investment; (c) There is sufficient numbers of regionally based experts to fulfil implementation needs of the project including building individual capacities in the region; (d) Participating countries will not be able to agree on the mechanisms necessary to achieve sustainability; and (e) Important local level stakeholders (communities, coastal managers, urban planners, tourism industry stakeholders) will see ecosystem based management efforts as being detrimental or unaffordable given their interests. Several other risks and their proposed mitigation measures have been noted in table 3 in the Executive Summary, p. 34. The project will have to find ways to put these mitigation measures in effect.

### 2.7 Expected global, national and local benefits

- The primary objective of the project is to preserve ecosystem integrity in the context of anticipated climate change impacts along the canary current coastline. The coastline is of global significance as it hosts a number of protected areas (PA) such as the Banc d’Arguin, Djoudj, Diawling, Saloum, etc. Although ecosystem integrity may be a necessary condition for the sustainability of these Pas, it alone is not sufficient.  The project makes an important contribution by ensuring that climate change concerns are better integrated with activities that support the management and use of globally significant biodiversity resources.  If adaptive measures to climate change impacts, including sea level rise, are not supported, these PAs are unlikely to realize, in the long term, the full benefits of measures implemented (under conventional biodiversity projects) to promote and manage globally important biodiversity resources. In particular, significant (and potentially irreversible) losses are likely to result in sensitive ecosystems.  The maintenance of ecosystem stability in light of climate change is therefore a necessary condition for the management of biodiversity in the production landscape, namely fisheries which is one of the main economic sectors for the targeted countries.  In promoting measures that set aside ecologically sensitive resources such as mangroves (for example, through the introduction and enforcement of zoning regulations), facilitating improved integrated management of coastal areas (including resources in wetlands and island ecosystems) and promoting replication based on the experiences and lessons learned, the project will contribute to the improved management and sustainable use of biological diversity of coastal and marine resources in several pilot sites in the West African region. The project will generate global environmental benefits by increasing the capacity of the participating countries to design and implement sustainable strategies in the biodiversity focal area in the face of changing climatic conditions. This will complement existing and planned GEF interventions in the BD focal area.

- The ACCC project will also simultaneously increase adaptation to climate change including variability.  This is a direct benefit in itself, both in terms of local benefits (reduced reliance on external technical assistance will strengthen economic development efforts) and global benefits (reduced levels of coastal erosion, maintenance of fish stocks, etc.)

- In addition, another indirect source of global benefits will be derived from policy changes by governments and donors; grantees and stakeholders taking action and achieving influence through greater awareness of global environmental issues and enhanced organizational capacity; and community members as advocates for global environmental issues.

- One of the most important impacts of the project will derive from actions that address the vulnerability of groups such as indigenous communities, who are frequently overlooked in many policy interventions.   Benefits are expected in primarily in the BD Focal area.  For example, in Mali, an SGP project worked with a group of seven villages in the southern Sahel to reverse desertification threatening local varieties of plant and animal species. The project not only undertook ecosystem restoration, but also demonstrated to the local authorities the capacity of the local people to sustainably manage their lands. These types of benefits will be amplified through the ACCC project, which focuses on similar issues but in the context of coastal regions.

### 2.8 Country Ownership: Country Eligibility and Country Drivenness

Country Eligibility

- All the proposed participating countries are eligible under paragraph 9(b) of the GEF Instrument. All the participating countries have ratified UNFCCC and are eligible for financial support under Annex 1 of the UNFCCC, and technical assistance from UNDP. Refer Section IV where the endorsement by national operational focal point can be found.

Country Drivenness

- In 2002, the UNEP/GEF MSP on the Environment Component of the New Partnership for Africa’s Development (NEPAD), “Capacity-Building Programme for the Development of Sub-Regional Environment Action Plans for the New Partnership for Africa’s Development”, was initiated with a view to facilitate the development of the NEPAD Environment Action Plan. In order to define priority areas for the NEPAD Action Plan, eight thematic working groups were established in the course of the MSP, including one on Marine, Coastal and Freshwater Resources. Following the recommendations of the Coastal/Marine working group, which met in Abuja, Nigeria, 24-25 February 2003, the NEPAD GEF MSP identified three projects of the African Process as core activities of the Environmental Action Plan: Project 1: Mitigation of coastal erosion and restoration of degraded areas in sub-Saharan Africa; Project 2: Supporting the development and implementation of ICAM in sub-Saharan Africa; Project 3.Assessment of the vulnerability of sub-Saharan coastal zones to the various impacts of climate change (including sea-level rise). The African Union adopted the NEPAD Environment Action Plan at its Summit in July 2003, Maputo.  As a result of informal regional consultations amongst the five countries, IOC of UNESCO was requested by the Government of Senegal, acting as Coordinator for the NEPAD Environment Initiative, to adapt the three NEPAD projects3 into a single regional project drawing on the complimentarity, commonality and inter-linkages of the issues being addressed, i.e. coastal erosion, climate change vulnerability, and Integrated Coastal Area Management.  The resulting Project concept was identified by the African Ministerial Conference on the Environment (AMCEN) as a one of the priority projects of NEPAD Action Plan to be implemented.

- The project was endorsed by the Focal Points designated by the five participating countries during a First Regional Planning Meeting of the NEPAD Project in Dakar, Senegal, on 3-5th March 2004. In addition to endorsing the proposal, the participating countries recommended that the project proposal should be further defined and developed, and that to this end the outline concept was submitted to GEF for PDF-B funding. The PDF B activities have now been completed and this proposal reflects the key outcomes of this preparatory phase.

### 2.8 Sustainability

- Sustainability is an integrated part of the project design, although it is not intended that the project, in and by itself will establish a sustainable ecosystem management framework. Provisions to facilitate the sustainability of such a framework will be engendered during the implementation phase, The sustainability of the project’s results will mainly depend on the effectiveness of stakeholder involvement, the appropriateness of the implementation of ICAM guidelines to the national and local contexts, adequate technical, legal and institutional capacity and expertise at the national level, and on the long-term political and financial commitment of decision makers.

- The long-term viability and sustainability of the project will also depend greatly on the extent to which national institutional capacities can be built through the implementation of the pilot activities. A number of measures are planned, to set the grounds for ensuring long-term institutional, political and financial sustainability. A phased approach will enable interventions to be scheduled within the absorptive capacities of the participating countries. A key strategy of the project in engendering institutional sustainability is to create partnerships at regional levels between institutions.  National institutions responsible for continuing the activities that will be started under the project will be identified, as will regional and international centres of expertise, which will provide the locus for capacity building services. The strategy is expected to greatly enhance prospects for assuring institutional sustainability, building on existing regional competencies.

- The scoping exercise conducted during the PDF B process will be expanded to identify the necessary capacity needs for national institutions, which will provide the basis for the development and implementation of core activities under this project. This will be updated periodically, based on the outcomes of questionnaire surveys of key stakeholders and independent evaluations. Training of capacity at the community level will be supplemented through participation in workshops, information exchange between communities and institutions, to be facilitated by the project management unit.

### 2.9 Replicability

- Replicability will be one of the criteria used in the selection of pilot project sites, and it is intended that the selected projects will demonstrate that adaptation planning and assessment can have practical outcomes that provide tangible benefits, that can be fully integrated into wider national and regional policy and sustainable development planning. The outputs and outcomes of all project components will have important demonstrative value with significant potential for replication at national, sub-regional and regional levels, and in particular in those countries where the improvement of coastal area management is recognized as an urgent need but which face similar constraints.

- Replicability will be achieved at the global level (e.g., through the provision of key lessons for integrating), the national (e.g., through the development of national capacity to support adaptation activities) and the local level (e.g., where new know-how among communities, local NGOs and CBOs can encourage a scaling up of adaptation to climate change activities).

- To lay the foundation for the replication of the approach and transfer of lessons from the project, a programme-wide capacity development effort will be initiated at the global, the country and the local level. This will be linked to UNDP-GEF’s Adaptation Learning Mechanism.

- Finally, though it is beyond the scope of the ACCC project, replication of adaptation activities will ideally occur over the long term through the implementation of new and emerging adaptation funds.

## PART III: Management Arrangements

- Implementation, execution and coordination of the Project will be carried out as described below. In brief, several activities are envisaged including the establishment of a Regional Project Steering Committee, the establishment of a Regional Coordination Unit (which includes the appointment of a Regional Project Coordinator, procurement of additional equipment and other requirements to upgrade the project unit), the convening of Regional Steering Committee meetings (including reports on Project Implementation and Progress), the establishment of national execution mechanisms, organizing coordination between Implementing and National and Regional Executing Agencies including consultation and signature of agreements, and participation of the Project in relevant International Conferences. TORs for personnel that need to be recruited are included in Annex A8.

### 3.1 Implementing Agency

- The Project will be implemented by UNDP. The UNDP-GEF, through its Capacity Development and Adaptation Cluster (CDAC) will be overall responsible for reaching the project objectives and putting them in a global perspective. CDAC staff will oversee monitoring and supervision of the Project and provide technival advice when needed.  UNDP-GEF Regional Coordination Unit (Dakar) and the relevant UNDP country offices will  provide implementation support services; the Senegal Country Office will be the lead CO..

### 3.2 Executing Arrangements

- In view of the specific scale of the project, which requires interventions at both the national and regional level, the Project will be executed at two distinct levels.

Regional Level Project Management and Coordination

- UNDP will be responsible for substantive issues related to technical support to the project and together with UNESCO/IOC will implement regional activities. UNESCO/IOC will also provide technical inputs to the Project and will be responsible for the monitoring and evaluation component on improvements in adaptive capacity. It will also be responsible for setting up and operating the Regional Project Steering Committee (RPSC), and ensure that the five participating countries work in a coordinated manner and not as individual projects. In this respect, UNESCO/IOC will also provide oversight to the national components being executed under national execution (NEX/DEX) arrangements. UNESCO/IOC will also act as a regional platform for exchange of information, capacity building delivery and the syntheses of experiences and lessons. In order to fulfill these responsibilities, UNESCO/IOC will establish a Regional Programme Management Unit located at the UNESCO Regional Office for Africa (Senegal).  In order to facilitate the regional component of this project, UNDP Country Office in Senegal will function as the lead on behalf of all the countries involved in this project.  A Memorandum of Understanding between UNDP CO (Senegal) and UNESCO/IOC will formalized on the basis of Annex 9 upon CEO endorsement and prior to project implementation.

- The national executing agencies will submit Work Plan for their country activities for technical approval and quality control to the PMU, UNESCO/IOC and UNDP-GEF as implementing agency.

Regional Programme Management Unit (RPMU)

- Regional coordination and collaboration, and the execution of regional activities will be facilitated through a Regional Programme Management Unit. The RPMU established at the UNESCO BREDA Office, will provide technical advice to all project participants, organize activities and administrative requirements for the regional component and provide oversight to the national components. It will consist of a Regional Project Manager (RPM) and his team of financial and technical assistants. The RPMU will coordinate regional activities, including:

  - Facilitating communication between participating countries and the Project Management Teams.

  - Working with UNDP-COs and National Lead Agencies to establish the Regional Project Steering Committee.

  - Hosting an annual meeting that will bring together representatives of all participating countries, the Regional Project Steering Committee, the Project Management Teams and others as required.

  - Ensure the implementation of national activities in conformity with aggreed national workplan, and provide technical guidance as appropriate;

  - the formulation of co-financing/collaboration  arrangement with potential regional and international partners;

  - Integrate the lessons learned and best practices into the Adaptation Learning Mechanism.

The RPMU will be directly accountable to the Implementing and Executing Agencies, and to the Regional Project Steering Committee of the Project. For the job descriptions of the team members, see below.

- UNESCO/IOC, in consultation with UNDP, will competitively recruit a Regional Project Manager consistent with standard UNDP procedures.  UNDP and UNESCO/IOC will agree on an MOU governing regional execution of relevant activities in the Project.

Regional Project Steering Committee (RPSC)

- A Regional Project Steering Committee will be established and should consist of the National Coordinator from each country, Representatives from the National Lead Agency, Implementing Agency (UNDP), Implementing Partner (UNESCO/IOC), any co-funding partners contributing actual cash assistance to the Project aims and SINEPAD, as the key partner organization for GEF in the region.

- Observers, who may be invited to attend by the RPSC, may include regional stakeholder representation, environmental NGOs (regional and international), other donor agencies, etc.  Observer attendance will be agreed by consensus within the Committee membership.  It is anticipated that regional programmes such as CCLME, PRCM and Abidjan Convention would be invited to attend as observers. The Committee will be jointly chaired by a national representative (on a rotational basis) and by the Implementing Agency representative (UNDP).

- The RPSC should meet annually, and in order to reduce bureaucracy and limit the added burden to country representatives, the Committee meeting will be held as a contiguous meeting to other regional meetings.

- The main functions of the RPSC will be to:

- monitor progress in project execution;

- to provide strategic and policy guidance;

- to review and approve annual work plans and budgets (including revisions) for the project;

- identify specific capacity building needs;

- to review and endorse all formal monitoring and evaluation reports and findings;

- to provide a regional forum for reviewing and resolving national concerns;

- to provide a regional forum for stakeholder participation;

- to provide a platform from which to launch new initiatives related to the Project but requiring separate donor support;

- to ensure all interested parties are kept informed and have an opportunity to make comment.

- Within two (2) months of signature of the Project Document, a regional Inception meeting will be convened with the purpose of finalising the national workplans and allocation of resources for each project activities. Following this regional meeting, the decisions taken will be conveyed to the national inception meetings.

National Level Project Management and Coordination

117. In each participating countries a national execution mechanism will be put in place. Each country will establish a National Project Management Team (NPMT) following UNDP NEX procedures. The NPMT will consist of a National Project Director (assigned by the Lead Agency as in-kind contribution), a National Project Coordinator and his team of assistants (TOR in Annex).  UNDP COs will support national activities and charge them to the NEX upon its request.  Local, regional and international consultants will be recruited for specific tasks as needed. In Guinea Bissau, the national executing role is delegated to UNDP. Contrary to NEX, where the National Lead Agency is responsible for effective project delivery and for the management of the national component, in DEX countries, the UNDP will therefore be handling such activities. The PMU will review and endorse the Annual Work Plan of each country team and disbursement of funds will be based on the quality of outputs, following technical clearance.  National teams will work with the PMU in the execution of their country specific activities, according to the reporting measures outlined in the M&E text of the project document. The UNDP-RTA for Adaptation (Dakar), and UNDP-HQ will advice on details regarding M&E requirements as per established procedures.

.

- The NPMT will establish administrative procedures and operations systems, perform annual audit, and establish project financial management system. It will work in close consultation with the the National Lead Agency, and the UNDP Country Office and will facilitate the work of the National Steering Committee (see below).

- The Lead Agencies identified for the project are as follows:

- Ministère de l’Environnement et de la Protection de la Nature, Direction de l’Environnement et de la Protection de la Nature (Senegal)

- Ministère du Développement Rural et de l’Environnement, Direction de l’Environnement (Mauritanie)

- Ministerio dos Recursos Naturais, Direcçao Geral  do Ambiente (Guinea Bissau)

- National Environment Agency (Gambia)

- Ministry of Environment and Agriculture, Direction Générale de l’Environnement (Cape Verde)

- As the executing structure will not be fully operational from the start, UNDP-GEF, UNESCO/IOC and the UNDP Country offices, working in coordination with the National Lead Agencies, will be involved in the planning of the project Inception Workshop.  The purpose of this workshop would be to fine-tune the Project’s first year activities and expenditures. The 1st Regional Project Steering Committee meeting will also take place at this time to endorse the recommendations arrived at during the inception meeting. During this inception meeting, the schedule of financial disbursements and modalities would be finalised.  Key project staff and counterpart officials would be introduced to each other and familiarized with UNDP rules and procedures.  All persons directly involved in executing this project would be made aware of their responsibilities and of UNDP’s monitoring and evaluation requirements. A meeting of the National Steering Committee (NSC) should be organised right after the inception meeting in order to endorse the National Annual Work Plan and execution modalities in accordance with UNDP requirements.  Figure 1 gives a schematic overview of the implementation arrangements.

- At the national level, each participating country will select a National Project Director (NPD), who will be a representative of the National Lead Agency within the project and a National Project Coordinator (NPC). The NPD will supervise and advise the NPC. The NPC will be recruited by the national executing agency in consultation with the NPD, the Project PMU, UNESCO/IOC and in line with UNDP proceedures. The NPC will work in close collaboration with the National Lead Agency and will provide regular reports on progress to the PMU. The NPC will ensure appropriate linkages with other relevant Government structures. The NPC will effect the establishment of a National Steering Committee (NSC), which will be headed by the NPD.

- Where there is already an appropriate national body (for example National Committee on Climate Change) that functions at the inter-sectoral level, this should be mandated to take on the role of the NSC (in order to avoid creating unnecessary parallel mechanisms).  The function of the NSC will be to work towards the project objective at the national level, to expedite national activities related to the project outcomes and outputs and to ensure complementary activities between national strategies and policies and regional project objectives.  Representatives from other relevant Enabling Activities, such as the NCSA and NAPA process, should also be consulted. It is the responsibility of the NSC and the PMU to ensure that duplication with priority activities as highlighted in the NAPA (and the focus of follow up projects) are not duplicated through this SPA initiative.  Where relevant, synergies with the follow up NAPA projects should be maximized to the extent possible.

## Figure 1: Schematic overview of the implementation arrangements.

- Both NPD and NPC will sit on the NSC and will participate in the RPSC.  This will firmly establish the National Project Coordinator as the key focal point for interactions with the Project Coordination Unit. The National Coordinator will work in close collaboration with the Regional Coordination Unit, and will provide periodical progress reports.

- The national (NEX/DEX) mechanism will be responsible for:

Overall Project Design and Implementation:

1. Develop a national project implementation plan reflective of the goals and objectives of the project

that will include:

- detailed project design, including timelines, deliverables, influencing strategy and budget;

- project management structure that will describe the roles, responsibilities and reporting relationships of all parties engaged in the project, including the Project Management Team, the Project Steering Committee, the Technical Advisory Committee and the National Steering Committees; and

- clarify, if needed, the project’s Logical Framework Analysis.

2. Revise and refine the detailed national project implementation plan, including, but not limited to, timelines, delegation of responsibilities and budget, as required and approved by UNDP.

3. Ensure regular communication with and between members of the National Steering Committees of the participating countries.

4. Collect lessons learned as the project progresses.

5. Communicate project outcomes and results to the wider policy and climate change community throughout the project cycle through, but not limited to:

  - Presentations at selected national and international conferences and workshops; and

- Publication of articles and case studies.

6. Confirm or establish National Steering Committees in the participating countries.

7. Work with the National Steering Committees to develop and finalize detailed country level implementation plans and monitoring processes, giving particular attention to the need for a policy up-scaling component. Implementation plans should include:

- detailed project design, including timelines, deliverables, influencing strategy and budget;

- project management structure that will describe the roles, responsibilities and reporting relationships of all parties engaged in the project; and

- a Logical Framework Analysis

8. Supervise, assist with and monitor implementation of the individual pilot projects to be undertaken in the participating countries.

9. Develop guidance and lessons on policy integration from field experience and assuring that pilot-project have well defined activities for up-scaling from field level to policy reform.

10. Maintain continual dialogue with National Steering Committees and national project-level implementation teams.

Technical Expertise

11. Identify, engage and manage technical experts and consultants required to support implementation of the overarching project as well as its individual pilot projects, and coordinate their participation in the National Steering Committee.

Capacity Building

To support capacity building within the regional organization and project implementation team, the NEX/DEX will:

12. Undertake a needs assessment at national level to identify areas for capacity enhancement within the Project Management Team.

13. Develop formal and informal strategies for building the Project Managers’ capacity to deliver field level and multi-country projects.

Monitoring and Reporting

15. Establish a baseline set of indicators, based on the GEF’s requirements for its Strategic Priority for Adaptation, and a monitoring framework for these indicators, against which reporting will be undertaken.

16. Produce the following narrative and financial reports in conformity with UNDP and GEF reporting requirements as appropriate (see PART IV: Monitoring and Evaluation Plan and Budget).

17. The project’s Executing Agencies will report to GEF/UNDP on a regular basis and hold monthly project management meetings

National Steering Committee (NSC)

- Attendance: The NSC should consist of senior (policy level) representatives from relevant government agencies/sectors (e.g. Fisheries, Environment, Industry, Finance, Tourism, etc.), NGO representatives as appropriate (environmental and industry), relevant funding agencies and community representation. The NAPA and SNC coordinator will be included in the National Steering Committee and will be consulted to ensure coordination with NAPA/SNC follow up activities of relevance to this project. Duplication with NAPA/SNC must be avoided.

- Frequency: The NSC should meet on a quarterly basis and prior to the Regional Project Steering Committee (so national concerns can be carried forward to regional level in a timely manner).

- Function: To endorse requests for in-country Project activities, monitor the effectiveness of in-country activities; validate work plans for in-country Project activities (prepared by the NSC); discuss project progress and implications at  national level.  To identify national concerns regarding project activities and delivery; ensure integrated coordination of the Project actions with those Government Departments concerned with adaptation issues; provide government representatives with an opportunity to update and inform each other and non-government participants; ensure transparency of process and multi-sectoral participation.

- Reporting:  The NPC will provide the respective UNDP Country Office and the Regional Project Management Unit with a summary report of its discussions as they relate to project issues and should highlight specific issues that need to be brought to the attention of the Regional Project Steering Committee.

- In order to accord proper acknowledgement to GEF for providing funding, a GEF logo should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent -- and separated from the GEF logo if possible, as UN visibility is important for security purposes.

## PART IV: Monitoring and Evaluation Plan and Budget

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures and will be provided to the project team and the UNDP Country Office (UNDP-CO) with support from UNDP-GEF.  Monitoring and Evaluation Plan provides for a series of linked activities, including annual Project Implementation Reviews (PIR), Tripartite Reviews, Quarterly Project Reports, Work Plans, and independent mid-term and final project Evaluations. A feature of the monitoring strategy is that it provides for Programme level monitoring, to ensure that project synergies are being realized, and activities dovetailed as planned. Such monitoring will be orchestrated with funds earmarked in the budget. Results will be evaluated by the Regional Project Steering Committee, which will recommend response measures. The mid-term independent evaluations will provide an important milestone for correcting project strategies. The Logical Framework Matrix provides performance and impact indicators for project implementation along with their corresponding means of verification. These will form the basis on which the project's Monitoring and Evaluation system will be built.

- The following sections outline the principle components of the Monitoring and Evaluation Plan and indicative cost estimates related to M&E activities. The project's Monitoring and Evaluation Plan will be presented and finalized at the Project's Inception Report following a collective fine-tuning of indicators, means of verification, and the full definition of project staff M&E responsibilities.

- More detailed information about the specific monitoring indicators can be found in the Executive Summary, “Monitoring and Evaluation” (p. 40 – 46) and Annex A4 and A5.

### 5.1 Monitoring and Reporting

Programme Inception Phase

- A Programme Inception Workshop will be conducted with nationals from each participating country, relevant government counterparts, co-financing partners, the UNDP-COs and the ACCC Project Team (PT) (i.e. Regional Project Steering Committee including National Focal Points).

- A fundamental objective of this Inception Workshop will be to assist the entire project  team to understand and take ownership of the project’s goals and objectives, as well as finalize preparation of the project's first annual work plan on the basis of the log frame matrix. This will include reviewing the log frame (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise finalize the Annual Work Plan (AWP) with precise and measurable performance indicators, and in a manner consistent with the expected outcomes for the project.

- Additionally, the purpose and objective of the Inception Workshop will be to provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the Annual Project Implementation Reviews (PIRs) and related documentation, the Annual Project Report (APR), Tripartite Review Meetings, as well as mid-term and final evaluations. Equally, the BD team will provide an opportunity to inform the programme team on UNDP programme/project related budgetary planning, budget reviews, and mandatory budget rephasings.

- The Inception Workshop will also provide an opportunity for all parties to understand their roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms. The Terms of Reference for project staff and decision-making structures will be discussed again, as needed, in order to clarify for all, each party’s responsibilities during the project's implementation phase.

Monitoring responsibilities and events

- A detailed schedule of programme review meetings will be developed by the programme management, in consultation with programme implementation partners and stakeholder representatives and incorporated in the Programme Inception Report. Such a schedule will include: (i) tentative time frames for Tripartite Reviews, Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) programme related Monitoring and Evaluation activities.

- Day to day monitoring of implementation progress will be the responsibility of the National Coordinators based on the project's Annual Work Plan and its indicators. The National Coordinators will inform the UNDP-CO and PT of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The National Coordinators and PT will fine-tune the progress and performance/impact indicators of the project in consultation with the full project team at the Inception Workshop. Specific targets for the first year implementation progress indicators together with their means of verification will be developed at this Workshop. These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan. The local implementing partners will also take part in the Inception Workshop in which a common vision of overall programme goals will be established. Targets and indicators for subsequent years will be defined annually as part of the internal evaluation and planning processes undertaken by the PT.

- Measurement of impact indicators related to global benefits will occur according to the schedules defined in the Inception Workshop and tentatively outlined in the indicative Impact Measurement Template. The measurement, of these will be undertaken through subcontracts or retainers with relevant institutions to be determined during the inception workshop  or through specific studies that are to form part of the programmes activities or periodic sampling.

- Periodic monitoring of implementation progress within each country will be undertaken by the UNDP-CO through quarterly meetings with the National Coordinators, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- UNDP Country Offices and the PT, as appropriate, will conduct yearly visits to field sites, or more often based on an agreed upon scheduled to be detailed in the project's Inception Report / Annual Work Plan to assess first hand project progress. Any other member of the Steering Committee can also accompany, as decided by the SC. A Field Visit Report will be prepared by the CO and circulated no less than one month after the visit to the project team, all SC members, and PT.

- Annual Monitoring will occur through the Tripartite Review (TPR). This is the highest policy-level meeting of the parties directly involved in the implementation of the project. The project will be subject to Tripartite Review (TPR) at least once every year. The first such meeting will be held within the first twelve months of the start of full implementation. The National Coordinators will prepare reports that will be compiled into Annual Project Report (APR) by the PT at least two weeks prior to the TPR for review and comments.

- The APR will be used as one of the basic documents for discussions in the TPR meeting. The PT will present the APR to the TPR, highlighting policy issues and recommendations for the decision of the TPR participants.  The PT also informs the participants of any agreement reached by stakeholders during the APR preparation on how to resolve operational issues. Separate reviews of each project component may also be conducted if necessary.

Terminal Tripartite Review (TTR)

- The terminal tripartite review is held in the last month of project operations. The PT is responsible for preparing the Terminal Report and submitting it to UNDP and the GEF Secretariat. It shall be prepared in draft at least two months in advance of the TTR in order to allow review, and will serve as the basis for discussions in the TTR. The terminal tripartite review considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective. It decides whether any actions are still necessary, particularly in relation to sustainability of project results, and acts as a vehicle through which lessons learnt can be captured to feed into other projects under implementation of formulation.

- The TPR has the authority to suspend disbursement if project performance benchmarks are not met. Benchmarks will be developed at the Inception Workshop, based on delivery rates, and qualitative assessments of achievements of outputs.

Programme Monitoring Reporting

- The National Coordinators in conjunction with the PT will be responsible for the preparation and submission of the following reports that form part of the monitoring process.

(a)	Inception Report (IR)

- A Programme Inception Report will be prepared immediately following the Inception Workshop. It will include a detailed First Year/ Annual Work Plan divided in quarterly time-frames detailing the activities and progress indicators that will guide implementation during the first year of the project. This Work Plan would include the dates of specific field visits, support missions from the UNDP-CO or the PT or consultants, as well as time-frames for meetings of the project 's decision making structures.  The Report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months time-frame.

- The Inception Report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of programme related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may effect project implementation.

- When finalized the report will be circulated to project counterparts who will be given a period of one calendar month in which to respond with comments or queries.

- Annual Project Report (APR)

- The APR is a UNDP requirement. It is a self -assessment report by project management to UNDP and provides input to the Tripartite Project Review.  An APR will be prepared on an annual basis prior to the Tripartite Project Review, to reflect progress achieved in meeting the project s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.

- The format of the APR is flexible but should include the following:

- An analysis of project performance over the reporting period, including outputs produced and, where possible, information on the status of the outcome

- The constraints experienced in the progress towards results and the reasons for these

- The three (at most) major constraints to achievement of results

- AWP, CAE and other expenditure reports (ERP generated)

- Lessons learned

- Clear recommendations for future orientation in addressing key problems in lack of progress

- Project Implementation Review (PIR)

- The PIR is an annual monitoring process mandated by the GEF. It has become an essential management and monitoring tool for programme managers and offers the main vehicle for extracting lessons from ongoing projects. Once the programme has been under implementation for a year, a Project Implementation Report must be completed by the PT, in cooperation with National Coordinators. The PIR can be prepared any time during the year (July-June) and ideally prior to the TPR.  The PIR should then be discussed in the TPR so that the result would be a PIR that has been agreed upon by all partners.

- Quarterly Progress Reports

- Short reports outlining main updates in programme progress will be provided quarterly to the local UNDP Country Office and the PT by National Coordinators.

- Periodic Thematic Reports

- As and when called for by UNDP or the GEF Secretariat, the PT will prepare Specific Thematic Reports, focusing on specific issues or areas of activity.  The request for a Thematic Report will be provided to the PT in written form by UNDP and will clearly state the issue or activities that need to be reported on.  These reports can be used as a form of lessons learnt exercise, specific oversight in key areas, or as troubleshooting exercises to evaluate and overcome obstacles and difficulties encountered.  UNDP is requested to minimize its requests for Thematic Reports, and when such are necessary will allow reasonable timeframes for their preparation by the project team.

- Project Terminal Report

- During the last three months of the project the PT will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the Programme, lessons learnt, objectives met, or not achieved, structures and systems implemented, etc. and will be the definitive statement of the project’s activities during its lifetime.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s activities.

### 5.2 Independent Evaluation

- In addition to the ongoing internal monitoring and evaluation process described above, a full package of independent monitoring of the Project will be undertaken through contract using a balanced group of independent experts. The project will be subjected to at least two independent external evaluations as follows:-

- Mid-term Evaluation

- An independent Mid-Term Evaluation will be undertaken at the end of the second year of implementation. The Mid-Term Evaluation will determine progress being made towards the achievement of outcomes and will identify course correction if needed. It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management. Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document. The Terms of Reference for this Mid-term evaluation will be prepared by the PT based on guidance from UNDP’s Office of Evaluation.

- Final Evaluation

- An independent Final Evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on the same issues as the mid-term evaluation.  The final evaluation will also look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals.  The Final Evaluation should also provide recommendations for follow-up activities. The Terms of Reference for this evaluation will be prepared by the PT based on guidance from UNDP’s Office of Evaluation.

- The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects. Identifying and analyzing lessons learned is an on- going process, and the need to communicate such lessons as one of the project's central contributions is a requirement to be delivered not less frequently than once every 12 months. UNDP shall provide a format and assist the project team in categorizing, documenting and reporting on lessons learned. To this end a percentage of project resources will need to be allocated for these activities (see Table 3 for indicative M&E workplan and corresponding budget).

Table 3: Indicative Monitoring and Evaluation Work plan and corresponding Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding programme team Staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop | Project Coordinator UNDP CO UNDP GEF | $80,000 | Within first two months of programme start up |
| Inception Report | Programme Team UNDP CO | None | Immediately following Inception Workshop |
| Measurement of Means of Verification for Programme Purpose Indicators | National Coordinators will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members | To be finalized in Inception Phase and Workshop. Indicative cost $30,000 | Start, mid and end of programme |
| Measurement of Means of Verification for Programme Progress and Performance (measured on an annual basis) | Oversight by PT Measurements by field officers and local IAs | To be determined as part of the Annual Work Plan's preparation. Indicative cost $25,000 | Annually prior to APR/PIR and to the definition of annual work plans |
| APR and PIR | PT UNDP-GEF | None | Annually |
| TPR and TPR report | Government Counterparts PT UNESCO/IOC | None | Every year, upon receipt of APR |
| Steering Committee Meetings | PT National Coordinators | None | Following Programme Inception Workshop and subsequently at least once a year |
| Periodic status reports | PT National Coordinators | 10,000 | To be determined by Programme team and UNDP CO |
| Technical reports | PT Hired consultants as needed | 10,000 | To be determined by Programme Team and UNDP-CO |
| Mid-term External Evaluation | PT National Coordinators External Consultants (i.e. evaluation team) | 25,000 | At the mid-point of programme implementation. |
| Final External Evaluation | PT National Coordinators External Consultants (i.e. evaluation team) | 25,000 | At the end of programme implementation |
| Terminal Report | PT National Coordinators External Consultant | None | At least one month before the end of the programme |
| Lessons learned | PT National Coordinators | 15,000 | Yearly |
| Visits to field sites (UNDP staff travel costs to be charged to IA fees) | UNDP Country Office PT Government representatives | 15,000 (average one visit per year) | Yearly |
| TOTAL indicative COST Excluding programme team staff time and UNDP staff and travel expenses | US$ 235,000 |  |

## PART V: Legal Context

- This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement between the Governments of Gambia, Guinea Bissau, Senegal, Mauritania, Cape Verde, Gambia, and the United Nations Development Programme, to be signed by the parties. The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

- The Resident Representative in each of the project countries is authorized to effect in writing the following types of revision to this Project Document, provided that he/she has verified the agreement thereto by the UNDP-GEF Unit at HQ and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document

##### SECTION II : STRATEGIC RESULTS FRAMEWORK AND GEF  INCREMENT

## PART I: Incremental Cost Analysis

- Refer to Annex A of the Executive Summary.

PART II: Logical Framework Analysis

Refer to Annex B of the Executive Summary.

##### SECTION III: Total Budget and Work plan

- The following budget will be finalized following the inception meeting of this project, as per standard practices.

Project Total budget

| TOTAL PROJECT WORKPLAN AND BUDGET |  |
| --- | --- |
| (to be read in conjunction with the Advisory Note on Atlas and Total Workplan Terminology) |  |
| Award ID: 00045638 |  |  |  |  |  |  |  |  |  |  |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |  |
| Project ID: 00053951 |  |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |  |
| Executing Agency: UNESCO/IOC |  |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years | Budget Notes |
| OUTCOME 1: Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts | NEX | GEF | 71200 | Intl Cnslt | 40,000 | 40,000 | 40,000 | 40,000 | 160,000 | 1 |
|  |  |  | 71300 | Lcl Cnslts | 30,000 | 30,000 | 30,000 | 30,000 | 120,000 | 2 |
|  |  |  | 71600 | Travel | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 3 |
|  |  |  | 72100 | Contr-Cmpy | 800,000 | 370,000 | 375,000 | 206,000 | 1,751,000 | 4 |
|  |  |  | 74200 | Printing & Publications, Translation | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 5 |
|  |  | sub-total | GEF |  | 885,000 | 455,000 | 460,000 | 291,000 | 2,091,000 |  |
| OUTCOME 2: Climate change and adaptation issues integrated into coastal area management policies and programmes. | NEX | GEF | 71200 | Intl Cnslt | 23,500 | 23,500 | 23,500 | 23,500 | 94,000 | 6 |
|  |  |  | 72100 | Contr-Cmpy | 23,900 | 34,600 | 63,000 | 27,500 | 149,000 | 7 |
|  |  |  | 71300 | Lcl Cnslts | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 |  |
|  |  | UNDP | 71300 | Lcl Cnslts | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 | 8 |
|  |  | sub-total | UNDP |  | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |  |
|  |  | sub-total | GEF |  | 55,400 | 66,100 | 94,500 | 59,000 | 275,000 |  |
| OUTCOME 3: Enhanced monitoring of coastal erosion and capacity building in coastal management and planning. | UNESCO | GEF | 71200 | Intl Cnslt | 35,000 | 35,000 | 35,000 | 35,000 | 140,000 | 9 |
|  |  |  | 71300 | Lcl Cnslts | 51,000 | 27,000 | 27,000 | 26,000 | 131,000 | 10 |
|  |  |  | 72100 | Contr-Cmpy | 70,000 | 70,000 | 70,000 | 69,500 | 279,500 | 11 |
|  |  | sub-total | GEF |  | 156,000 | 132,000 | 132,000 | 130,500 | 550,500 |  |
| OUTCOME 4: Monitoring, Learning, Adaptive Feedback and Evaluation | UNESCO | GEF | 71200 | Impact monitoring (Intl Cnslt) | 20,400 | 34,600 | 14,300 | 46,900 | 116,200 | 12 |
|  |  |  | 71300 | Impact monitoring (Lcl Cnslt) | 4,690 | 14,070 | 4,690 | 23,450 | 46,900 | 13 |
|  |  |  |  | Website Development and Maintenance | 4,080 | 2,040 | 2,040 | 2,040 | 10,200 | 15 |
|  |  |  | 71600 | Travel | 24,500 | 12,200 | 12,200 | 13,300 | 62,200 | 16 |
|  |  | sub-total | GEF |  | 53,670 | 62,910 | 33,230 | 85,690 | 235,500 |  |
| OUTCOME 5: Project Mangement Unit* | UNESCO | GEF | 71100 | Intl Cnslt | 30,000 | 30,000 | 30,000 | 30,000 | 120,000 | 17 |
|  |  |  | 71600 | Travel | 7,000 | 7,000 | 7,000 | 7,000 | 28,000 | 18 |
|  |  | sub-total | GEF |  | 37,000 | 37,000 | 37,000 | 37,000 | 148,000 |  |
| subtotals | GEF |  |  | 1,187,070 | 753,010 | 756,730 | 603,190 | 3,300,000 |  |
|  | UNDP |  |  | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |  |
|  | TOTAL |  |  | 1,212,070 | 778,010 | 781,730 | 628,190 | 3,400,000 |  |
| * The GEF contribution for the overall management and coordination structure (outcome 5) does not exceed the normal 10-20% of the total GEF contribution (it is estimated at about 15%). |  | Summary of Funds: |  |
|  |  | GEF | 1,187,070 | 753,010 | 756,730 | 603,190 | 3,300,000 |  |
|  |  | Unesco (Cash) | 15,000 | 15,000 | 15,000 | 15,000 | 60,000 |  |
|  |  | Unesco (In Kind) | 113,293 | 78,172 | 30,211 | 28,323 | 250,000 |  |
|  |  | UNDP Cos (Cash) |  | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |  |
|  |  | Govt (cash) | 16,170 | 17,248 | 17,248 | 16,003 | 66,668 |  |
|  |  | Govt (parallel/ in kind) | 1,483,830 | 1,582,752 | 1,582,752 | 1,468,514 | 6,117,849 |  |
|  |  | NGO/UICN (parallel/ in kind) |  |  | 740,937 | 511,246 | 197,583 | 185,234 | 1,635,000 |  |
|  |  | Bilateral/JICA (parrallel/inkind) |  |  | 375,000 | 375,000 | 375,000 | 375,000 | 1,500,000 |  |
|  |  | Total Cash | 1,243,240 | 810,258 | 813,978 | 659,193 | 3,526,668 |  |
|  |  | Total parallel/ in kind |  |  | 2,713,060 | 2,547,171 | 2,185,547 | 2,057,072 | 9,502,849 |  |
|  |  | PDF B money |  |  |  |  | 700,000 |  |
|  |  | Grand total | 3,956,300 | 3,357,428 | 2,999,525 | 2,716,264 | 13,729,517 |  |

A detailed workplan will be outlined during the inception meeting.

Regional Component Budget/UNESCO

| TOTAL PROJECT WORKPLAN AND BUDGET |
| --- |
| (to be read in conjunction with the Advisory Note on Atlas and Total Workplan Terminology) |
| Award ID: tbd |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |
| Project ID: tbd |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |
| Executing Agency: UNESCO/IOC |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years |
| OUTCOME 3: Enhanced monitoring of coastal erosion and capacity building in coastal management and planning. | UNESCO | GEF | 71200 | Intl Cnslt | 35,000 | 35,000 | 35,000 | 35,000 | 140,000 |
|  |  |  | 71300 | Lcl Cnslts | 51,000 | 27,000 | 27,000 | 26,000 | 131,000 |
|  |  |  | 72100 | Contr-Cmpy | 70,000 | 70,000 | 70,000 | 69,500 | 279,500 |
|  |  | sub-total | GEF |  | 156,000 | 132,000 | 132,000 | 130,500 | 550,500 |
| OUTCOME 4: Monitoring, Learning, Adaptive Feedback and Evaluation | UNESCO | GEF | 71200 | Impact monitoring (Intl Cnslt) | 20,400 | 34,600 | 14,300 | 46,900 | 116,200 |
|  |  |  | 71300 | Impact monitoring (Lcl Cnslt) | 4,690 | 14,070 | 4,690 | 23,450 | 46,900 |
|  |  |  |  | Website Development and Maintenance | 4,080 | 2,040 | 2,040 | 2,040 | 10,200 |
|  |  |  | 71600 | Travel | 24,500 | 12,200 | 12,200 | 13,300 | 62,200 |
|  |  | sub-total | GEF |  | 53,670 | 62,910 | 33,230 | 85,690 | 235,500 |
| OUTCOME 5: Project Mangement Unit* | UNESCO | GEF | 71100 | Intl Cnslt | 30,000 | 30,000 | 30,000 | 30,000 | 120,000 |
|  |  |  | 71600 | Travel | 7,000 | 7,000 | 7,000 | 7,000 | 28,000 |
|  |  | sub-total | GEF |  | 37,000 | 37,000 | 37,000 | 37,000 | 148,000 |
| subtotals | GEF |  |  | 246,670 | 231,910 | 202,230 | 253,190 | 934,000 |
|  | TOTAL |  |  | 246,670 | 231,910 | 202,230 | 253,190 | 934,000 |
|  |  | Summary of Funds: |
|  |  | GEF | 246,670 | 231,910 | 202,230 | 253,190 | 934,000 |
|  |  | Unesco (Cash) | 15,000 | 15,000 | 15,000 | 15,000 | 60,000 |
|  |  | Unesco (In Kind) | 113,293 | 78,172 | 30,211 | 28,323 | 250,000 |
|  |  | Total Cash | 261,670 | 246,910 | 217,230 | 268,190 | 994,000 |
|  |  | Total parallel/ in kind |  |  | 113,293 | 78,172 | 30,211 | 28,323 | 250,000 |
|  |  | PDF B money |  |  |  |  | 700,000 |
|  |  | Grand total | 374,963 | 325,082 | 247,441 | 296,513 | 1,944,000 |

National Component Budget/Senegal

| TOTAL PROJECT WORKPLAN AND BUDGET |
| --- |
| (to be read in conjunction with the Advisory Note on Atlas and Total Workplan Terminology) |
| Award ID: tbd |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |
| Project ID: tbd |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |
| Executing Agency: Ministry of Environment and Nature Protection |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years |
| OUTCOME 1: Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts | NENP | GEF | 71200 | Intl Cnslt | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 |
|  |  |  | 71300 | Lcl Cnslts | 6,000 | 6,000 | 6,000 | 6,000 | 24,000 |
|  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 |
|  |  |  | 72100 | Contr-Cmpy | 160,000 | 74,000 | 75,000 | 41,200 | 350,200 |
|  |  |  | 74200 | Printing & Publications, Translation | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 177,000 | 91,000 | 92,000 | 58,200 | 418,200 |
| OUTCOME 2: Climate change and adaptation issues integrated into coastal area management policies and programmes. | MENP | GEF | 71200 | Intl Cnslt | 4,700 | 4,700 | 4,700 | 4,700 | 18,800 |
|  |  |  | 72100 | Contr-Cmpy | 4,780 | 6,920 | 12,600 | 5,500 | 29,800 |
|  |  |  | 71300 | Lcl Cnslts | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 9,480 | 11,620 | 17,300 | 10,200 | 48,600 |
| subtotals | GEF |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  | TOTAL |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Summary of Funds: |
|  |  | GEF | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Govt (parallel/ in kind) | 754,545 | 754,545 | 754,545 | 754,545 | 3,018,181 |
|  |  | NGO/UICN (parallel/ in kind) |  |  | 204,438 | 204,438 | 204,438 | 204,438 | 817,750 |
|  |  | Bilateral/JICA (parrallel/inkind) |  |  | 375,000 | 375,000 | 375,000 | 375,000 | 1,500,000 |
|  |  | Total Cash | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Total parallel/ in kind |  |  | 1,333,983 | 1,333,983 | 1,333,983 | 1,333,983 | 5,335,931 |
|  |  | Grand total | 1,520,463 | 1,436,603 | 1,443,283 | 1,402,383 | 5,802,731 |

National component budget/Cape Verde

| TOTAL PROJECT WORKPLAN AND BUDGET |
| --- |
| (to be read in conjunction with the Advisory Note on Atlas and Total Workplan Terminology) |
| Award ID: tbd |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |
| Project ID: tbd |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |
| Executing Agency: Ministry of Environment and Agriculture |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years |
| OUTCOME 1: Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts | MEA | GEF | 71200 | Intl Cnslt | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 |
|  |  |  | 71300 | Lcl Cnslts | 6,000 | 6,000 | 6,000 | 6,000 | 24,000 |
|  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 |
|  |  |  | 72100 | Contr-Cmpy | 160,000 | 74,000 | 75,000 | 41,200 | 350,200 |
|  |  |  | 74200 | Printing & Publications, Translation | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 177,000 | 91,000 | 92,000 | 58,200 | 418,200 |
| OUTCOME 2: Climate change and adaptation issues integrated into coastal area management policies and programmes. | MEA | GEF | 71200 | Intl Cnslt | 4,700 | 4,700 | 4,700 | 4,700 | 18,800 |
|  |  |  | 72100 | Contr-Cmpy | 4,780 | 6,920 | 12,600 | 5,500 | 29,800 |
|  |  | UNDP | 71300 | Lcl Cnslts | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |
|  |  | sub-total | UNDP |  | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |
|  |  | sub-total | GEF |  | 9,480 | 11,620 | 17,300 | 10,200 | 48,600 |
| subtotals | GEF |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  | UNDP |  |  | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |
|  | TOTAL |  |  | 211,480 | 127,620 | 134,300 | 93,400 | 566,800 |
|  |  | Summary of Funds: |
|  |  | GEF | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | UNDP Cos (Cash) |  | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |
|  |  | Govt (cash) | 16,170 | 17,248 | 17,248 | 16,003 | 66,668 |
|  |  | Govt (parallel/ in kind) | 159,917 | 159,917 | 159,917 | 159,917 | 639,668 |
|  |  | Total Cash | 227,650 | 144,868 | 151,548 | 109,403 | 633,468 |
|  |  | Total parallel/ in kind |  |  | 159,917 | 159,917 | 159,917 | 159,917 | 639,668 |
|  |  | Grand total | 387,567 | 304,785 | 311,465 | 269,320 | 1,273,136 |

National component budget/Gambia

| Award ID: tbd |
| --- |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |
| Project ID: tbd |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |
| Executing Agency: National Environment Agency |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years |
| OUTCOME 1: Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts | NEA | GEF | 71200 | Intl Cnslt | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 |
|  |  |  | 71300 | Lcl Cnslts | 6,000 | 6,000 | 6,000 | 6,000 | 24,000 |
|  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 |
|  |  |  | 72100 | Contr-Cmpy | 160,000 | 74,000 | 75,000 | 41,200 | 350,200 |
|  |  |  | 74200 | Printing & Publications, Translation | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 177,000 | 91,000 | 92,000 | 58,200 | 418,200 |
| OUTCOME 2: Climate change and adaptation issues integrated into coastal area management policies and programmes. | NEA | GEF | 71200 | Intl Cnslt | 4,700 | 4,700 | 4,700 | 4,700 | 18,800 |
|  |  |  | 72100 | Contr-Cmpy | 6,380 | 8,520 | 14,200 | 7,100 | 36,200 |
|  |  | UNDP | 71300 | Lcl Cnslts | 25,000 | 25,000 | 25,000 | 25,000 | 100,000 |
|  |  | sub-total | GEF |  | 11,080 | 13,220 | 18,900 | 11,800 | 55,000 |
| subtotals | GEF |  |  | 188,080 | 104,220 | 110,900 | 70,000 | 473,200 |
|  | TOTAL |  |  | 188,080 | 104,220 | 110,900 | 70,000 | 473,200 |
|  |  | Summary of Funds: |
|  |  | GEF | 188,080 | 104,220 | 110,900 | 70,000 | 473,200 |
|  |  | Govt (parallel/ in kind) | 200,000 | 200,000 | 200,000 | 200,000 | 800,000 |
|  |  | Total Cash | 188,080 | 104,220 | 110,900 | 70,000 | 473,200 |
|  |  | Total parallel/ in kind | 200,000 | 200,000 | 200,000 | 200,000 | 800,000 |
|  |  | Grand total | 388,080 | 304,220 | 310,900 | 270,000 | 1,273,200 |

National compoment budget/Guinea Bissau

| TOTAL PROJECT WORKPLAN AND BUDGET |
| --- |
| (to be read in conjunction with the Advisory Note on Atlas and Total Workplan Terminology) |
| Award ID: tbd |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |
| Project ID: tbd |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |
| Executing Agency: UNDP/DEX |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years |
| OUTCOME 1: Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts | UNDP/DEX | GEF | 71200 | Intl Cnslt | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 |
|  |  |  | 71300 | Lcl Cnslts | 6,000 | 6,000 | 6,000 | 6,000 | 24,000 |
|  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 |
|  |  |  | 72100 | Contr-Cmpy | 160,000 | 74,000 | 75,000 | 41,200 | 350,200 |
|  |  |  | 74200 | Printing & Publications, Translation | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 177,000 | 91,000 | 92,000 | 58,200 | 418,200 |
| OUTCOME 2: Climate change and adaptation issues integrated into coastal area management policies and programmes. | UNDP/DEX | GEF | 71200 | Intl Cnslt | 4,700 | 4,700 | 4,700 | 4,700 | 18,800 |
|  |  |  | 72100 | Contr-Cmpy | 4,780 | 6,920 | 12,600 | 5,500 | 29,800 |
|  |  |  | 71300 | Lcl Cnslts | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 9,480 | 11,620 | 17,300 | 10,200 | 48,600 |
| subtotals | GEF |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  | TOTAL |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Summary of Funds: |
|  |  | GEF | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Total Cash | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Grand total | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |

National compoment budget/Mauritania

| TOTAL PROJECT WORKPLAN AND BUDGET |
| --- |
| (to be read in conjunction with the Advisory Note on Atlas and Total Workplan Terminology) |
| Award ID: tbd |
| Award Title: PIMS 3341 CC-A FSP: West Africa Shoreline Project |
| Project ID: tbd |
| Project Title: PIMS 3341 CC-A FSP: Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management. |
| Executing Agency: Departement of Environment |
| GEF Outcome/Atlas Activity** | Responsible Party | Source of Funds | Atlas Budgetary Account Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Amount (USD) Year 3 | Amount (USD) Year 4 | Total (USD) All Years |
| OUTCOME 1: Implemented pilot activities to increase the adaptive capacity and resilience of coastline ecosystems in regions vulnerable to climate change impacts | DE | GEF | 71200 | Intl Cnslt | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 |
|  |  |  | 71300 | Lcl Cnslts | 6,000 | 6,000 | 6,000 | 6,000 | 24,000 |
|  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 |
|  |  |  | 72100 | Contr-Cmpy | 160,000 | 74,000 | 75,000 | 41,200 | 350,200 |
|  |  |  | 74200 | Printing & Publications, Translation | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 177,000 | 91,000 | 92,000 | 58,200 | 418,200 |
| OUTCOME 2: Climate change and adaptation issues integrated into coastal area management policies and programmes. | DE | GEF | 71200 | Intl Cnslt | 4,700 | 4,700 | 4,700 | 4,700 | 18,800 |
|  |  |  | 72100 | Contr-Cmpy | 4,780 | 6,920 | 12,600 | 5,500 | 29,800 |
|  |  |  | 71300 | Lcl Cnslts | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 |
|  |  | sub-total | GEF |  | 9,480 | 11,620 | 17,300 | 10,200 | 48,600 |
| subtotals | GEF |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  | TOTAL |  |  | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Summary of Funds: |
|  |  | GEF | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Govt (parallel/ in kind) | 415,000 | 415,000 | 415,000 | 415,000 | 1,660,000 |
|  |  | NGO/UICN (parallel/ in kind) |  |  | 204,438 | 204,438 | 204,438 | 204,438 | 817,750 |
|  |  | Total Cash | 186,480 | 102,620 | 109,300 | 68,400 | 466,800 |
|  |  | Total parallel/ in kind |  |  | 619,438 | 619,438 | 619,438 | 619,438 | 2,477,750 |
|  |  | Grand total | 805,918 | 722,058 | 728,738 | 687,838 | 2,944,550 |

##### Budget Notes

1. Estimated at a cost of US$400/day for an International Consultant to provide approximately 20 days of support to each country (5) over 4 years in support of Outcome 1. Terms of Reference for the International Consultant is in Annex A8.

2. Estimated at a cost of US$2000 per month for 3 months worth of support each year in each country during the project duration to provide technical input and guidance in lieu of Outcome 1. Terms of Reference for the National Consultants is in Annex A8.

3. This will cover the cost of approximately 3 missions by an international consultant to provide technical support for Outcome 1.  Estimated at the rate of US$1300 per 3-day mission per country (including the cost of Ticket, DSA, TF).  Figures based on average estimates from the preparatory phase.  See Terms of Reference in Annex A8.

4. This budgeted amount will support the implementation of pilot demonstration activities as outlined in the Council approved FSP.

5. Publication of materials produced by the national and international consultants on outcomes of outcome 1 for dissemination at the national and international for a. Estimated at $8000 per country.

6. Estimated at a cost of US$400/day for an International Consultant to provide approximately 11.5 days of support to each country (5) over 4 years in order to realize Outcome 2. Terms of Reference for the International Consultant is in Annex A8.

7. Estimated cost of meeting outcome 2. Details are specified in the Council approved FSP.

8. Estimated at a cost of US$2000 per month for 2 months worth of support each year during the project duration to provide technical input and guidance in lieu of Outcome 2. Terms of Reference for the National Consultants is in Annex A8.

9. Estimated at a cost of US$400/day for an International Consultant to provide approximately 17.5 days of support to each country (5) over 4 years in order to realize Outcome 3. Terms of Reference for the International Consultant is in Annex A8.

10. Estimated at a cost of US$2000 per month for 3 months worth of support each year in each country during the project duration to provide technical input and guidance in lieu of Outcome 3. Terms of Reference for the National Consultants is in Annex A8.

11. Estimated cost of meeting outcome 3. Details of outcome 3 are specified in the Council approved  FSP.

12. Estimated at a cost of US$400/day for an International Consultant to provide approximately 14.5 days of support to each country (5) over 4 years in order to establish and lead the M&E component for the project. Terms of Reference for the International Consultant is in Annex A8.

13. Estimated at a cost of US$2000 per month for 3 months worth of support each year during the project duration to provide technical input and guidance in lieu of M&E requirements. Terms of Reference for the National Consultants is in Annex A8.

14. This will cover the cost of travel (est. $1300 per mission including DSA, travel etc) for approximately one mission per year to each of the project countries over the project duration for an international consultant to provide support to the national country teams with the M&E component.

15. This will cover the cost of time spent on management issues by an international consultant. The estimate is based on approximately 1.25 days per month (12) spent on management functions in each country (5) over 4 years at a rate of US$400/day.

16. This will cover the cost of travel (est. $1300 per mission (3 days) including DSA, travel etc) for approximately two missions per year to each of the project countries over the project duration for management supervisory purposes.  Note: items in line 16 and 17 constitute about 4% of the GEF funds for PMU activities.

##### SECTION IV: ADDITIONAL INFORMATION

## PART I : Other agreements

- Letters of financial commitment and the MOU with UNESCO/IOC have been added in the Exec. Summ. p. 98 and  Annex A9.

## PART II : Organigram of Project

- Refer section on Management Arrangements

## PART III : Terms of References for key project staff and main sub-contracts

- The TOR have been included in Annex A8.

## PART IV:  Stakeholder Involvement Plan

- As the ACCC project targets interventions at the community level in each of five countries, a wide range of stakeholders have been consulted. The PDF B process included a series of stakeholder consultations in each country (at the community as well as policy level) to validate the findings of the initial desk review of the problem of climate change and coastal erosion, as well as to identify activities to be implemented through the project. Moreover, prior to the implementation of pilot/demonstration projects, targeted activities will be undertaken to raise stakeholder awareness of coastline change and climate change issues and the benefits that coastal communities can derive from strategies to address these issues within the wider context of integrated coastal area management. Subsequently, the successful implementation of the proposed pilot/demonstration projects depend on the active involvement of all stakeholders (community, governmental, non-governmental as well as private sector), and the effective supervision of implementation and subsequent monitoring. Stakeholder participation will be assured by the consultative arrangements established under the project, whereby each party stands to benefit from the implementation of agreed strategies.

- The major stakeholders in the design of this project include:

- Communities in coastal regions vulnerable to climate change

- National government departments responsible for fisheries, marine and coastal affairs, infrastructure, environment and tourism

- National and Regional marine research institutions, universities

- Regional organizations, projects or conventions: e.g. Abidjan Convention & RCU, Canary Current LME, Programme Regional de Conservation de la Zone Côtière et Marine en Afrique de l’Ouest, UNEP/UNIDO GEF Project on Tourism in East and West Africa (including Senegal, Gambia); African Development Bank Projects, etc.

- Donor agencies that are active in the region

- Non-Governmental Organization involved in regional marine and coastal issues

- Private sector organizations involved in regional coastal issues

- Communities involved in harvesting and marketing coastal and marine resources

- In particular, UNFCCC focal points have been engaged at key regional and national level stakeholder discussions and have played an integral role in the preparation of the outputs that have contributed to this proposal. During the implementation phase, in order to ensure effective stakeholder involvement the project will:

- Establish mechanisms to empower and facilitate consultation with and between all national and local stakeholders

- Undertake activities to raise stakeholders awareness of coastline change issues and the importance of implementing measures to address such issues within the wider context of integrated coastal area management

- Ensure that designed measures, strategies and guidelines are consistent with national needs, and that there is constant interaction between the regional, national and local levels to ensure that Regional Project Steering Committee work in partnership with national focal points and local stakeholders

- Place a priority on the delivery of effective capacity development activities at the regional, national and local levels, and facilitate the exchange of experiences and lessons learned at all levels.

- The project has been designed to ensure broad stakeholder participation in all components. The PDF-B process included a series of stakeholder consultations in each country (at the community as well as policy level) to validate and obtain information identified through initial desk reviews. Moreover, prior to the implementation of pilot/demonstration projects, targeted activities will be undertaken to raise stakeholder awareness of coastline change and climate change issues and the benefits that coastal communities can derive from strategies to address these issues within the wider context of integrated coastal area management. Subsequently, the successful implementation of the proposed pilot/demonstration projects depend on the active involvement of all stakeholders (community, governmental, non-governmental as well as private sector), and the effective supervision of implementation and subsequent monitoring. Stakeholder participation will be assured by the consultative arrangements established under the project, whereby each party stands to benefit from the implementation of agreed strategies.

- The major stakeholders in this project are:

- Communities in coastal regions vulnerable to climate change

- National government departments responsible for fisheries, marine and coastal affairs, infrastructure, environment and tourism

- National and Regional marine research institutions, universities

- Regional organizations, projects or conventions: e.g. Abidjan Convention & RCU, Canary Current LME, Programme Regional de Conservation de la Zone Côtière et Marine en Afrique de l’Ouest, UNEP/UNIDO GEF Project on Tourism in East and West Africa (including Senegal, Gambia); African Development Bank Projects, etc.

- Donor agencies that are active in the region

- Non-Governmental Organization involved in regional marine and coastal issues

- Private sector organizations involved in regional coastal issues

- Communities involved in harvesting and marketing coastal and marine resources

- Specific stakeholders who have been consulted during the country specific consultations through national workshops, consultations at the pilot sites and other project meetings have been listed in the Executive Summary, Chapter 2 (page 34 – 40). Also, Annex A1 gives a more detailed description of the stakeholder involvement.

- In order to ensure effective stakeholder involvement the project will establish mechanisms to empower and facilitate consultation with and between all national and local stakeholders. This will occur through the National Steering Committees that will be formed in each country as part of the implementation set up (see section on Implementation Arrangements). The specific role of stakeholders, such as those identified above will be to:

- Undertake activities to raise stakeholders awareness of coastline change issues and the importance of implementing measures to address such issues within the wider context of integrated coastal area management

- Ensure that designed measures, strategies and guidelines are consistent with national needs, and that there is constant interaction between the regional, national and local levels to ensure that Regional Project Steering Committee work in partnership with national focal points and local stakeholders

- Place a priority on the delivery of effective capacity development activities at the regional, national and local levels, and facilitate the exchange of experiences and lessons learned at all levels.

Part V to X : OTHER ADDITIONAL INFORMATION AS REQUIRED BY THE SPECIFIC FOCAL AREA, OPERATIONAL PROGRAM, AND STRATEGIC PRIORITY .

- None

SIGNATURE PAGE

Country: Lead Country, Senegal

Other Participating Countries:

Cape Verde

Mauritania

Guinea Bissau

The Gambia

UNDAF Outcome(s)/Indicator(s):

_____UNDAF IN REVIEW PROCESS________________________________

(Link to UNDAF outcome., If no UNDAF, leave blank)

(CP outcomes  linked to the SRF/MYFF goal and service line)

MDG: ensuring sustainable development

Goal: Promotion of energy services and environment protection for sustainable development

Service Line: frameworks and strategies for sustainable development

Outcomes: Creation of sub-regional/national/local capacities for sustainable development

Core results: National Strategies for Sustainable Development for integrating of economic, social and environmental issues adopted and implemented

Expected Output(s)/Indicator(s): (Indicated below)

| Outputs | Indicators |
| --- | --- |
| 1.1 Implemented pilot demonstration activities reduce climate and anthropogenic driven coastline erosion Baseline vulnerability assessment studies completed | - Coastal erosion rates in pilot sites - Runoff rates in pilot sites - Areas (in hectares) of dunes covered by vegetation - Number of projects that promote alternative livelihood - Area (in hectares) covered by mangroves in the pilot sites |
| 2.1 Coastal management activities integrated across sectors, programmes and at various levels of society in the programme sites | - Integrated coastal management plan including climate change concerns formulated - Number of new and old developments adhering to zoning regulations |
| 2.2 National policies and programmes designed to facilitate adaptation to climate change in coastal regions | - Workshops and review reports on national plans and policies to integrate adaptation to climate change concerns. - Draft action plan for addressing coastal erosion. - Number of decentralized task forces in sub-national government agencies and community leaders participate in discussions to enforce laws and regulations. Score-card indicator |
| 2.3 Communities outside the project sites replicate successful approaches to mitigate and adapt to shoreline change (SPA & co-financing, district to national/regional level | - Number of communities adopting piloted approaches, Number of stakeholder exchanges; Information disseminated through print and electronic medium. - Number of media articles on the pilot projects - Number of contact points with an adaptation strategy that requires implementation. |

Implementing partner: Intergovernmental Oceanographic Commission (IOC) UNESCO

(designated institution/Executing agency)

Other Partners:							_________________________

Agreed by Government of Senegal:______________________________________________

Agreed by Government of Cape Verde: ___________________________________________

Agreed by Government of The Gambia: ___________________________________________

Agreed by Government of Guinea Bissau: _________________________________________

Agreed by Government of Mauritania:_____________________________________________

Agreed by (Implementing partner/Executing agency): UNESCO/IOC________________________________

Agreed by UNDP Senegal ________________________________________________________

Agreed by UNDP Cape Verde

Agreed by UNDP Gambia

Agreed by UNDP Guinea Bissau

Agreed by UNDP Mauritania

Agreed by the Ministry of Environment and  Nature Protection/Senegal

Agreed by the Ministry of Environment and Agriculture/Cape Verde

Agreed by the National Environment Agency/The Gambia

Agreed by the Departement of Environment/Mauritania

## List of Annexes

PÁRT 1:

Annex A1: 	List of stakeholders involved in the ACCC process so far.

Annex A4:	Project Design and Monitoring and Evaluation Framework.

Annex A5:	Example of Indicators

Annex A8: 	TORs

Annex A9: 	MOU with EA’s

Annex A10:	Template for inclusion of lessons learned in ALM

Annex A11:	Response Table to comments by GEFSEC members

PART II: To be sent separately.

Annex A2:	Overview of Stakeholder Consultations and Field Visit in The Gambia (An Example)

Annex A3:	Climate Change Scenarios for West Africa

Annex A6:	Country Reports (Summary of National Reports)

Annex A7:	Table with priorities from coutries’ CC EA (INC, SNC, NAPA).

Annex A1: 	List of stakeholders involved in the ACCC process so far.

Specific stakeholders who have been consulted during the country specific consultations through national workshops, consultations at the pilot sites and other project meetings have been listed per participating country below.

I. Guinea-Bissau

GOVERNMENT

- Ministère des Affaires Etrangères et la Coopération Internationale

- Ministère de l’Agriculture et Développement Rural

- Ministère des Travaux Publiques, Construction et l’Urbanisme

- Ministère du Tourisme et Aménagement du Territoire

- Ministère de la Pêche et Economie Maritime

- Ministère des Transports

- Ministère de la Solidarieté, la Famille et Lutte contre la Pauvreté

- Ministère de l’Administration Territoriale

- Ministère de l’Economie

- Secrétariat d’Etat à l’Energie

- Direction Générale d’Environnement

- Direction Générale de la Marine Mercante

- Direction Générale de la Météo

- Direction Générale des Fôrets

- Direction Générale des Ressources Hydriques

- Direction Générale de la Géologie et Mines

- Institut National des Etudes et la Recherche (INEP)

- Institut de la Biodiversité et Aires Protégées (IBAP)

- Institut National de la Recherche et Technologie Appliquée (INITA)

- Institut National de la Recherche Agraire (INPA)

- Centre de Recherche en Pêche Artisanale (CIPA)

# NGO

- Action pour le Développement (AD)

- Tiniguena

- Nantynian

- Guiné-Verte

- Associtation pour les Etudes et Alternatives (ALTERNAG)

- Association National des Paysans (ANAG)

# Projects

- CCLME

- PRCM

- AGIR

- OMVG

- EPAN-BD

- EPAN-Desertification

National Park Authorities

- Parc Naturel des Mangroves du fleuve Cachéu

- Parc Naturel des Lagunes de Cufada

- Parc National de l’Ile d’Orango

- Parc National de João Vieira et Poilão

- Maison de l’Environnement de Bubaque

- Autorité Traditionnelle du Village de Varela

# International Donor Organisations

- UICN

- SWISSAID

- PNUD

- FAO

- Coopération Française

- Union Européenne

- Communauté des Pays Lusophones

- Banque Mondial

- Banque Africaine de Développement

- Banque Islamique de Développement

- UEMOA

- CEDEAO

- Agence Espagnole de Coopération Internationale (AECI)

- Coopération Téchnique Alemande (GTZ)

- Service Neerlandais de Coopération (SNV)

- Coopération Portugaise

Media

- Rádios urbaines

- Rádios Communautaires

- Télévision Nationale

II.  Cape Verde

| Names | Organisations |
| --- | --- |
| Manuel Adilson Cardoso Fragoso | Direction Général Environnement |
| Carlos Guido S. De Figueiredo | Direction Général de la Douanes |
| José António R. da Graca | Service National de Protection Civile |
| Luciano Fonseca | FAO |
| Pedro Ramos | Direcção Geral do Ambiente |
| Carlos A Sousa Monteiro | DGPOG - MAAP |
| Carlos Dias | MAA – Maio |
| Laecticia Baudous | ONG – Maio |
| Fernando Jorge Frederico | Mairie de l’île de Maio |
| Orlando Delgado | Mairie de Porto Novo |
| Maria da Cruz G. Soares | Projet Conservation Marine et Côtière |
| Alcides Barros | DGCI/MNEC |
| Francisco Martins | INMG-Praia |
| António Reis | Délégation Maritime de Santo Antão |
| Manuel Soares Silveira | MAA –Porto Novo |
| João Spencer | INIDA |
| Marinho Rocha | Mairie |
| Lourenço Monteiro | Mairie de Paúl |
| Nuno Ribeiro | DGA |
| Victor Barreto | DGA |
| Margarida Varela | DGA / Consultant Local ACCC |
| Arlinda Duarte Neves | ANMCV / Consultant Local ACCC |
| Manuel Leão Carvalho | DGA / Consultant Local ACCC |
| Luísa Morais | INERF |
| Francisco Correia | INMG-Praia- Coord. National de ACCC |
| Adama Dao | PNUD |
| Jose Levy | PNUD |

III. The Gambia

| Names | Organisations |
| --- | --- |
|  | Coastal Communities |
| Alh. Yunus SAnneh | Brufut Village |
| Karamu Sanneh |  |
| Abdou Dampha |  |
| Alhagi Sanneh |  |
| Cherno Bojang | Tanjeh Village |
| Fanding Sanyang |  |
| Alas an Gibba |  |
| Alh. Momodou Gibba |  |
| Abdou K. Njie |  |
| Seedy Bojang | Tujereng Village |
| Kumba Trawally |  |
| Sireh Jatta |  |
| Abdoulie Jatta |  |
| Alh. Bakary Jabang | Sanyang Village |
| Demba Sanyang |  |
| Alikalo Kuruba |  |
| Alhagi Saidy |  |
| Malang Bojang |  |
| Baraka Touray | Gunjur Village |
| Nfansu K. Touray |  |
| Alh. Sabake Touray |  |
| Omar Jatta |  |
| Bubucarr Touray |  |
| Alikalo, Kartung | Kartung Village |
| Seyfo, Kombo South |  |
| Ousman Bangura | Bakau |
| L.C. Jammeh |  |
| Alkalo, Bakau |  |
| Alhagie Sanyang |  |
| Badou Faal | Banjul |
| MBK Sinyan |  |
| I.A.S. Burang John |  |
|  | Government Institutions |
| Jerreh Barrow | Geology Unit |
| Omar Ngum | Dept. of Community Development |
| Joko Sanyang | National Agric. Research Institute |
| Lamin Jobarteh | W/Africa Bird Watching Association |
| Lamin Bojang | Dept. of Forestry |
| Bernard E. Gomez | Dept. of Water Resources |
| Famara Darboe | Dept. of Fisheries |
| Jalamang Jatta | Dept. Agricultural Services |
| Kajali Sonko | Women’s Bureau |
| Fatou Raji | Gambia Tourism Authority |
| M. S. Jobe | Gambia Tourism Authority |
| Momodou Sowe | Poverty Alleviation Coordination Office |
| Dr. Almamy Camara | Dept. of Parks & Wildlife Management |
| Ishaqa Bah | Dept. of State for Finance & Economic Affairs |
| Mr. Bubu Jallow | PS, Dept. of State Fisheries and Water Resources |
| Mr. Ousainou Touray | ICAM Project, Dept. of Parks & Wildlife Mgt. |
| Mr. Momodou Sarr | Executive Director, Nat. Environment Agency |
| Mr. Momodou Canteh | Director, Technical Services Network, NEA |
| Mr. Saikou Njie | NEA |
| Mr. Adama Cham | NEA |
| Mr. Papa Secka | NEA |
| Mr. Dawda Badgie | NEA |
| Mr. Touray | NEA |
| Mr. Sulayman Chune | NEA |
| Mr. Babucarr Cham | NEA |
| Mr. Nfamara Jobe | NEA |
| Mr. Sheikh Alkinky Sanyang | NEA |
| Mr. Dodou Trawally | NEA |
|  | Non-governmental Institutions |
| Badara Bajo | Gunjur Env. Protection & Develop. Group |
| Ousman Sanneh | “ |
| Kebba Bajo | “ |
| Ousman Gaye | Brikama Area Council |
| Omar Njie | UNDO |
| Mamour Jagne | UNDP |
| Momodou Jallow | Forum for the Arts |
|  | Press |
| Ensa Badgi | Gambia Radio & TV Services |
| Amadou Bah | Gambia Radio & TV Services |
| Lamin Jabbi | Foroyaa Newspaper |
| Sulayman Makalo | Independent Newspaper |
| Sarata Jabbi | Point Newspaper |
|  | Secretariat/Accounts |
| Jacquiline Kolly | Secretary, NEA |
| Amadou Bah | IT Officer, NEA |
| Momodou Cham | Driver, NEA |
| Jumbo Cham | Messenger, NEA |
| Ajiawa Njabo | Accounts, NEA |
| Mamundaw Camara | Accounts, NEA |

Others

- The Association of Non-governmental Organizations (TANGO)

- The Hotel Association

- The Association Small Scale Enterprises in Tourism (ASSET)

- The Banjul City Council

- Kanifing Municipal Council

IV. Senegal

| Names | Organisations |
| --- | --- |
| Momar Talla DIAGNE | DREEC/Ziguinchor |
| Cherif CISSE | Projet Mangrove |
| Pathé BALDE | DEEC/MEPN |
| Ibrahima NDIAYE | DMP |
| Samba THIAM | DEFCCS/PRL |
| Massamba NDOUR | DEEC/MEPN |
| Aliou BA | EDEN Group Int. |
| Ibrahima TOURE | DE/MEM |
| Prosper HOUETO | Consultant |
| Dr Jean KALY | Projet Mangrove |
| Alassane DIENG | GIRMAC |
| Amadoune DIOP | DAT/MUAT |
| Pape Samba NDIAYE | ARD/Dakar |
| Djiby Alassane SOW | DAT/MUAT |
| Fagamou Sy DIOP | DREEC/Saint-Louis |
| Cheikh FOFANA | SINEPAD/Env |
| Amath Dior MBAYE | TROPICA |
| Dr Jacques André NDIONE | CSE / MEPN |
| Charles DIEME | DREEC/Dakar |
| Massamba DIENG | DCL/MIN.CL |
| Diendonné BAKANOVA | WAAME |
| Helene GNING | NSMTP |
| Rassoul NDAW | Mines |
| Birame DIOUF | CONGAD |
| Ndèye Fatou MBACKE | DUA / MUAT |
| Charles M. BEYE | Wet Lands International |
| Beytir GUEYE | DEFCCS/MEPN |
| Ousmane DIOP | PAD |
| Soudou DIAGNE | DTT/MIETTMI |
| Aïta Sarr SECK | DEEC/MEPN |
| Sokhna SY | DEEC/MEPN |
| Papa Goumbo LO | IST / UCAD |
| Momar SOW | DEEC/MEPN |
| Papa Mawade WADE | Consultant s/c CSE |
| Bamar DIAGNE | Dir. Météo.Nationale |
| Malick DIAGNE | GIRMAC |
| Ernest DIONE | DEEC/MEPN |
| Alioune KANE | Dpt Géologie/UCAD |
| Yakhya Aïcha DIAGNE | DREEC/Louga |
| Mamadou SALL | Journaliste au MESSAGER |
| Babacar Mbaye BALDE | Journaliste Radio Oxy-Jeunes |
| Abdoulaye THIAM | « Le Soleil « Président Asso.Journalistes en Environnement |
| Ibrahima SALL | MEPN/CEPS |
| Bocar MBACKE | Consultant / DEEC |
| Moussa DIOUF | PGIES |
| Michel SECK | DEEC/MEPN |
| Ndèye Fatou Diaw GUENE | DEEC/MEPN |
| Elimane BA | DEEC/MEPN |
| El Hadji Mbaye DIAGNE | DG Adjoint SONACOS |

V. Mauritania

| Names | Organisations |
| --- | --- |
| Maouloud N’Daye | PNUD |
| Samba Harouna | SGP/ FEM |
| Mohamed Ould Kercoub | ONG ABDS |
| Maloum Dine Ould Maouloud | Directeur Adjoint de l’Environnement |
| Sidi Mohamed Ould MD Yeslem | DA/DATAR |
| Ahmed Ould Senhoury | Université de Nouakchott |
| Mohamed Ould Md Vall | IMROP |
| Cheikh saad Bouh Ould Mohamed | PDU |
| Mohamd Ould Jiddou | FST |
| Ebnou Ould Ahmed | DENV |
| Ledib Ould Ebnou | ONNG/AREM |
| Sidi MD Ould Touhami | ONG/AFDD/ |
| Ahmed Ould Jiddou Ould Baba | CUN |
| Mahfoudh Ould Sidi Elemine | ASECNA |
| Oumar Deye | Maire Ndiago |
| Banemou Ould Tlayor | ONG AGREEM |
| Khattar Ould Tebakh | Direction Mine |
| Dia Ismaila | Direction Industrie |
| MD Ould Souleymane | Travaux Publics |
| Aboubakary Thia | Observatoire |
| El Hacen Ould Khouna | PREDAS |
| Aminetou mint Kebd | Observatoire du Littoral |
| Basse Diabdé | DTTSR/MET |
| Dr Abderrahmane Ould Limam | Expert |
| Sidi Ould Taleb Boubacar | DENV |
| Yemhelha mint Mohamed | DLE |
| Mahfoudh Ould Md Lamine | ONG LCP |
| Kaber Ould Md Lemine | ONG/PL/CAP |
| Md Lemine Ould Hmeyada | ONG PRONADE |
| Boubacar Diop | Projet Biodiversité |
| Marret Fredric | Conseiller Direction de l’Environnement |
| Baye Fall | Coord. C.C. |
| Abderrahmane Ould Hafed | PNBA |
| Marico Demba | Université de Nouakchott |
| Jade GEORIS CREUSEVEAU | PALM/UICN |
| Zeinebou Mint Sidoumou | Université/ FST |
| Moctar Ould Hacen | DATAR / MIPT |
| Cheikh Ould Soueidy | Direction du Tourisme |
| Ba Amadou | Parc National de Diawling |
| Mohamed Abdellahi Ould Selme |  |

Annex A3: Climate Change Scenarios for West Africa

Climate scenarios for the 21st century

Data covering West Africa are available from a number of global and regional climate model projections, although there has been much less emphasis on this region and on Africa as a whole than on other regions in model-based studies of future climate (Hulme et al., 2000. Climate scenarios are relatively robust in predicting warming across the African continent, including West Africa. Sea-level rise is expected to accelerate in the 21st century off the West African coast as elsewhere. Planning for coastal change may therefore be based on the assumption that mean temperatures and sea-level will increase regionally, although there is considerable uncertainty regarding the magnitude of future changes in temperature and sea-level. There is a high level of uncertainty regarding the evolution of rainfall in the West African region over the 21st century: while some model projections predict a decline in rainfall, others predict an increase. Uncertainties in these parameters are related to uncertainties in future greenhouse gas (GHG) emissions, climate sensitivity, the distribution of warming, and the responses of key systems to changes in global and regional mean temperatures.

It is therefore not possible, nor sensible, to choose a single climate scenario for the 21st century for the purposes of adaptation planning. Rather, a variety of plausible scenarios may be used to inform the development of flexible adaptation strategies designed to deal with a variety of possible climatic outcomes, within ranges suggested by modelling, observational, historical and palaeoclimatic studies. These strategies may be updated as new information becomes available.

Temperature

Most of the African continent warmed over the course of the 20th century, with the average rate and magnitude of warming reflecting that observed globally. However, mean annual temperatures over the West African coastal region exhibit a mean linear cooling trend of between 0.5º and 1.0º C between 1901 and 1995 according to Hulme et al., (2001). Warming of the African continent is expected to continue into the 21st century, with projected rates ranging from less than 0.2º to more than 0.5º C per decade, depending on emissions scenario and climate sensitivity. In terms median values from a range of model simulations, coastal West Africa experiences a similar warming to the rest of Africa, with temperatures increases being somewhat greater in the interior of West Africa (Hulme et al., 2001).

Rainfall

Model projections of rainfall over West Africa are inconsistent, with some simulations suggesting that the region will become drier, and others predicting increases in rainfall over the 21st century (Hulme et al, 2001). Recently a number of modelling studies have explicitly addressed the impacts on increased GHG concentrations on West African rainfall, with and without representing vegetation-atmosphere feedbacks. These studies suggest that increases in atmospheric GHG concentrations (from current elevated levels up to about 550 ppm) may make the West African rainfall regime more robust, and droughts less frequent and persistent (Brooks, 2004). A number of these studies show strengthening of the West African Monsoon (WAM) and a penetration of rainfall and vegetation further north, resulting in a “greening” of the northern Sahel and southern Sahara (Claussen et al., 2002; Maynard et al., 2002; Wang and Eltahir, 2002). These results are consistent with recent trends in the Sahel, where rainfall and vegetation cover have increased in many areas relative to the dry period lasting from the early 1970s until the mid 1990s (Anyamba and Tucker, 2005; Olsson et al, 2005).

Little modelling has been conducted of the response of the WAM to the high GHG concentrations (600 - 1000 ppm or greater) that will result from the sustained and unmitigated use of fossil fuels. A modelling study by Mitchell et al. (2000) suggests that stabilising atmospheric CO2 concentrations at 550 and 750 ppm by the end of the twenty first century will result in a warming of the southern hemisphere oceans and northern Indian Ocean relative to the remaining northern hemisphere oceans. Historically, this configuration of global sea-surface temperatures has been associated with dry conditions in the Sahel (Folland et al., 1986; Giannini et al., 2003). It is therefore plausible any intensification of the WAM at intermediate GHG concentrations may be followed by  a period of desiccation analogous to that experienced from the 1970s to the 1990s. In the study by Mitchell et al. (2000) this relative warming of the southern hemisphere does not occur at higher atmospheric CO2 concentrations. Over the coming century or longer it is therefore plausible that the Sahel and southern Sahara will experience alternating periods of humidity and aridity as atmospheric GHG concentrations increase, although this scenario is highly speculative at present, and a number of uncertainties remain, such as the role of ENSO.

Even if predictions of a strengthened monsoon prove accurate, rainfall is likely to remain highly variable both temporally and spatially. Changes in the rainfall regime may also be associated with shifts in seasonality. At present it is unclear whether any greening of the Sahel-Sahara transition zone will represent additional regional rainfall, or a redistribution of rainfall that may result in other parts of northern and western Africa becoming drier. The impacts of an intensification of the WAM is likely to have the greatest impact in northern Senegal and Mauritania. While additional rainfall in these regions may be beneficial in some respects, it might also be associated with negative impacts such as more frequent flash flooding and locust infestations, and inappropriate agricultural expansion into historically marginal areas such as occurred throughout the Sahel in the 1950s, resulting in dramatic increases in regional vulnerability to climate variability and change (Brooks et al., 2005).

Any changes in rainfall in the coastal region will have an impact on runoff and the transport of sediment to the coastal zone. Increases in rainfall may offset erosion or inundation in deltaic or estuarine areas as a result of increased sediment transport, but may lead to accelerated channel erosion. The impact of these processes on shorelines will depend on local topography and geomorphology. Changes in runoff may also affect marine and estuarine ecosystems through changes in salinity and/or turbidity. Buoyant freshwater plumes originating from continental runoff can inhibit the surface expression of coastal upwelling and generate instabilities in flow that alter marine circulation patterns (Kudela et al., 2005). Any increase in stream flow of major rivers may therefore have an impact on coastal marine ecosystems. Any increase in vegetative cover in the Sahel and Sahara may also reduce the mobilization and transport of dust to the Atlantic, where it is believed to play a role in biological productivity via iron fertilization (Brooks et al., 2005; Jickells et al., 2005).

Increases in humidity may partially offset atmospheric warming, due to increases in cloud cover and evaporation, the latter of which will result in the conversion of sensible to latent heat.

Sea-level rise

Sea-level rise (SLR) is likely to accelerate over the 21st century. The IPCC (2001) estimates an increase in global mean sea-level of 0.09 to 0.88m, with a central value of 0.48 m by 2100 relative to the 1990 level, based on 35 different scenarios. This value includes contributions from glaciers and the melting of ice sheets in the Arctic and Antarctic regions, and assumes that there will be little or no contribution from the disintegration of large ice sheets such as the Greenland Ice Sheet (GIS) and West Antarctic Ice Sheet (WAIS). The likelihood of a large contribution to global mean sea level during the 21st century from either of the ice sheets is thought to be low (Oppenheimer, 1998; Vaughan and Spouge, 2002), However, recent studies indicate that wasting of the GIS has accelerated in recent years, and that the WAIS may be less stable than previously thought (Paterson and Reeh, 2001; Rignot and Jacobs 2002; De Angelis and Skvarca, 2003; Bøggild et al., 2004; Gegory et al., 2004; Thomas et al., 2004). Glacial thinning in Alaska and Patagonia also accelerated towards the end of the 20th century (Arendt et al., 2002; Rignot et al., 2003). Taking into account these new findings, published after the 2001 IPPC report, it is reasonable to plan for a 1m increase in mean sea-level by 2100, with further, and perhaps more rapid, increases after 2100, due to the increasing likelihood of ice sheet collapse. In  the longer term, the loss of both the GIS and the WAIS is entirely plausible. Occurring over a period of up to 1000 years, the complete melting of these ice sheets alone would raise global mean sea-level by up to 13 m (Vaughan and Spouge, 2002; Gregory, 2004). A sustained (although not necessarily smooth) increase in sea-level of over 1m per century therefore represents a realistic long-term scenario.

The impacts of SLR of a magnitude likely to be experienced during the 21st century are potentially severe for the West African coastal zone. Low-lying areas, for example around the Gambian and Mauritanian capitals, are at risk of inundation as a result of relatively modest increases of sea-level. This risk will be increased by erosion and the destruction of coastal ecological and geomorphological systems such as mangroves and dunes. Increases in sea-level will increase water depth in shallow coastal marine waters such as the Banc d’Arguin in Mauritania, where the small water depth results in high salinity and water temperature (Sevrin-Reyssac, 1993). SLR may therefore cause changes in salinity, temperature and turbidity, in turn affecting ecosystem functioning.

Changes in circulation

Waters off the West African coast are sensitive to changes in the wind regime, which modulates upwelling strength, sea-surface temperatures and biological productivity (Moreno et al., 2002). Wind patterns in turn vary due to changes in the position and/or strength of the Azores high pressure region, which in turn is associated with variations in the strength of the North Atlantic Oscillation (NAO). Moreno et al. (2002) present evidence that cooler sea-surface temperatures, a strengthening of the Azores High and stronger trade winds during glacial-interglacial transitions led to increased productivity in the Canary Current region. Diffenbaugh (2005) presents results from model-based studies of eastern boundary currents in the 21st century that indicate changes in pressure and wind regimes, although the overall impact of these changes on ecosystems is unclear.

While the 21st century evolution of the coupled ocean-atmosphere system off West Africa is uncertain, palaeoclimatic analogues and modelling studies suggest that changes in upwelling strength and seasonality are likely. Such changes may interact with changes in continental runoff and sediment input to have significant impacts on biological productivity.

Summary

The climatic future of the West African coastal zone is uncertain, and no single scenario can be provided at present. While temperatures and sea-levels are almost certain to rise, rainfall may increase or decrease, and circulation changes will influence ocean productivity in ways that are currently unclear. Adaptation planning might be based on a “worst case” scenario incorporating the following assumptions:

- increases in mean surface temperature of up to 0.5º C per decade, with increased evapotranspiration

- increased rainfall variability and intensity resulting in increases in continental runoff and sediment transport,  but less predictability in the timing of rainfall

- accelerated SLR of around 1 m per century, resulting in accelerated coastal erosion and disruption to coastal marine ecosystems

- reduced coastal up-welling resulting from weakening of the Azores high and the trade winds, exacerbated by disruption from freshwater plumes of continental origin.

While this scenario is speculative, basing adaptation planning on worst case assumptions is a sensible precaution, provided it does not result in the diversion of resources into unnecessary activities. Given the extreme variability and uncertainty associated with climate and climate change in this region, a flexible approach to adaptation is essential.

References

Anyamba A. and Tucker, C. J. 2005. Analysis of Sahelian vegetation dynamics using NOAA-AVHRR NDVI data from 1981–2003, Journal of Arid Environments 63, 596–614.

Arendt, A. A. et al. 2002. Rapid wastage of Alaska glacier and their contribution to rising sea level. Science 297, 382-386.

Bøggild, C.E. et al. 2004. Towards an assessment of the balance state of the Greenland Ice Sheet. Geological Survey of Denmark and Greenland Bulletin 4, 81-84.

Brooks, N. 2004. Drought in the African Sahel: long-term perspectives and future prospects. Tyndall Centre Working Paper No. 61.

Brooks, N., Di Lernia, S., Drake, N. Chiapello, I., Legrand, M., Moulin, C. and Prospero, J. 2005. The environment-society nexus in the Sahara from prehistoric times to the present day. The Journal of North African Studies 304, 253-292.

Claussen M , Brovkin V, Ganopolski A, et al. 2003. Climate change in northern Africa:

The past is not the future. Climatic Change 57 (1-2), 99-118.

Cook, K. H. 1999. Generation of the African Easterly Jet and Its Role in Determining

West African Precipitation. Journal of Climate 12, 1165-1184.

De Angelis, H. and Skvarca, P. 2003. Glacier surge after ice shelf collapse. Science 299, 1560-1562.

Folland, C. K., Palmer, T. N. and Parker, D. E. (1986) Sahel rainfall variability and

worldwide sea temperatures, 1901-85, Nature 320, 602-606.

Gregory J. M. et al. 2004. Threatened loss of the Greenland ice-sheet. Nature 428, 616.

Hulme, M., Doherty, R., Ngara, T., New, M. and Lister, D. 2001. African climate change: 1900-2100. Climate Research 17, 145–168.

Intergovernmental Panel on Climate Change. 2001. IPCC Third Assessment Report, Climate Change 2001: The Scientific Basis. Cambridge University Press.

Jickells, T. D., An Z. S., Andersen, K. K., Baker, A. R., Bergametti, G., Brooks, N., Cao J.J., Boyd, P. W., Duce, R. A., Hunter, K. A., Kawahata, H., Kubilay, N., La Roche, J., Liss, P. S., Mahowald, N., Prospero, J. M., Ridgwell, A. J., Tegen, I. Torres, R. 2005. Global Iron Connections: Desert Dust, Ocean Biogeochemistry and Climate. Science 307, 67-71.

Kudela, R., Pitcher, G., Probyn, T., Figueiras, F., Moita, T. and Trainer, V. 2005. Harmful algal blooms in coastal upwelling systems. Oceanography 18, 184-197.

Maynard, K., Royer, J. F. and Chauvin, F. 2002. Impact of greenhouse warming on the

West African summer monsoon, Climate Dynamics 19, 499-514.

Mitchell, J. F. B., Johns, T. C., Ingram, W. and Lowe, J. A. 2000. The effect of stabilising

the atmospheric carbon dioxide concentrations on global and regional climate

change. Geophysical Research Letters 27(18), 2977-2980.

Moreno, A., Nave, S., Kuhlman, H., Canals, M., Targarona, J., Freudenthal, T. and Abrantes, F. 2002. Productivity response in the North Canary Basin to climate changes during the last 250 000 yr: a multi-proxy approach. Earth and Planetary Science Letters 196, 147-159.

Olsson, L., Eklundh, L.  and Ardo, J. 2005. A recent greening of the Sahel—trends, patterns and potential causes. Journal of Arid Environments 63, 556–566.

Oppenheimer, M. 1998. Global warming and the stability of the West Antarctic Ice Sheet. Nature 393, 325-332.

Paterson, W. S. B. and Reeh, N. 2001. Thinning of the ice sheet in northwest Greenland over the past forty years. Nature 414, 60-62.

Rignot, E. and Jacobs, S. S. 2002. Rapid Bottom Melting Widespread near Antarctic Ice Sheet Grounding Lines. Science 296, 2020-2023.

Rignot et al. 2003. Contribution of the Patagonia icefields of South America to sea level rise. Science 302, 434-437.

Sevrin-Reyssac, J. 1993. Hydrology and underwater climate of the Banc d'Arguin, Mauritania: a review. Hydrobiologia 258, 211-222.

Thomas, R. et al. 2004. Accelerated sea-level rise from West Antarctica. Science 306, 255-258.

Vaughan, D.G. and Spouge, J.R. 2002. Risk estimation of collapse of the West Antarctic Ice Sheet. Climatic Change 52, 65-91.

Wang, G. L. and Eltahir, E. A. B. 2002. Impact of CO2 concentration changes on the

biosphere-atmosphere system of West Africa. Global Change Biology 8, 1169-

1182.

Wolff, W. J., van der Land, J., Nienhuis, P. H. and de Wilde, P. A. W. J. 1993. The functioning of the ecosystem of the Banc d'Arguin, Mauritania: a review. Hydrobiologia 258, 211-222.

Annex A4: Project Design and Monitoring and Evaluation Framework.

The aim of the ACCC project is to deliver local and global benefits in the form of (i) enhanced capacity of coupled social-ecological systems to adapt to climate change, and (ii) the improved management and use of biodiversity through measures that both promote a combination of conservation and improved ecosystem resilience.  A combination of adaptive capacity (AC) and biodiversity (BD) related indicators will therefore be used to assess project performance. The project addresses a single, overarching goal and objective, which are approached by pursuing a set of outcomes, which are in turn realised through a number of different activities. Each activity will be designed to have a particular impact or set of impacts on the systems it has been designed to target. Approximately half the activities will be targeted at capacity development and biodiversity enhancement with respect to specific climate change threats, and will be eligible for core project funding under the terms of the SPA.  The remaining activities will support more general capacity development and biodiversity enhancement in order to reduce physical and social vulnerability to existing climatic and other threats. These activities will be supported by co-financing, and will complement the climate change activities, for example by increasing the resilience of ecosystems through the reduction or removal of anthropogenic stresses.

Types of indicators

Indicators will assess project performance on a variety of timescales, and different indicators will be required at different stages of the project.

Process indicators will assess levels of activity (e.g. number of community members or households engaged in alternative livelihood development, extent to which project activities are influencing policy development, new areas designated as protected etc.).  These will be used in a limited way throughout the project implementation phase.  It is recognized that process indicators can, by themselves, be of limited value as they do not accurately capture whether or not the project has had the desired outcome (i.e. reduced vulnerability to climate change or improved biodiversity, etc).  However, they are indicative of measures that have been implemented and are often used to complement other types of indicators.

In that respect, impact indicators will assess the consequences or impacts of the various activities (e.g. changes in household income, number of new developments with adequate setback from the shoreline, changes in forest cover or erosion rates at specific locations targeted by particular activities etc.).  Impact indicators will be relevant once the project has been running long enough for the various activities to start yielding results.

Outcome indicators will assess the extent to which the intended outputs and outcomes have been realised.  Whereas impact indicators will focus on the extent to which individual activities have had the intended results with respect to specific interventions, outcome indicators will assess the results of multiple activities in a more general sense (e.g. greater general preparedness for climate change, improvements in data coverage resulting from new monitoring sites, average erosion rates over large areas, economic losses and mortality from climate-related disasters etc.).  Outcome indicators will be most meaningful once a project has been running for multiple years, and after the project has ended. They must also be accompanied by assessments of causal mechanisms in order to establish that improved outcomes are the result of project activities and not simply coincidental.  Outcome indicators will rely heavily on qualitatively-derived scores, particularly in the area of capacity development, as outlined below.

#### Levels of intervention

Input, process, impact and outcome indicators will be developed at a number of different scales as appropriate for the various activities and outcomes.  For example, BD impact indicators may address a particular locality, a region or district, or a whole country or stretch of coastline.  Assessment of AC is less clear cut, due to the  AC impact indicators, for example relating to awareness, may address the individual (e.g. individual awareness of climate change), the organisational (e.g. incorporation of climate change considerations into policy), or larger scales.  UNDP-GEF (2003) define three levels of intervention for capacity development:

- The individual level, relating to the process of changing attitudes and behaviour, e.g. through training and the provision of knowledge, but also encompassing participation, ownership, motivation, morale, accountability and responsibility.

- The organizational level, focusing on overall performance and functioning capabilities, e.g. the ability to develop mandates, tools, guidelines, information management systems that help the organization adapt to change. Capacity development will also address the component parts of the organization (e.g. individuals and groups), as well as its interaction with its external environment.

- The systemic level, focused on the creation of “enabling environments” within which individuals and institutions can operate and realise their own adaptive capacity. At this scale adaptive capacity is influenced by the wider socio-economic, political, policy and regulatory environments, and by the ways in which institutions interact with one another.

The type of indicators chosen for M&E of project activities, and the scales at which these indicators are employed, will depend on the nature of the activity to be assessed.  This in turn will depend on the desired impacts and outcomes, as well as the social, economic, political and environmental contexts, which will determine what activities are feasible, effective and acceptable. In the Logical Framework a number of activities are identified based on the output of stakeholder meetings designed to identify adaptation options, as well as input from national teams. Each activity is associated with at least one suggested indicator.  However, these indicators should be viewed as preliminary, and subject to approval by project teams and stakeholders once activities reach the implementation stage.  It is important that the indicators (i) are appropriate to local contexts, (ii) serve rather than drive project development and implementation, (iii) are reviewed throughout the project in order to ensure that they are useful and representative of project activity and impact, and (iv) are supported by qualitative assessment and expert judgment.

## Quantitative and qualitative indicators

The indicators listed in the Logical Framework represent a mixture of quantitative and qualitative data. Quantitative data will be gathered by direct measurement, and will be most useful in assessing progress in the BD focal area, as well as the success of particular technical interventions associated with piloting activities. Both quantitative and qualitative results may be converted into scores, where this is required for the purposes of comparing outcomes in different localities or countries. Quantitative measurements may be given a score of, for example, 1 to 4 based on assigning results to quartiles. This would generally be done with respect to a baseline or target, and might be used to assess the success of a technical intervention such as increasing protective vegetative cover on coastal dunes. If the target was to revegetate dunes along 1 km of shoreline, the revegetation of 250m of shoreline dunes might be given a score of 1 out of 4, and so on.

#### Qualitative Indicators of Adaptive Capacity

To measure improvements in adaptive capacity, the Vulnerability Reduction Assessment (VRA) methodology may be used.  The VRA is a structured set of seven perception-based indicators, which are measured through open-ended questions that generate numerical scores and supporting qualitative information.  Corresponding to the five-stepped approach of the UNDP-GEF Adaptation Policy Framework (APF), the VRA measures perceptions of current risk, future risk, ability to adapt, and capacity to continue adaptation autonomously.

The seven indicators, with corresponding questions tailored to the ACCC project, are listed in table X below.

| APF Step | Indicator | Specific Question | Logic |
| --- | --- | --- | --- |
| Assessing current vulnerability | 1. Vulnerability of livelihood/welfare to existing climate change and/or climate variability. | What are the main current impacts of climate change on coastal processes in your locality/constituency/jurisdiction, and how severe are these present impacts on economic sectors and livelihoods (on a scale of 1-10)? | Addresses present climate-related development issues – often the main climate concern of many stakeholders. Applicable to climate variability and/or climate change (depending on specific risk and community context). Prepares target audience for following questions that are specific to anthropogenic climate change by grounding that discussion in a framework that relates it to present impacts. |
| Assessing current vulnerability | 2. Efficacy of coping mechanisms in the face of current climate change/climate variability risks. | What, if any, measures are taken in response to present impacts of climate change including variability on coastal processes in your locality/constituency/jurisdiction, and how effective are they (on a scale of 1-10)? | During the first VRA meeting, this question will describes baseline adaptation to climate variability. During subsequent meetings, it will assess progress against that baseline. Applicable to climate variability and/or climate change (depending on specific climate risk and community context). As above, grounds community in present practices, preparing them to think about how changing conditions might impact those practices. |
| Assessing future climate risks | 3. Vulnerability of livelihood/welfare to developing climate change risks.* *Climate risks as based on country strategies, which in turn are based on National Communications and NAPAs | Describe the local impacts of climate change on coastal processes in your locality/constituency/jurisdiction, and describe the severity of those projected impacts on livelihoods, ecosystems and economies in your locality/constituency/jurisdiction on a scale of 1-10. Note: “Local impacts” can here be understood to represent local manifestations of country-level impacts, described in annex A6 of the UNDP project document. | Once present context of variability has been discussed, this question focuses the community on their perceptions of likely impacts of climate change. This question is based on “likely” impacts on sectors identified in project target, which in turn are based on CCPS. Allows the community to begin to consider long-term viability of livelihood practices in the face of climate change, leading to the following question. |
| Assessing future climate risks | 4. Ability of the community to respond to developing climate change risks. | To what degree (on a scale of 1-10) is your locality/constituency/jurisdiction currently able to effectively respond to the coastal risk(s) described above, without a diminution in livelihoods, economic sectors, ecosystems, or other important goods/sectors/processes? | This question compliments the previous one by focusing the community on potential actions to respond to CC. During the first VRA meeting, this question will measure baseline adaptive capacity. During subsequent VRA meetings, as answers to this question improve, this question measures progress against that baseline, influenced by the project intervention. |
| Formulating an adaptation strategy | 5. Magnitude of barriers (institutional, policy, technological, financial, etc) barriers to adaptation. | What adaptations strategies are being considered in your locality/constituency/jurisdiction, what are the barriers (economic, political, social) to the successful implementation of these measures, and how surmountable are they (on a scale of 1-10)? | This question will qualify the above question, and focus it onto the needs of the community in successfully achieving adaptation. This question will identify policy barriers, forming useful lessons for the country and global programmes. This question will also measure unintended consequences, unexpected setbacks, and other barriers that were not identified during the project scoping phase. |
| Continuing the adaptation process | 6. Ability and willingness of the community to sustain the project intervention | With regard to the specific interventions that will arise from the ACCC project, to what degree do you think that these have the potential to continue after the conclusion of the project period, given current capacity (measured on a scale of 1-10)? | This question measures project sustainability and ownership, essential if adaptation to long-term climate change is to be successful. |
| Continuing the adaptation process | 7. Ability and capacity of community to continue the adaptation process, and to carry it beyond the specific project focus | To what degree (on a scale of 1-10) do you believe that there is capacity, willingness, and resources in your locality/constituency/jurisdiction to evaluate climate risks and undertake interventions in the coastal sector, outside the ambit of the ACCC project? | This question measures adaptive capacity more directly than other questions, as it seeks to determine to what extent communities will continue to adapt, and to what extent they feel that they are able to do so. |

Questions are posed to an agreed-upon group of stakeholders, and are recorded using the “H-form (Figure X).”  The H-form is a good general tool for eliciting information from groups of stakeholders, for example during meetings and workshops, and for translating qualitative data into scores.  Generally, the H-form is drawn on a large flip chart for participatory community vulnerability assessment, but may be adapted into a short questionnaire, where key stakeholders individually score the questions and write in their responses.  Regardless of the approach, the wealth of qualitative data generated from the VRA and the H-form also facilitates the development of case studies and lessons learned.

Figure 1:  The H-form.  In a group context, participants score their response to the given question along the center line, and provide comments supporting their choice of score on the left and right sides of the form.  Feedback on potential ways of improving the score is recorded at the bottom.  For the purpose of the VRA, low scores are always unfavorable, while hih scores are always favorable.

The output of one VRA measurement is a VRA index value, which is just a simple average of the seven scores for each individual question.  This value is meaningless on its own, as two individuals or groups might measure objectively identical situations differently.  The key output of the VRA – over the course of a project in which several VRA measurements occur – is the percentage change in VRA values from the first measurement to the last measurement.  Taken at mid-course in a project, the VRA also can also identify situations that require corrections in the course of a project, through lack of performance in subjective scores, or through qualitative comments supporting those scores at the sides and the bottom of the H-form.  Thus, the H-form allows for M&E to contribute to dynamic project management.

The appropriate methodology for measuring the VRA should be tailored to those that it seeks to measure the perceptions of.  For example, VRA measurements from a group of artisanal fisheries would be conducted very differently than VRA measurements from a group of local government officials.

#### Process for VRA Implementation in the ACCC Project

The VRA measures perception, and as such should be targeted at those whom a given project is designed to benefit, and not at those who are responsible for the implementation of a project (who may have a personal stake in the project’s success or failure).  Thus, the first step in the VRA process is determining who what stakeholders will participate in VRA, when VRA will be measured, and how it will be measured.  Determinations should be made as to whether to include local stakeholders such as people living and working in coastal regions, CBO or NGO representatives who might represent the interests of local people, local government officials, private sector representatives, or local experts.  Regardless of the choice, the group should be available for the total period of the project, as consistency among the participants is important to maintain the continuity required for the index of change in perception of vulnerability and adaptive capacity.

After a target group of stakeholders/beneficiaries for the VRA is selected, the schedule for VRA meetings should be determined.  While in all cases one VRA measurement should be taken at the beginning and another at the end, one or more measurements should be taken to correspond with project milestones, or appropriate times for project revision.  These schedules should be determined on a country by country basis, and approved by the Implementing Agency, along with the choice of stakeholders for the VRA.

#### Qualitative capacity development indicators from scorecards

The UNDP-GEF capacity development indicator framework includes the following strategic areas of support:

- capacity to conceptualize and formulate policies, legislation and programmes

- capacity to implement policies, legislation and programmes

- capacity to engage and build consensus among all stakeholders

- capacity to mobilize information and knowledge

- capacity to monitor, evaluate, report and learn

Capacity development does not lend itself to assessment using easily measurable quantitative indicators, such as may be used to assess the success of technical interventions.  While some measurable quantities (e.g. number of staff trained) may be relevant to the assessment of adaptive capacity, processes of adaptation, and the associated processes underlying behavioural changes at different levels, and are poorly understood and difficult to confine within the bounds of the logical framework.  Assessment of capacity (in this case adaptive capacity) requires a more qualitative approach, while at the same time providing practical, useful data that can be employed to compare project performance across different sites, regions and countries.  For this project, a score-card approach is suggested, based on that piloted for the UNDP-GEF biodiversity and climate change focal areas (UNDP-GEF, 2003).  For each of the five strategic areas listed above, the scorecards present a number of descriptive sentences relating to different levels of success, with a score assigned to each sentence. Respondents will be asked to choose a score based on which sentence they feel most accurately describes success in a particular area.  These score-card indicators, derived from qualitative data, are particularly relevant to Outcomes 2 and 3, and will complement the relevant quantitative indicators listed in the Logical Framework.

Table 1.  Score-card AC indicators for project impacts and outcomes.

| Strategic Area of Support | Level, funding (SPA/CF) | Output | Outcome Indicators (Scorecard) | Initial Evaluation | Expected Outputs | Programme Activities | Target | Evaluative Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, legislation and programmes |
| 1.1 | Systemic, SPA | The adaptation agenda is being effectively championed / driven forward | 0 - There is effectively no adaptation agenda 1 - There are some persons or institutions actively promoting adaptation in the policy arena, but they have little effect or influence 2 - There are a number of adaptation champions that drive the adaptation agenda, but more is needed 3 - There are an adequate number of able champions and leaders effectively driving forward an adaptation agenda | 0 | Adaptation network / advocacy group comprising members from different departments and agencies created | Creation of group, engagement of policy makers | 3 |  |
| 1.2 | Systemic, SPA+CF (protection against anthrop. & CC drivers of erosion & degradation) | There is a strong and clear legal mandate for the establishment of adaptation strategies, linked to designation of protected areas | 0 - There is no legal framework for adaptation or protected areas 1 - There is a partial legal framework but it has many deficiencies 2 - There is a reasonable legal framework but it has a few weaknesses and gaps 3 - There is a strong a clear legal mandate for the establishment of protected areas and the implementation of management schemes | 1 | New laws enacted on protection of key areas, including space for migration where appropriate | Development and enactment of laws, with attention to impacts on land tenure and livelihoods | 3 |  |
| 1.3 | Institutional SPA+CF (ICAM must address anthrop. & CC drivers of coastal change) | There is an institution responsible for the ICAM, including the development and implementation of adaptation strategies | 0 - ICAM institutions are unaware of, and have no plans to adapt to, climate change 1 - ICAM institutions are aware of climate change but have few or no strategies to deal with it 2 - ICAM institutions have developed some strategies to adapt to climate change but these are poorly resourced, inadequate and top-down in nature 3 - ICAM institutions have active, well-resourced, participatory strategies for adaptive to climate change | 1 | Creation or strengthening of ICAM institutions with adaptation as one of the principle foci of activity | Establish-ment of ICAM institution and/or main-steaming of adaptation into ICAM | 3 | No ICAM strategies or overseeing institutions in some countries |
| 2. Capacity to implement policies, legislation and programmes |
| 2.1 | Institutional SPA+CF (mandate will include general management, e.g. of pollution, land use etc) | There is a well-resourced ICAM institution mandated to implement adaptation strategies and measures, with well trained and motivated staff | 0 - ICAM institution is poorly resourced with no mandate for implementation or enforcement 1 - Institution has some resources but little power to enforce measures necessary for adaptation 2 - Institution is reasonably well resourced and has some success in enforcement but gaps remain 3. - Institution is well resourced and enforcement is effective, supported by strong legal framework | 1 | Institutions have resources, mandate and ability to enforce necessary management measures | Strength-ening of institutional mandates | 2 |  |
| 2.2 | Systemic / Institutional SPA+CF (ICAM plans will be based on adaptive management of dynamic systems forced by CC, plus management of anthrop. drivers) | Comprehensive ICAM policies & strategies exists which incorporate adaptation, are flexible and responsive, and regularly updated | 0 -- There is no policy or it is old and not reviewed regularly; 1 -- Policy is only reviewed at irregular intervals; 2 -- Policy is reviewed regularly but not annually; 3 -- ICAM and adaptation policies and plans reviewed and updated annually | 0 | Policies and strategies are constantly evolving to ensure that ICAM plans are appropriate in the changing climatic environment | Review of existing policies and strategies, and development of mechanisms for regular review | 3 |  |
| 2.3 |  | Protected areas designated in order to allow ecosystems to adapt, with intervention where necessary | 0 - No protected areas 1 - Some protected areas but boundaries poorly delineated little or no enforcement of protective measures 2 - Well-defined protected areas with some effective enforcement, but gaps and limited success due to conflicts of interest, lack of resources and absence of strong legal framework 3 - Clearly delineated protected areas with successful enforcement of protective measures | 1 | Resilience of key ecological and geomorphological systems enhanced by protective measures that enable them to respond and adapt to CC impacts | Designation of protected areas where risk of erosion or other CC impacts high, development of enforcement policy, within effective legal framework | 2 |  |
| 2.4 | Systemic SPA (planned adaptation may involve measures that adversely effect livelihoods or require relocation of certain activities and settlements) | Mechanisms for conflict resolution exist and are adequate for addressing potential adverse impacts of adaptation measures on communities & livelihoods | 0 - Conflict resolution is generally not considered and no mechanisms exist 1 - Need for conflict resolution is recognized, but not pursued seriously 2 - Mechanisms for conflict resolution exist but are rarely deployed, inadequate, and have very limited success 3 - Conflict resolution is pursued effectively through community and stakeholder engagement, with adequate compensation offered where appropriate | 0 | Implementing agencies have access to specialists in conflict resolution and mediation; recognized processes for resolving conflicts, frameworks for compensation exist | Training in conflict resolution, development of frameworks for conflict resolution and frameworks for allotting compensation | 3 |  |
| 2.5 | Systemic / individual SPA+CF (alternative livelihoods will be necessary to replace those made untenable by CC, but also to reduce anthrop. drivers of coastal change) | Alternative livelihoods are available to offset negative livelihood impacts of adaptation | 0 - Livelihoods are undermined by adaptation measures, resulting in increases in poverty and marginalisation 1 - Limited compensation is given to those whose livelihoods are affected by adaptation measures, but this is less than adequate 2 - Alternative livelihoods are developed, but uptake is patchy and success is mixed; no conditionality of adaptation on alternative livelihood development 3 - Adaptation measures are automatically linked to the development of successful livelihood alternatives, and are only implemented when these are acceptable to those affected | 0 | Adaptation measures do not increase poverty and marginalisation, and foster the development of sustainable livelihoods | Piloting of alternative livelihood strategies | 3 |  |
| 3. Capacity to engage and build consensus among all stakeholders |
| 3.1 | Systemic SPA | Adaptation plans have the political commitment they require | 0 - There is no political will at all, or the prevailing political will results in maladaptive actions; 1 - Some political will exists, but is not strong enough to make a difference 2 - Reasonable political will exists, but is not always strong enough to fully support the necessary adaptation measures 3 -- There are very high levels of political will to support adaptation measures | 0 | Awareness raised among decision makers | Engagement & training of decision makers in CC and adaptation issues | 3 |  |
| 3.2 | Individual / Systemic SPA+CF (public engagement must address need for adaptation but also role of anthrop. drivers in increasing vulnerability) | Adaptation measures have the public support they require | 0 -- The public has little interest in adaptation and there is no support for adaptation measures, perhaps hostility towards them; 1 -- There is limited support for adaptation & protected areas; 2 -- There is general public support for adaptation measures, provided the perceived impacts of adaptation measures are not too disruptive 3 - Adaptation is widely recognised as essential and people are prepared to make sacrifices for the sake of long-term sustainability | 1 | Awareness raised among general public through media campaigns and stakeholder engagement | Media campaign, training of community members as adaptation “focal points”, building links between government and communities via stakeholder workshops | 3 |  |
| 3.3 | Institutional SPA+CF (ICAM requires management under baseline and future climatic conditions) | ICAM institutions are mission oriented | 0 - Institutional mission not defined; 1 -- Institutional mission poorly defined and generally not known and internalized at all levels; 2 - Institutional mission well defined and internalized but not fully embraced; 3 – Institutional missions are fully internalized and embraced | 1 | Well-defined adaptation strategies based on ICAM and adaptive management principles, informed by CC scenario information | Develop strategies for adaptation as component of ICAM | 3 | No ICAM strategies or overseeing institutions in some countries |
| 3.4 | Institutional SPA+CF (see above) | ICAM institutions can establish the partnerships needed to achieve their objectives | 0- ICAM institutions operate in isolation; 1 - Some partnerships in place but significant gaps and existing partnerships achieve little; 2 - Many partnerships in place with a wide range of agencies, NGOs etc, but there are some gaps, partnerships are not always effective and do not always enable efficient achievement of objectives; 3 - ICAM institutions establish effective partnerships with other agencies and institutions, including provincial and local governments, NGO's and the private sector to enable achievement of objectives in an efficient and effective manner | 0 | Partnerships with other ministries and with NGOs and communities established | Facilitate building of partnerships through workshops, bilateral meetings, etc | 2 | No ICAM strategies or overseeing institutions in some countries |
| 4. Capacity to mobilize information and knowledge |
| 4.1 | Systemic SPA+CF (data includes climate data but also data on ecosystem functioning, pollution, loss due to anthrop. drivers etc) | Institutions and organizations have the data & information they need to develop, implement and monitor strategies to plan for and respond to CC | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 -- Much information is easily available and mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 -- Institutions have the information they need to develop, implement and monitor adaptation strategies | 0 | Institutions will have access to sufficient information for them to develop informed adaptation strategies | Collation of information on historical trends, provision of CC scenario information, implemen-tation & strength-ening of monitoring stations & networks | 2 |  |
| 4.2 | Institutional SPA+CF (staff trained in CC science and adaptation issues, technology provided for processing & mapping of geographic, scientific, vulnerability data etc) | Institutions have the ability to process and interpret CC and adaptation-related data & information and to develop informed adaptation strategies | 0 -- Staff are few and poorly trained, and resources to process information are limited or nearly non-existent 1 -- Some well-trained staff, but few resources 2 -- Staff generally well-trained and resources sufficient for processing and using data, but some gaps in expertise and technology 3 -- Staff cover all necessary areas of expertise and are well resourced with information technology, GIS, access to international journals and emerging data streams | 0 | Available information will be used effectively and fully in development of adaptation strategies | Technical training for staff and provision of IT equipment including GIS where needed | 2 |  |
| 4.3 | Institutional SPA+CF (information and outreach will include CC adaptation and general coastal zone management issues) | Institutions are able effectively to disseminate information on CC, adaptation and management strategies to the public | 0 -- information on CC & related issues does not reach the public 1 -- Information is disseminated but not understood or seen as irrelevant by the public 2 -- Information reaches some sections of the public, e.g. more educated sectors, & informs views of adaptation & management needs 3 -- Information reaches wide cross section of public and is understood, fostering widespread recognition of need for adaptation | 0 | Regular dissemination of new information to a receptive public | Training in public communication of science for institution staff, setting up of partner-ships with media | 3 |  |
| 5. Capacity to monitor, evaluate, report and learn |
| 5.1 | Systemic | Adaptation policy is continually reviewed and updated | 0 -- There is no policy or it is old and not reviewed regularly; 1 -- Policy is only reviewed at irregular intervals; 2 -- Policy is reviewed regularly but not annually; 3 -- Adaptation policy is reviewed annually | 0 | An updated policy elaborated and mechanism for regular update in place | Policy and mechanisms for updating developed | 2 |  |
| 5.2 | Systemic | Society monitors the state of vulnerable areas | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the protected areas | 0 | Wide ranging public awareness raised, at all levels of society | Media campaign | 3 |  |
| 5.3 | Institutional | Institutions are highly adaptive, responding effectively and immediately to change | 0 -- Institutions resist change; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change | N/A |  | Establishment of PACU. | 3 | Little information available |
| 5.4 | Institutional | Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 1 | Internal reporting, monitoring and evaluation system developed and applied within new PA agency | Staff training | 3 |  |
| 5.5 | Systemic | Examples of successful adaptation inspire and are emulated by other institutions, communities, individuals | 0 - Adaptation projects occur in isolation and are not known outside immediate locality 1 - Some awareness of projects but little emulation due to lack of capacity for autonomous “imitation” 2 - Some emulation but autonomous adaptation patchy 3 - Widespread awareness of adaptation examples leads to widespread autonomous adaptation drawing on examples | N / A no such projects at this stage | Autonomous adaptation outside pilot sites, based on similar principles and learning by example | Information dissemination and exchange | 2 |  |

Annex A5: Examples of BD specific Indicators

Guidance on measuring the performance and outcomes of biodiversity projects using indicators is available on the GEF website at:

http://thegef.org/MonitoringandEvaluation/MEPoliciesProcedures/MEPIndicators/mepindicators.html

Specific indicators from the Biodiversity Focal Area are available though http://thegef.org/Working_Paper__12.pdf

An appropriate suite of indicators (based on the above guidelines) will be discussed, and selected at the inception workshop for the project prior to implementation.

#### INDICATORS FROM THE GEF BIODIVERSITY PROGRAM

Next to local level benefits, the ACCC project will demonstrate global environmental benefits in biodiversity. Therefore, indicators such as those proposed on pages ix - xii of GEF Monitoring and Evaluation Working Paper 12 may be used (Measuring Results of the GEF Biodiversity Programme, 2003: http://thegef.org/Working_Paper__12.pdf).  These indicators are divided into coverage, impact and context categories, with coverage and impact indicators being most relevant to project and programme performance (and the only ones dealt with here). The indicators relate to four outcomes, and examples of indicators that might be particularly relevant in the context of the ACCC project  (in terms of demonstrating global environmental benefits) and are grouped under these outcomes below. The indicators are identified according to their type (i.e. indicators of coverage or impact) and the scale at which they operate (project, programme etc).  While the working paper focuses on the programme level, some indicators might be applied at both the programme and project levels, for example hectares of protected areas addressed by individual projects and the programme as a whole.

4.  The ACCC  project teams need only use a relatively small number of indicators for assessing global environmental benefits/biodiversity aspects of the ACCC activities, as practical and appropriate to the activities in question.

Outcome 1. Establishing and extending protected areas and improving their management

- Number of projects addressing protected areas and number and hectares of protected areas (coverage; programme - also project for number of hectares)

- Number of projects addressing protected areas under a particular IUCN management category (or national equivalent) and number of hectares (coverage; programme)

- Number of projects addressing protected areas under any “global priority lists” (i.e., World Heritage sites, Ramsar, MAB, hotspots) and number of hectares (coverage; programme)

- Improvement in management effectiveness of protected areas receiving GEF support according to WWF/WB scorecards measured at three times during project implementation: initial (baseline), mid-life, and final stage of project (impact; programme, project)

- Change in number and hectares of protected areas by IUCN management category resulting from GEF interventions (impact; programme, project)

Outcome 2. Conserving and ensuring sustainable use of biological resources in the production environment (landscapes and seascapes

- Number of hectares addressing production environment and biodiversity (coverage; programme, project)

- Number of projects addressing conservation and/or sustainable use of wild species (coverage; programme)

- Change in area of production environment receiving GEF funding under verified sustainable management, in transition towards sustainable management, or with integrated zoning plans adequately reflecting biodiversity considerations (impact; programme, project)

- Change in area for agri-biodiversity under or in transition to verified sustainable management systems (impact; programme, project)

Outcome 3. Improving enabling environment through action at (a) the national and local, and (b) the international level

- Number of projects whose objectives include reform of sectoral policies, laws and regulations to reflect biodiversity considerations (coverage, programme level)

- Number of projects aiming to develop capacity to manage biological resources (coverage, programme)

- Number of projects aiming to enhance public awareness and/or formal education about biodiversity (coverage, programme)

- Number of projects addressing financial arrangements for conservation and sustainable use of biological resources (coverage; programme)

- Changes in sectoral policies, laws and regulations to reflect biodiversity considerations (i.e. number of relevant sectoral policies, laws and regulations that have moved along the pathway from drafting to enforcement with GEF support) (impact, programme)

- Number of NGOs implementing GEF projects (impact; programme, project)

- Leveraging of national funding for biodiversity (i.e. changes over time of national sources co-financing in GEF projects) (impact, programme)

Outcome 4. Facilitating fair and equitable sharing of the benefits arising from the use of genetic resources

- Number of projects addressing the sharing of benefits arising out of genetic resources as defined by CBD (coverage, programme)

- Number of agreements on access and benefit sharing concluded with GEF support (impact, programme)

- Dollar value of benefits transferred under agreements on access and benefit sharing concluded with GEF support (impact; project, programme)

5.  The indicators listed above may also be adapted for ACCC activities to assess coverage, processes and project impacts. For example, whereas a biodiversity programme might assess the number of projects aiming to enhance public awareness of or formal education in biodiversity, ACCC activities might include awareness raising about climate change and adaptation. A programme-level coverage indicator might then be the number of projects including an climate change awareness-raising component, while a project-level process or impact indicator might be the number of climate change awareness raising activities planned or generated by a project.

# ANNEX A8: Terms of Reference for ACCC Project Management

For the purpose of these terms of reference:

- Implementing Agency (IA) refers to UNDP-GEF Capacity Development and Adaptation Clustre

- Regional Coordination Unit (RCU) refers to the project management team, consisting of the regional project manager and his team of assistants/financial managers; established at the UNESCO BREDA office;

- Regional Project Manager (RPM), refers to a manager for the overall project; recruited internationally by IOC/UNESCO, in consultation with UNDP;

- Regional Project Steering Committee refers to a coordinating body consisting of  the National Coordinator from each country, representatives from the National Lead Agency, Implementing Agency (UNDP), UNESCO/IOC, UNDP Country Offices), any co-funding partners contributing actual cash assistance to the Project aims and SINEPAD

- National Lead Agency (NLA) refers to the government body that holds national responsibility for the project.

- National Project Director refers to the responsible person within the NLA for the project.

- National Steering Committee (NSC) refers to an assembly of senior (policy level) representatives from relevant government agencies/sectors (e.g. Fisheries, Environment, Industry, Finance, Tourism, etc.), NGO representatives as appropriate (environmental and industry), relevant funding agencies and community representation. Also, the NAPA coordinator will be included in the National Steering Committee and will be consulted to ensure coordination with NAPA follow up activities of relevance to this project.  Duplication with NAPA activities must be avoided.

- National Project Coordinator refers to a locally recruited project manager who will also provide technical input;

- National Project Bureau refers to the project management team, consisting of the NPC and his team of assistants and financial people;

- Regional/National Technical and Financial Project Assistants refer to the supporting staff for the coordinator and manager.

The following terms of reference focus on responsibilities of each of these partners in project implementation. Note: This model should be adapted as necessary to the actual needs and circumstances of the project.

## Implementing Agency

The Project will be implemented by UNDP-GEF (CDAC). It is responsible for provision of:

- staff for monitoring and supervision of the Project;

- Technical advice when needed.

UNDP will also provide implementation support services from its Dakar Regional Coordination Unit and from the relevant UNDP country offices.

The UNESCO has been designated by the Governments of Cape Verde, Guinea Bissau, Mauritania, Senegal and The Gambia to oversee the national execution (NEX) of the UNDP-supported (ACCC) project on its behalf.

UNESCO/IOC will be responsible for substantive issues related to the coordination of the project and the implementation of regional activities. UNESCO/IOC will provide the technical inputs to the Project and will be responsible for the monitoring and evaluation component.  It will also be responsible for setting up and operating the Regional Project Steering Committee (RPSC), and ensure that the five participating countries work in a coordinated manner and not as individual projects.  UNESCO/IOC will also lead the regional platform for exchange of information, capacity building delivery and the syntheses of experiences and lessons. In order to fulfil these responsibilities, UNESCO/IOC will establish a Regional Coordination Unit located at the UNESCO Regional Office for Africa (Senegal

Regional Project Management Unit (RMPU)

Regional coordination and collaboration, and the execution of regional activities will be facilitated through a Regional Coordination Unit. The RPMU established at the UNESCO BREDA Office, will provide technical advice to all project participants, as well as organize activities and administrative requirements for the regional component. It will consist of a Regional Project Manager and his team of financial and technical assistants.

The RPMU will coordinate regional activities, including:

a. Facilitating communication between participating countries and the National Project Management Teams.

  - Working with UNDP-Cos and National Lead Agencies to establish the Regional Project Steering Committee.

  - Hosting an annual meeting that will bring together representatives of all participating countries, the Regional Project Steering Committee, the National Project Management Teams and others as required.

  - the formulation of co-financing/collaboration  arrangement with potential regional and international partners;

  - Integrate the lessons learned and best practices into the Adapatation Learning Mechanism.

The RPMU will be directly accountable to the Implementing and Executing Agencies, and to the Regional Project Steering Committee of the Project. For the job descriptions of the team members, see below.

### Regional Project Steering Committee

A Regional Project Steering Committee (RPSC) will be established and should consist of the National Coordinator from each country, Representatives from the National Lead Agency, Implementing Agency (UNDP-GEF), UNESCO/IOC), any co-funding partners contributing actual cash assistance to the Project aims and SINEPAD, as the key partner organization for GEF in the region.

Observers, who may be invited to attend by the Committee meetings, may include regional stakeholder representation, environmental NGOs (regional and international), other donor agencies, etc.  Observer attendance will be agreed by consensus within the Committee membership.  It is anticipated that regional programmes such as CCLME, PRCM and Abidjan Convention would be invited to attend as observers. The Committee will be jointly chaired by a national representative (on a rotational basis) and by the Implementing Agency representative (UNDP-GEF).

The RPSC should meet annually, and in order to reduce bureaucracy and limit the added burden to country representatives, the Committee meetings will be held as a contiguous meeting to other regional meetings.

The main functions of the RPSC will be to:

- monitor progress in project execution;

- provide strategic and policy guidance;

- review and approve annual work plans and budgets (including revisions) for the project;

- identify specific capacity building needs;

- review and endorse all formal monitoring and evaluation reports and findings;

- provide a regional forum for reviewing and resolving national concerns;

- provide a regional forum for stakeholder participation;

- provide a platform from which to launch new initiatives related to the Project but requiring separate donor support;

- ensure all interested parties are kept informed and have an opportunity to make comment.

## NEX/DEX mechanism

In each participating countries a national execution mechanism will be put in place. In most countries, the national execution will be arranged by the National Lead Agency following UNDP NEX procedures. UNDP COs will support national activities and charge them to the NEX/DEX upon its request. In Guinea Bissau, the national executing role is delegated to UNDP. Contrary to NEX, where the National Lead Agency is responsible for effective project delivery and for the management of the national component, in DEX countries, the UNDP will therefore be handling such activities. The NEX/DEX will consist of a National Project Director (assigned by the National Lead Agency as in-kind contribution), a National Project Coordinator and his team of assistants. National, regional and international consultants can be recruited according to UNDP regulations as needed.

The NEX/DEX will establish administrative procedures and operations systems, perform annual audit, and establish project financial management system. It will work in close consultation with the National Lead Agency, and the UNDP Country Office and will facilitate the work of the National Steering Committee (see below).

The Lead Agencies identified for the project are as follows:

- Ministère de l’Environnement et de la Protection de la Nature, Direction de l’Environnement et de la Protection de la Nature (Senegal)

- Ministère du Développement Rural et de l’Environnement, Direction de l’Environnement (Mauritanie)

- Ministerio dos Recursos Naturais, Direcçao Geral  do Ambiente (Guinea Bissau)

- National Environment Agency (Gambia)

- Ministry of Environment and Agriculture, Direction Générale de l’Environnement (Cape Verde)

As the NEX/DEX structure will not be fully operational from the start, UNESCO/IOC and the UNDP Country offices, working in coordination with the Implementing and Executing Agencies, will be intensively involved in the planning of the national project Inception Workshop.  The purpose of this workshop would be to fine-tune the Project’s first year activities and expenditures, based on the decisions of the 1st Regional Project Steering Committee meeting. During this workshop, the schedule of subsequent financial disbursements would be finalised.  Key project staff and counterpart officials would be introduced to each other and familiarized with UNDP rules and procedures.  All project staff would be made aware of their responsibilities and of the Project’s monitoring and evaluation requirements. A meeting of the National Steering Committee (NSC) should be organised right after the inception workshop in order to endorse the Annual Work Plan and execution modalities in accordance with UNDP requirements.

At the national level, each participating country will appoint a National Project Director (NPD), who will be a representative of the National Lead Agency within the project, and a National Project Coordinator (NPC). The NPD will supervise and advise the NPC. The NPC will be recruited by the NEX/DEX in consultation with the Executing Agencies and in line with UNDP rules. The NPC will also work in close collaboration with the national Lead Agency and will provide report on progress. The NPC will ensure appropriate linkages with other relevant Government structures. The NPC will effect the establishment of a National Steering Committee (NSC), which will be headed by the NPD.

Where there is already an appropriate national body (for example National Committee on Climate Change) that functions at the inter-sectoral level, this should be mandated to take on the role of the NSC (in order to avoid creating unnecessary parallel mechanisms).  The function of this Committee will be to contribute towards the achievement of the project objectives, to expedite national activities related to the project outcomes and outputs, and to ensure complementary activities between national strategies and policies and regional project objectives.  Representatives from other relevenat Enabling Activities, such as the NCSA and NAPA process, SNC, should also be consulted or participate in the committee in order to ensure that duplication is avoided and synergies are maximized.

Both NPD and NPC will sit on the NSC and will participate in the RPSC.  This will firmly establish the National Project Coordinator as the key focal point for interactions with the Regional Project Management Unit. The National Coordinator will work in close collaboration with the RPMU, and will provide periodical progress reports.

The NEX/DEX mechanism will be responsible for:

Overall Project Design and Implementation:

1. Develop a national project implementation plan reflective of the goals and objectives of the project

that will include:

- detailed project design, including timelines, deliverables, influencing strategy and budget;

- project management structure that will describe the roles, responsibilities and reporting relationships of all parties engaged in the project, including the National Project Management Team, the NSC, the National Lead Agency; and

- clarify, if needed, the project’s Logical Framework Analysis.

2. Revise and refine the detailed national project implementation plan, including, but not limited to, timelines, delegation of responsibilities and budget, as required and approved by UNDP.

3. Ensure regular communication with and between members of the National Steering Committees of the participating countries.

4. Collect lessons learned as the project progresses.

5. Communicate project outcomes and results to the wider policy and climate change community throughout the project cycle through, but not limited to:

a. Presentations at selected national and international conferences and workshops; and

b. Publication of articles and case studies.

6. Confirm or establish National Steering Committees in the participating countries.

7. Work with the NSC to develop and finalize detailed country level implementation plans and monitoring processes, giving particular attention to the need for a policy up-scaling component. Implementation plans should include:

- detailed project design, including timelines, deliverables, influencing strategy and budget;

- project management structure that will describe the roles, responsibilities and reporting relationships of all parties engaged in the project; and

- a Logical Framework Analysis

8. Supervise, assist with and monitor implementation of the individual pilot projects to be undertaken in the participating countries.

9. Develop guidance and lessons on policy integration from field experience and assuring that pilot-project have well defined activities for up-scaling from field level to policy reform.

10. Maintain continual dialogue with National Steering Committees and national project-level implementation teams.

Technical Expertise

11. Identify, engage and manage technical experts and consultants required to support implementation of the overarching project as well as its individual pilot projects, and coordinate their participation in the National Steering Committee.

Capacity Building

To support capacity building within the regional organization and project implementation team, the NEX/DEX will:

12. Undertake a needs assessment at national level to identify areas for capacity enhancement within the Project Management Team.

13. Develop formal and informal strategies for building the Project Managers’ capacity to deliver field level and multi-country projects.

Monitoring and Reporting

15. Establish a baseline set of indicators, based on the GEF’s requirements for its Strategic Priority for Adaptation, and a monitoring framework for these indicators, against which reporting will be undertaken.

16. Produce the following narrative and financial reports in conformity with UNDP and GEF reporting requirements as appropriate (see PART IV: Monitoring and Evaluation Plan and Budge).

17. The project’s Executing Agencies will report to GEF/UNDP on a regular basis and hold monthly project management meetings

National Steering Committee (NSC)

Attendance: The NSC should consist of senior (policy level) representatives from relevant government agencies/sectors (e.g. Fisheries, Environment, Industry, Finance, Tourism, etc.), NGO representatives as appropriate (environmental and industry), relevant funding agencies and community representation. The NAPA coordinator will be included in the National Steering Committee and will be consulted to ensure coordination with NAPA follow up activities of relevance to this project. Duplication with NAPA activities must be avoided.

Frequency: The NSC should meet on quarterly basis and prior to the Regional Steering Committee (so national concerns can be carried forward to regional level in a timely manner).

Function: To endorse requests for in-country Project activities, monitor the effectiveness of in-country activities; validate work plans for in-country Project activities (prepared by the NC); discuss project progress and implications at  national level.  To identify national concerns regarding project activities and delivery; ensure integrated coordination of the Project actions with those Government Departments concerned with adaptation issues; provide government representatives with an opportunity to update and inform each other and non-government participants; ensure transparency of process and multi-sectoral participation.

Reporting:  The National Coordinator will provide the respective UNDP Country Office and the Regional Coordination Unit with a summary report of its discussions as they relate to project issues and should highlight specific issues that need to be brought to the attention of the Regional Steering Committee.

A schematic interpretation of the Project Management and Coordination Arrangements is included in table 4 of the Executive Summary, p. 66.

##### National Project Director

###### Duties and Responsibilities

The National Project Director (NPD), appointed by the government , is a National Lead Agency representative, responsible for supporting implementation of the project. The NPD serves as the project focal point on the part of UNESCO and as such ensures effective communication between the government and other relevant national stakeholders/actors and monitors the progress towards expected outputs and strategic results under the project. Specifically, the NPD’s major responsibilities, in close collaboration with UNDP CO and the RPMU are:

(a)    Undertake project advocacy at the policy level (high officials of the parliament, cabinet, line ministries, government agencies and other public sector institutions, civil society, private sector and the donor community) to ensure national commitment and contribution to the project objectives;

(b)    Undertake policy level negotiations and other activities to facilitate effective and efficient project implementation and maximize its impact;

(c)    Provide policy guidance to the National Project Bureau congruent with national policies, including for the selection of local consultancy, training and other specialist services;

(d)    In consultation with the Ministry of Finance and Economy (MOFE) and the Designated institution concerned, ensures that requisite financial allocations are contained in the national budget, in accordance with the in-kind, cash or cost-sharing budgets, and the established schedules of payment;

(e)    Ensures that the project document revisions requiring Government’s approval are processed through the MOFE (as a Government’s Coordinating Authority), in accordance with established procedures;

(f)     Participate in the finalization and approve the Project Annual and Quarterly Work Plans and budget, in close discussion with the UNDP, to maximize the leverage of the project resources in order to achieve the desired overall state of development and immediate objectives set out in the project document; s/he may also approve individual payments on a day-to-day basis.

(g)    Supervise and approve the project budget revision and NEX delivery report;

(h)    Review jointly with the PMU success indicators and progress benchmarks against expected project outputs so that progress can be assessed, and review and clear Annual Project Progress and Terminal Reports;

(i)      Conduct regular monitoring sessions with UNDP and the PMU, including Project Appraisal Committee (PAC) Meeting, Annual and Terminal Tripartite Review Meetings to measure progress made or achieved towards the project objectives, and comment on Project Review and Evaluation Reports;

(j)      Report regularly to the Project Steering Committee on the project progress, in conjunction with the PMU staff;

(k)    Assess on regular basis staff work performance in the PMU, including that of National Project Manager, Administrative & Finance Assistant and other staff;

(l)      Establishes close linkages with other UNDP and UN supported as well as other donor or nationally funded projects/programmes in the same sector

Persons to be recruited:

a. Regional Project Manager (RPM)

IOC/UNESCO, in consultation with UNDP will competitively recruit a Regional Project Manager (RPM) consistent with standard UNDP procedures.  The RPM will facilitate the successful execution of project activities as described in Outcomes 1-3 (see log-frame).  He will be in charge of the Regional Coordination Unit.

The RPM will effect the establishment of a Regional Project Steering Committee (RPSC).  The RPM will also work in close collaboration with the National Project Coordinators and the National Lead Agencies and will provide report on progress. The RPM will ensure appropriate linkages with other relevant regional structures.

The RPM will head the RPSC. The RPM will work in close collaboration with the National Project Bureau’s, and will provide periodical progress reports. The RPM will be responsible for supervision of the NPC’s, and will have final responsibility for achieving the outputs and, hence, objectives of the project, and ensuring the co-operation and support from the implementing agent.

The RPM will be responsible for managing the implementation of the project on a regional scale, which includes personnel, subcontracts, training, equipment, administrative support and financial reporting keeping the Implementing Agency aware of all relevant factors which could impact on project implementation. The specific responsibilities of the RPM will be to:

1.       Set up and manage the project office, including staff facilities and services, in accordance with the project work plan;

2.       Prepare and update regional project workplans, and submit these to the UNDP-GEF and UNDP-CO for clearance and ensure their implementation consistent with the provisions of the project document.

3.       Ensure that all agreements with designated project implementing agencies are prepared, negotiated and signed.

4.       With respect to external project implementing agencies:

a) ensure that they mobilize and deliver the inputs in accordance with their implementation agreement and contract, and

b) provide overall supervision and/or coordination of their work to ensure the production of the corresponding project outputs.

5.       Act as a principal representative of the project during review meetings, evaluations and in discussions and, hence, be responsible for preparation of review and evaluation reports such as the Project Portfolio Report for the consideration of the UNDP-GEF.

6.       Ensure the timely mobilization and utilization of project personnel, subcontracts, training and equipment inputs:

a) identify potential candidates, national and international, for posts under the project

b) prepare the ToR, in consultation with the implementing agent and subcontractors;

c) prepare training programmes (in consultation with the implementing agents) designed for staff, with particular emphasis on developing an overall training plan.

d) draw up specifications for the equipment required under the project; procure such equipment according to hosting Government, EA and UNDP rules and procedures governing such procurement.

7.       Assume direct responsibility for managing the project budget on behalf of the IA, ensuring that:

a) project funds are made available when needed, and are disbursed properly;

b) accounting records and supporting documents are kept;

c) required financial reports are prepared;

d) financial operations are transparent and financial procedures/regulations for REX projects are applied; and

e) the project is ready to stand up to audit at any time.

8.       Exercise overall technical and administrative oversight of the project, including supervision of national and international personnel assigned to the project.

9.       Report regularly to UNDP-GEF and UNDP-CO up-to-date on project progress and problems, if any.

10.   Ensure timely preparation and submission of required reports, including technical, financial, and study tour/fellowship reports;

11.   Perform others coordinating tasks as appropriate for the successful implementation of the project in accordance with the project document.

Responsibilities on project completion and follow-up

In order to ensure the efficient termination of project activities, the RPM will:

1.       Prepare a draft Terminal Report for consideration at the Terminal Tripartite Review meeting (RPSC Meeting), and submits a copy of this report to the designated Implementing Agency for comments at least 12 weeks before the completion of the project;

2.       Make a final check of all equipment purchased under the project through a physical inventory, indicating the condition of each equipment item and its location; discusses and agrees with the UNDP and the implementing agent(s) the mode of disposition of such equipment and follow up on the exchange of letters among the UNDP, Government and implementing agent(s) on the agreed manner of disposition of project equipment; take action to implement the agreed disposition of equipment in consultation with the project parties.

3.       Ensure all terminal arrangements relating to project personnel are completed at the final closure of the project.

Accountability

The RPM will work under the general guidance of and report to the Regional Technical Agency. The RPM is accountable to UNDP for the manner in which he/she discharges the assigned functions.

The RPM shall discharge his/her duties in line with the rules and procedures set forth in the UNDP User Guide on Programming for Results and other project management guidelines including, where applicable, the provisions of the agreements concluded with cost-sharing donors. The RPM acts as the Certifying Officer. As such, he/she is responsible for the actions taken in the course of his/her official duties. The RPM may be held personally responsible and financially liable for the consequences of actions taken in breach of the prevailing financial rules and regulations.

Skills and Expertise

- Knowledge and Experience with Adaptation to Climate Change Projects

- Management Experience for: Budget Management, Delivery of Field Projects, Ability to Meet Deadlines

- Regional Network and Multi-Stakeholder processes;

- Strong Communication and Interpersonal-Skills;

- Institutional Capacity to Manage the project: Time, Guidance, Budget Management System, Infrastructure, In-kind contribution

General qualifications

Education:         	Post-graduate level (preferable academic background)

Experience:       		At least 10 years work experience in the relevant area;

Demonstrated management experience and organizational capacity;

Ample previous experience/ familiarity with UNDP/UNESCO procedures;

Skills:                	Good analytical skill

Good interpersonal and communication skills

Good computer skill

Language:       	Fluent in English and French; knowledge of Spanish and Portuguese will be an asset.

b. National Project Coordinator

At the national level, each participating country will recruit a National Coordinator for the Project in consultation with the UNDP Country Office and the RPMU and in line with UNDP rules.  The Project National Coordinator (NPC) will effect the establishment of a National Steering Committee (NSC).  The NPC will also work in close collaboration with the National Lead Agency and will provide report on

progress. The NPC will ensure appropriate linkages with other relevant Government structures.

The NPC will sit on the NSC and will participate in the Regional Project Steering Committee.  This will firmly establish the NPC as the key focal point for interactions with the Project Coordination Unit. The NPC will work in close collaboration with the RPMU, and will provide periodical progress reports.  The NPC, under supervision of the RPM, will be responsible for achieving the outputs and, hence, objectives of the project, and ensuring the co-operation and support from the implementing agent.

The NPC will be responsible for managing the implementation of the project, which includes personnel, subcontracts, training, equipment, administrative support and financial reporting keeping the RPM aware of all relevant factors which could impact on project implementation. The specific responsibilities of the NPC will be to:

1.       Set up and manage the project office, including staff facilities and services, in accordance with the project work plan;

2.       Prepare and update project workplans, and submit these to the RPM and UNDP-GEF and UNDP-CO for clearance and ensure their implementation consistent with the provisions of the project document.

3.       Ensure that all agreement with designated project implementing agencies are prepared, negotiated and signed.

4.       With respect to external project implementing agencies:

a) ensure that they mobilize and deliver the inputs in accordance with their implementation agreement and contract, and

b) provide overall supervision and/or coordination of their work to ensure the production of the corresponding project outputs.

5.       Act as a principal representative of the project during review meetings, evaluations and in discussions and, hence, be responsible for preparation of review and evaluation reports such as the Annual Project Report (APR) for the consideration of the RPM.

6.       Ensure the timely mobilization and utilization of project personnel, subcontracts, training and equipment inputs:

a) identify potential candidates, national and international, for posts under the project

b) prepare the ToR, in consultation with the implementing agent and subcontractors;

c) prepare training programmes (in consultation with the implementing agents) designed for staff, with particular emphasis on developing an overall training plan.

d) draw up specifications for the equipment required under the project; procure such equipment according to Government and UNDP rules and procedures governing such procurement.

7.       Assume direct responsibility for managing the project budget on behalf of the RPM, ensuring that:

a) project funds are made available when needed, and are disbursed properly;

b) accounting records and supporting documents are kept;

c) required financial reports are prepared;

d) financial operations are transparent and financial procedures/regulations for NEX projects are applied; and

e) the project is ready to stand up to audit at any time.

8.       Exercise overall technical and administrative oversight of the project, including supervision of national and international personnel assigned to the project.

9.       Report regularly to and keeps the RPM and UNDP-GEF and UNDP-CO up-to-date on project progress and problems, if any.

10.     Ensure timely preparation and submission of required reports, including technical, financial, and study tour/fellowship reports;

11.   Perform others coordinating tasks as appropriate for the successful implementation of the project in accordance with the project document.

Responsibilities on project completion and follow-up

In order to ensure the efficient termination of project activities, the NPC will:

1.       Prepare a draft Terminal Report for consideration at the Terminal Tripartite Review meeting (NPSC Meeting), and submits a copy of this report to the UNDP Resident Representative and designated Implementing Agency for comments at least 12 weeks before the completion of the project;

2.       Make a final check of all equipment purchased under the project through a physical inventory, indicating the condition of each equipment item and its location; discusses and agrees with the UNDP and the implementing agent(s) the mode of disposition of such equipment and follow up on the exchange of letters among the UNDP, Government and implementing agent(s) on the agreed manner of disposition of project equipment; take action to implement the agreed disposition of equipment in consultation with the project parties.

3.       Ensure all terminal arrangements relating to project personnel are completed at the final closure of the project.

Accountability

The NPC will work under the general guidance of and report to the National Project Director. The NPC is accountable to UNDP for the manner in which he/she discharges the assigned functions.

The NPC shall discharge his/her duties in line with the rules and procedures set forth in the UNDP User Guide on Programming for Results and other project management guidelines including, where applicable, the provisions of the agreements concluded with cost-sharing donors. The NPC acts as the Certifying Officer. As such, he/she is responsible for the actions taken in the course of his/her official duties. The NPC may be held personally responsible and financially liable for the consequences of actions taken in breach of the prevailing financial rules and regulations.

Skills and Expertise

- Knowledge and Experience with Adaptation to Climate Change Projects

- Management Experience for: Budget Management, Delivery of Field Projects, Ability to Meet Deadlines

- Regional Network and Multi-Stakeholder processes;

- Strong Communication and Interpersonal-Skills;

- Institutional Capacity to Manage the project: Time, Guidance, Budget Management System, Infrastructure, In-kind contribution

General qualifications

Education:         	Post-graduate level (preferable academic background)

Experience:       		At least 5 years work experience in the relevant area;

Demonstrated management experience and organizational capacity;

Previous experience/ familiarity with UNDP (or other donors) an asset.

Skills:                	Good analytical skill

Good interpersonal and communication skills

Good computer skill

Language:       	Fluent in English and the national language of the country (French, Portuguese, Spanish)

##### c. Regional/ National Administrative and Finance Assistant

Organizational setting

The Administrative and Finance Assistant will work under the direct supervision of the National Project Manager and provide assistance to project implementation in the mobilization of inputs, the organization of training activities and financial management and reporting.

Job content

- The Administrative and Finance Assistant will be responsible of the following duties:

- Prepare all payment requests, financial record-keeping and preparation of financial reports required in line with NEX financial rules and procedures

- Assistance to the recruitment and procurement processes, checking the conformity with UNDP and the Government rules and procedures

- Assistance to the organization of in-country training activities, ensuring logistical arrangements

- Preparation of internal and external travel arrangements for project personnel

- Maintenance of equipment ledgers and other data base for the project

- Routine translation/interpretation during projects meetings and drafting of correspondence as required

- Act as a Petty Cash custodian

- Maintain project filing

- Other duties which may be required

General Qualifications

Education:                    	University Degree, some training in business and/or administration desirable (finance or accounting)

Experience:                   		At least five years administrative experience;

Skills:                            		Good organizational skills;

Good computer skills, including spread-sheets and database

Languages:                  	Fluent in English and the national language of the country (French, Portuguese, Spanish)

##### D. International Consultant for Technical Input (ICT)

IOC/UNESCO, in consultation with UNDP, will competitively recruit International Consultants consistent with standard UNDP procedures.  The ICTs will provide technical guidance to participating countries for the execution of project activities as described in Outcomes 1-4 (see log-frame).

The incumbent will provide technical backstopping to the Project Team based in Dakar. The incumbent will work from his/her usual place of work but will undertake several missions in the 5 participating countries in the course of the project implementation.

## Duties

Under the supervision of IOC/UNESCO and in close cooperation with the Regional Project Manager, the International Consultants will provide technical backstopping and in particular:

1. Prepare technical documents that will support the implementation of Outcomes listed in the UNDP Project Document

2. Participate and provide technical advice in Project Steering Committee and technical group meetings as required;

3. Provide technical guidance based on previous experiences in the development of demonstration measures as identified in the project document and as they relate to the identified project sites;

4. Prepare methodologies and tools, based on international best practices, for use in the implementation of project components

5 .Guide the monitoring and evaluation activities as they relate to the project and the approved Vulnerability Reduction Approach for measuring improvements in adaptive capacity

6. Guide the preparation of knowledge products and contribute towards the effective dissemination of KM products at regional and national level;

5. Provide technical input at capacity development fora as outlined in the project document;

6.  Review and revise inputs provided by national institutions;

7. Provide technical backstopping to the Project as required and as requested by the Regional Project Manager

8. Assist the facilitation of lessons learned into the UNDP-GEF Adaptation Learning Mechanism

9. Facilitate cross-country knowledge transfer

Develop papers and briefs highlighting successful case studies and lessons learned from the project

Accountability

The ICTs will work under the general guidance of and report to the Regional Technical Agency. The ICTs are accountable to UNDP and IOC/UNESCO for the manner in which he/she discharges the assigned functions.

Skills and Expertise

- Knowledge and Technical Experience with Adaptation to Climate Change and Coastal Management Projects,

- Ability to review, prepare and present methodological material

- Regional Network and Multi-Stakeholder processes;

- Strong Communication and Interpersonal-Skills;

General qualifications

Education:         	Post-graduate level (preferable academic background)

Experience:       		At least 10 years work experience in the relevant area;

Demonstrated management experience and organizational capacity;

Ample previous experience/ familiarity with UNDP/UNESCO/GEF projects;

Skills:                	Good analytical skill

Good interpersonal and communication skills

Good computer skill

Language:       	Fluent in English and French; knowledge of Portuguese will be an asset.

##### D. NATIONAL Consultant for Technical InputS (NCT)

Location:			In the respective project country

Responsible unit:		UNDP CO / NEX Agency

Supervisor(s):	NEX Agency/ Project Manager

Overall Objective:

The consultant will, under the supervision of the Project Manager, develop and/or strengthen the technical aspects of the country specific project activities. Detailed Terms of Reference will be developed by the Project Manager and selection of the consultant should be in line with UNDP established procedures.

- Develop technical input and provide guidance in lieu of for Outcome 1, 2, 3 and 4

Implementation and Coordination Arrangements

  - To be determined pending project implementation.

Qualifications and Experience

  - Technical knowledge of adaptation to climate change

  - Monitoring and Evaluation Expertise based on UNDP Practices for GEF projects

  - Knowledge of national policy relevant to adaptation

  - Experience with project and programme design

  - Capacity to engage with multiple levels of stakeholders, including communities, civil society, government, and the private sector

  - Fluency in English (knowledge of French/Spanish is an advantage)

# Annex A9: MOU between EA’s
To be completed prior to disbursement of funds.

AGREEMENT BETWEEN THE UNITED NATIONS ( or other UN Agency)AND THE UNITED NATIONS DEVELOPMENT PROGRAMME (UNDP)

A.	PROJECT SUMMARY

Project Title:	[Title of project]

Time frame:	The Project will be implemented from [Time frame]

Location:	in [Location]

Contribution amount:		US$ [Amount](inclusive of cost recovery)

Donor:			[Name of donor agency /project]

Recipient Agency :           United Nations development programme (UNDP)

Executing Agency:	  United Nations Development Programme (UNDP)/ any other                                                     Executing Agency

- PROJECT DESCRIPTION AND IMPLEMENTATION

The contribution governed by this Agreement shall be utilized exclusively for [Project details](see Annex 1).  It will be used by the recipients to contribute to [Specify project activity]. This contribution will be administered in accordance with the regulations and rules applicable to UNDP.

C.	CONTRIBUTIONS AND SCHEDULE OF PAYMENTS

This contribution will be allocated in one installment of US$ [Amount] immediately after this Agreement has been signed by both parties [or state  payment schedule].  The total contribution is inclusive of UNDP’s 5-7% cost recovery for general management support.

## D	UNDP REPORTING

Substantive Progress Reporting

Substantive reports shall detail achievements, constraints and impacts with regards to the utilization of this contribution. The substantive report for the period  [ For Agreements of one year or less such reports are given within six months after the date of completion or termination of the Agreement and in case of Agreements for more than one year, such reports are given every year]will be submitted to the[Donor]no later than on[date]  This report will be accompanied by the preliminary financial report signed by the Resident Representative of UNDP-[Country office]

The final substantive report detailing achievements, constraints and impact with regard to the utilization of the contribution from the country office and the final financial report, certified by the Comptroller of UNDP, will be provided no later than 30 June of the year following the financial closing of the project. (see paragraph below).

Financial Reporting

Financial reports shall reflect the amount received in relation to expenditure from the contribution. The first preliminary financial report signed by the Resident Representative of UNDP-[Country office] for the period to will be submitted no later than [ reporting cycle will be the same as in the substantive reports in paragraph 3. For Agreements of one year or less, within six months after the completion /termination of the Agreement and for Agreements for more than one year, every year]. This report will be accompanied by the first substantive progress report (see paragraph 3). The financial report certified by the Comptroller of UNDP will be submitted no later than 30 June of the year following the financial closing of the project.

Financial reports signed by the Resident Representative will provide information according to the following categories:

- Amount received

- Staff and other personnel costs

- Travel

- Contractual services

- Procurement

- Fellowships, Grants and other

- Sub-total

- Cost recovery

- TOTAL EXPENDITURES

At the termination of the project, any unexpended or uncommitted part of the contribution will be returned to the UN, unless otherwise agreed in writing by the parties.

E.	PAYMENT INSTRUCTIONS

Upon receipt of this Agreement, the funds shall be paid into the following account:

[ Bank details]

F.	CERTIFICATION AND AGREEMENT BY UNDP

UNDP certifies that the statement herein, under the heading “Project description and implementation”, is an accurate description of the Project and that agreement and acceptance of the terms and conditions of this Agreement Document is indicated by the duly authorized signature below.

Signed:

Date:	_________________

G.	CERTIFICATION BY THE UN

It is hereby certified that the activities described in this document are consistent with the [objectives of the UN agency project] and that agreement and acceptance of this Agreement Document is indicated by the duly authorized signature below.

Signed:

Date:	________________

# Annex A10: Template on lessons learned for ALM.

Completed by: 							Date:

Project Data

Name of the project:

PIMS:

Project funding source: SPA/SCCF/LDCF

Project priority:

Agricultural practices or policies

Water availability or management

Health prevention or planning

Disaster risk management

Coastal zone management or planning

Natural resource management

Global environmental benefits (select) – BD, LD, IW, CC

Climate change risk:

Disaster-related (flood, drought, storm)

Resource constraint (shifting viability of agriculture, water availability, etc)

Other:

Timescale of risk:

Short term (seasonal and inter-annual)

Long term (decadal and multi-decadal)

Both

Timescale of response benefits:

Short term (seasonal and inter-annual)

Long term (decadal and multi-decadal)

Both

Target exposure unit:

Ecosystem/single area

Multiple sector/geographic areas

Project scope:

Local/national/sub-regional/regional/global

Please share lessons learned through the project in your responses to the following questions. Please keep your responses to 100 words.

Lessons on Process

Stakeholder Involvement

1. Describe how the project has succeeded or struggled to engage stakeholders (methods for engagement and participation, mechanisms for transparency and information sharing, etc.)

Policy dialogue

2. Describe how the project succeeded or struggled to undertake effective policy dialogue (achieving national ownership, relevance of policy dialogue: departmental, ministerial, local authority, etc.)

Institutional and individual capacity building

3. Describe how the project succeeded or struggled to build capacity for adaptation.

Tools and approaches for mainstreaming

4. Describe successful or unsuccessful entry points and methods for mainstreaming climate change and adaptation.

Lessons on Outcomes

Design

5. Describe successes and/or failures to deliver the project’s combination of outcomes: policy level integration; hard measures to reduce risk; vulnerability reduction; improved adaptive capacity; capacity building; and/or risk transfer.

Impact

6. Describe successes and barriers to success in achieving impact targets.

Sustainability

7. Describe initial evidence of successes or failures of the project in achieving sustainability of adaptation benefits and relevant factors.

Innovation

8. Describe any successes or failures of the project in introducing innovations to support adaptation in the following categories: project design, implementation of adaptation measures, building adaptive capacity, policymaking to facilitate adaptation, adaptation mainstreaming, risk transfer/financial measures, others.

Replication

9. How does the project capitalize on the ALM? What other mechanisms for replication are incorporated into the project?

Lessons on Operations

Execution modality

10. Describe how the project’s execution modality has been effective or ineffective.

Project implementation infrastructure

11. Describe how the project implementation structure been advantageous or disadvantageous.

Overall

12. Key recommendations for future adaptation projects:

### Annex A11:  GEF Secretariat and other Agencies’ comments and IA/ExA response

| GEFSEC Comment | UNDP Response | Reference to Proposal |
| --- | --- | --- |
| French: - Coastal erosion and sedimentation have been a reality for centuries in those countries, and are not a consequence of climate change due to anthropic carbon emission. - Only soft intervention (maintaining mangrove protection and dune vegetation for instance…) can be considered with that level of funding. There should not be any important public works which are beyond GEF mandate | - Included sentence in PRODOC: “Even though coastal erosion and sedimentation have been a reality for centuries in these countries, and are not solely a consequence of climate change due to anthropic carbon emission, both processes are strongly influenced by changes in climatic conditions.” - Included sentence in PRODOC : ‘’ Only soft interventions will be subject to GEF funding; if important public works are necessary, they will have to be financed through non-GEF funding; to this effect, an SCCF proposal is currently being elaborated. | See Part 1 A, paragraph 1. see Part 3 A, paragraph 71 of Exec. Summ. See also Part II, par. 2.3. |
| Swiss: - Excellent practical adaptation objectives of the programme could be at risk because of so far regrettably onerous, inefficient, and ineffective requirements for monitoring, evaluation, and reporting. - The complexity also may have an impact on the transaction cost generated at country level. This in particular as the modalities of co-financing are not clear yet. Co-financing does in practice lead to an increase of complexity at the implementation stage. - This complexity is partly the consequence of guiding principles issued by the GEF on adaptation and incrementality (GEF/C.23/Inf8/rev1) with regard to global benefits. The programme should fit into the priorities laid out by the host countries in their initial national communication. The priorities of host governments and communities typically focus on enhancing coping capacity in terms of local development. This dilemma could possibly be overcome by short listing at the national level sectoral interventions which generate global environmental benefits in terms of e.g. biodiversity, land management, desertification based on the stressed resource base prevailing on eligible geographical areas. This could possibly reduce the M&E requirements to be applied to local level organizations and hence lead to a reduction of transaction cost. The global benefits are materialized in practice in a sustainable manner only if the programme is successfully implemented in development terms, and hence the local community does adapt the improvements in resource management during the operation and maintenance phase. - The programme implemented in NAPA countries may generate lessons on the manner in which local communities can successfully be integrated in an adaptation policy framework. Lessons learned with regard to the complementarities of the NAPA process and the CBA through the small grant programme would be highly welcome. | - M&E and Reporting are standard operations within the GEF and UNDP-GEF framework. To this effect, UNDP has developed a standard M&E/Reporting text to be adapted to the project situation and included in the PRODOC. This text has been used in the PRODOC. The M&E/Reporting activities are a necessary aspect of project management and allow the IA/EA to monitor progress and step in when necessary. Standard forms have been developed for reporting, minimizing projectteams’ timeinput, while optimizing information output. Nevertheless, an effort will be made to simplify the M&E/Reporting framework, with minimization of transaction costs in view. - See above. - An annex has been prepared stating the main gaps and capacity building priorities resulting from the National Communications of the participating countries: the table shows national level sectoral interventions which generate GEB. - A strong complementarity between the NAPA processes and the CBA programme will be stimulated in the ACCC project. NAPA project teams will be involved in the ACCC project as key resource persons; on a regional level, the RPC will liaise with the CBA regional coordinator to exchange lessons learned and good practices. Duplication with NAPA activities will be avoided but synergies maximized. | See paragraph 81 of the Exec. Summ. See also PART IV: Monitoring and Evaluation Plan and Budget, page 95 of PRODOC ; See above. See Annex X, page x of PRODOC; See paragraph 29 of the Exec summ. See also Part III, paragraph 183 on page 56 of PRODOC. |

Report of the LPAC Meeting

ACCC Project

Adaptation to Climate Change: Responding to Shoreline Change and its human dimensions in West Africa, through integrated coastal area management

Full Size Phase

Tuesday 15 May 2007, UNESCO-BREDA, Dakar, Senegal

1. OPENING

M. Abdoulaye Ndiaye, UNDP/GEF Representative (RCU) welcomed the participants on behalf of the implementing team of the ACCC Project. He recalled the various steps that have led to the development of the Project document in its present form. He stressed the importance of the LPAC as being a starting point in the implementation of the full size ACCC project. In this respect, the LPAC recommendations will be attached to the Project document that will be submitted in the coming days to the GEF CEO.

M. David Njiki Njiki, Executive secretary of SINEPAD, also recalled that this Project was developed in the framework of the NEPAD Environmental Action Plan approved by the African Heads of States. SINEPAD considers this initiative as pioneering project, which originated from the African Process.

M. Teeluck Bhuwanee, Representative of the UNESCO BREDA Director, Mme Ben Barka, gave a welcome address highlighting the work accomplished by the project team during the preparation phase of the project (PDF-B). He recalled that the objective of the meeting was to present the Project document to the participating countries as well as partners (present and potential), and in particular to validate the executing and implementing modalities in view of the start of the Project in the coming months.

2. 	ELECTION OF CHAIR AND DESIGNATION OF RAPPORTEURS

Mr. Elimane Ba, Ministry of Environment, Senegal, and representative of the project national focal point, Mme F. Touré, was elected as chair of the meeting. Mme. N. Djigal Sall, UNDP/GEF (RCU) and M. L. Touré, UNDP Senegal,  were appointed as rapporteurs.

3. 	PRESENTATION ON THE STATUS OF THE PROJECT

Following the endorsement of the project by the GEF Council in June 2006, Mr. P. Kurukulasuriya UNDP/GEF, explained the final endorsement process required from the GEF CEO and the following steps, including the issuing by UNDP/GEF of the Delegation of Authority (DOA) letters:

- at the national level for NEX or DEX mechanisms : Once the DOA letters are signed by UNDP-GEF CEO and upon receipt of these letters, the Government, the national executing agency and the UNDP Resident Representative will sign the project document.

- at the regional level, once the DOA has been issued to the Regional Technical Agency, the UNDP Resident Representative of the Lead Country Office (Senegal), the Governments and UNESCO-IOC will need to sign the project document.

Mr. P. Kurukulasuriya highlighted the key role of the UNDP Country offices during the negotiation to be undertaken with the national agencies, for the finalization of the NEX mechanisms.

Finally, he recalled that due to the specificity of the SPA as a GEF funding source, some activities did not qualify for funding during the PDF-B and were therefore removed from the Full Size Project document. These activities have been reformulated in the shape of a second project document which will be shortly submitted to GEF for funding under the Special Climate Change Fund (SCCF).

4. PRESENTATION OF THE PROJECT

Mr. J. Barbière, representative of the technical executing agency UNESCO-IOC, presented the following components, highlighting changes that have occurred in the project document since the original submission in May 2006:

- Background

- Objectives and expected outcomes

- Provisional Budget

- Status of Co-financing

- Execution Modalities at national and regional level

-  Monitoring and Evaluation mechanisms.

He informed the LPAC that 2 new outcomes at the project level have been inserted: Outcome 4 which is a common outcome for all SPA funded projects, and Outcome 5 which relates to the Regional Project Management Unit.

With regards to Outcome 2, which relates to the mainstreaming of adaptation measures in coastal management policies, Mr. Barbière informed the participants that because of the regional dimension of Outputs 2.4, activities and related funds for this output have been moved to Outcome 4 which relates to Learning, Evaluation and Adaptive Management.

5. COUNTRIES COMMENTS ON THE PROJECT DOCUMENT

Following Mr. Barbière’s presentation, the participants provided some general comments.

The LPAC stressed the importance of harmonizing the implementation of the ACCC project with the follow-up activities in the framework of the NAPAs, and to ensure that there are no duplication in the development of national strategies and activities at the national level. In this respect, the NAPA national focal point should be a member of the national project committee.

The representative of the UNDP Country Office for Mauritania confirmed that his office will provide co-financing for the project and that a letter was being prepared to this effect. The recent institutional changes in Mauritania should be noted in the document ( §119).

With regards to document, some degree of harmonization should be sought for the following sections/paras :

- §165 and 53 with regards to the financial implications ;

-§53 with regards to the incremental costs section ;

- §12, should insert a reference to the importance of the Senegambia river coastal ecosystem.

- Harmonization in the 2 languages with regards to the terminology used for outcomes, outputs, and activities.

- Annex A8, NPD, the NPD is the focal point of the project for UNESCO

- Add more recent references for §14, 19, 20, 35

- Total amount for M & E table (§160) should be recalculated.

6.	LPAC RECOMMENDATIONS

1. The LPAC recommends the insertion in Part V. Legal Context, of a mention of the grant agreements which will be signed between the UNDP country offices and the national agencies in the framework of the NEX and DEX mechanisms.

2. The LPAC recommends the renaming of  the National Consultative Committee (NCC) into a National Steering Committee in order to better reflect its supervisory role at the national level.

3. With regards to the national coordinator, it is proposed to clarify the recruitment process which in the case of NEX will be undertaken by the national agencies, in consultation with the RPMU and the UNDP Country Office. Position adverts will be widely disseminated through local media, and the recruitment will be implemented through an evaluation panel comprising of the national agencies, UNDP, and the RPMU. In the case of DEX, UNDP will be in charge of the recruitment process. An evaluation panel comprising of the national agencies, UNDP, and the RPMU, will also be established in this case.

4. With regards to the validation process of the Workplans, the involvement of the Ministries of Economy and Finances or other governmental audit bodies (depending on the country) is crucial as these institutions will have to authorize expenses of the UNDP office at the national level. Representatives of these institutions should sit at the National Steering Committee of the Project.

5. The LPAC stressed the need to organize National Steering Committee meeting on a quarterly basis in order to follow up project progress more closely.

6. It was recalled that the contribution of the National Project Director (NPD) is considered as an in-kind contribution from the governments to the Project. In addition, GEF funds cannot be used for government staff salaries nor for UNDP staff salaries.

7. The role of the National Coordinator and of the National Project Director in the monitoring and evaluation of national activities should be better clarified and each country will have to apply existing procedures with regards to the administrative linkage between the NPC and NPD. As a model for the Project it is proposed that the NPC reports directly to the Project Director who in turn will report directly to the National Steering Committee. However, it should be noted that the Coordinator will be recruited on a contractual basis by the Project and that he/she will have to report on the utilization of funds to the UNDP office. The NPC terms of reference should reflect the three lines of reporting towards the NPD, the UNDP offices and the RPMU.

8. With regards to cash disbursement modalities, in the case of both NEX and DEX, these modalities will be clarified during the negotiations to be undertaken by UNDP and the governments for the finalization of the country agreements.

9. With regards to the financial allocation at the national level, it was stressed that these allocations will be based on the results that contribute to the achievements of the overall project objective. Whilst at this stage, the Project budget is not detailed, its breakdown will be discussed later during the inception workshop of the Project, it will then be validated by the National Steering Committee’s and the Regional Project Steering Committee. To this effect, national teams will receive guidelines from the RPMU on how to plan national activities and national allocations. It is recommended that an equity principal is applied in the allocation of the Project resources.

The LPAC approves the above recommendations 1to 9 by acclamation.

The LPAC endorses the Project document under the condition that the comments and recommendations from the participants have been taken into account.

Annex I – Agenda

Annex II – List of participants

## ANNEXE I

## Agenda

| 9h30 –10h00 | 1. Ouverture/Opening 2. Élection du Président et Rapporteurs 2. Election of Chair and Rapporteurs |
| --- | --- |
| 10h00-10h30 | Pause Café – Coffee Break |
| 10h30-12h45 | 3. Présentation sur l’état d’avancement du processus 3. Presentation on the status of the project |
|  | 4. Présentation du document de projet en mettant en exergue les principaux changements depuis son adoption au Conseil du FEM 4. Presentation of the project document highlighting the main changes since adoption by the GEF Council |
| 12h45-14h00 | Pause déjeuner / Lunch Break |
| 14h00 –15h30 | 5. Discussions en Plénière : Commentaires des pays sur le document de projet 5. Plenary discussions : Countries comments on the Project document |
| 15h30-16h00 | Pause café / Coffee Break |
| 16h00-18h00 | 6. Formulation des recommandations clés sorties des discussions 6. Formulation of Key recommendations |
|  | 7. Discussions en plénière et validation des recommandations clés 7. Plenary Discussions and adoption of Key recommendations |
|  | 8. Information sur les étapes suivantes 8. Information on next steps |
|  | 9. Clôture 9. Closure |

ANNEXE II

LIST of PARTICIPANTS

Gambia

Mr. SARR Momodou B

Executive Director

National Environment Agency

5 Fitzgerald Street

PMB 48

Banjul

Phone: (220) 422 3860

Fax: 	(220) 422 9701

E-mail: msarr@gamtel.gm

Mr. JAGNE Mamour A.

Programme Analyst

UNDP Country Office The Gambia

5 Kofi Annan Street

Cape Point, West Africa

Phone: (220) 449-4760, 449-4761-9

Fax: (220) 449-4758

E-mail: mamour.a.jagne@undp.org

Guinea-Bissau

Mr.  LOPES  Joao Raimundo

Senior Energy Officer/GHG

Inventories Expert

General Direction of Energy/National Climate Change Program

Ex-QG (Santa Luzia)

P.O. Box 311

Bissao

Phone: (245)22-2951/ 256-239

Fax: 	(245)20-5881/ 256-238

E-mail: jraylopes@yahoo.com

Mauritania

M. LAFDAL Mohamed Yahya O.

Directeur des Politiques Environnementales

Secrétariat d'Etat auprès du Premier Ministre chargé de l'Environnement

B.P : 170

Nouakchott

Phone:	+222 5243143

Fax: 	+ 222 6303128

E-mail:	lafdal@environnement.gov.mr

M.  N’DIAYE Maouloud

Leader Thématique Environnement PNUD

PNUD-Mauritanie

203, rue 42-133

Ilot K

Nouakchott

Phone: 	+222 525 2409

Fax: 	+222 525 2616

E-mail: maouloud.ndiaye@undp.org

Senegal

Mr. Elimane BA

Chef de Division pollution et nuisances

Ministère de l’Environnement et de la Protection de la Nature

Dakar – Sénégal

Tél. (221) 538 90 14 ou 538 90 19

E-mail : elimanl2003@yahoo.fr

Mr. Laba Touré
PNUD-SENEGAL

Immeuble Fayçal, 19 Rue Parchappe, 
Dakar - Sénégal
B.P. 154 - Tél.(221)-839-90-50

Fax: (221)-823-55-00 
Email :  laba.touré@undp.org

Mr. Pacal VARDON

Conseiller franco-allemand du Ministre de l’Environnement et de la Protection de la Nature du Sénégal

SCAC Dakar - Sénégal

BP. 2014

Tél. (221) 587 97 87

E-mail : p.vardon@orange.sn

SINEPAD

M.  NJIKI NJIKI DAVID

Secrétaire Exécutif

Secrétariat Intérimaire du Volet Environnement du NEPAD

Boulevard Djily Mbaye,

Immeuble FAHD, 3ème Etage

P O Box: 813

Dakar

Phone: +(221) 842 73 11

Fax: 	+(221) 842 73 11

E-mail: njikinjiki@yahoo.com

UNDP/GEF

M. NDIAYE Abdoulaye
UNDP/GEF Regional Coordinator, Biodiversity 
United Nations Development Programme
SURF West &Central Africa Office
P.O. Box 154, Dakar, Senegal
Tel: (221) 869 06 61 
E-mail: abdoulaye.ndiaye@undp.org

Ms. DJIGAL SALL Ndeye

Programme Associate-CC and CDAC clusters 
United Nations Development Programme
SURF West &Central Africa Office
P.O. Box 154, Dakar, Senegal
Tel. (221) 869 06 78

Fax. (221) 869 06 29
Email: ndeye.djigal.sall@undp.org

KURUKULASURIYA Pradeep

Technical Advisor- Climate Change Adaptation

& Task Manager- West Africa Shoreline Project

UNDP/GEF

United Nations Development Programme

Global Environment Facility Unit (UNDP-GEF)

304 East 45th Street

10017

New York, NY

E-mail: pradeep.kurukulasuriya@undp.org

UNESCO-IOC

Mr. BARBIÈRE Julian

Acting Head, Ocean sciences

Programme Specialist

Intergovernmental Oceanographic Commission (IOC)

UNESCO

1, rue Miollis

75732

Paris Cedex 15

Phone: +33.01.45.68.40.45

Fax: 	+33.01.45.68.58.12

E-mail: j.barbiere@unesco.org

IUCN

Ms. Oumou Koulsoum LY

Chargée de Programme à l’UICN

BP. 3215

Av. Bourguiba X Rye 3 Castors

Dakar – Sénégal

Tél. (221) 869 0285

Fax. (221) 824 92 46

E-mail oumou-koulsoum.ly@iucn.org

CRDI

Nathalie BEAULIEU
Spécialiste-Administratrice de Programme / Program Officer
Adaptation aux Changements Climatiques en Afrique (ACCA) /
Climate Change Adaptation in Africa (CCAA)
Bureau Régional de l'Afrique du Centre et de l'Ouest (BRACO), CRDI /
West and central Africa Regional Office (WARO), IDRC
BP 11007 Peytavin, Dakar, Sénégal
Tel : (221) 864 00 00 ext: 2244 Fax : (221) 825 32 55
E-Mail : nbeaulieu@idrc.org.sn

M. Alioune Badara KAERE

Agent de Recherche au CRDI

Programme Adaptation aux changements climatiques en Afrique

BP. 11007 Dakar – Sénégal

Tél. (221) 864 00 00 ; Fax (221) 825 32 55

E-mail a.kaere@idrc.org.sn

Absent/excusé

Mme Ivone Andrade LOPES, Ministry of Environment, Cape Verde

M. José Levy, PNUD, Cape Vert

M. Valentin Traore, PNUD, Guinee Bissau

# Footnotes

The GEF-funded Medium Size Project (MSP) Sub-Saharan Africa Project “Development and Protection of the Coastal and Marine Environment in Sub-Saharan Africa”, also known as the ‘African Process’

These particular five countries have, through their respective National Communications process and in the formulation of their respective National Adaptation Programs of Action (NAPAs), highlighted that the impact of climate change on their coastal regions is a priority.

Response to council member observation. The response table has been included in Annexe 
A 11 of this PRODOC and in the Executive Summary.

Allersman and Tilsmans 1993 – quoted in Africa Environmental Outlook (2000)

As highlighted by Eric Bird during the STAP review of this proposal.

Based on an in-country assessment including National Communications and consultations with relevant stakeholders (see Annex 1.1 for details)

McLean, R. F., Tsyban, A., Burkett, V., et al. 2001. Coastal Zones and Marine Ecosystems. Chapter 6 in Climate Change 2001: Impacts, Adaptation and Vulnerability. Contribution du Groupe de travail II au Troisième Rapport d'évaluation du GIEC. Cambridge Press.

Senegal, The Gambia, Cote d’Ivoire, Ghana, Benin, Togo, Nigeria, Cameroon, South Africa, Tanzania, Seychelles, Mauritius, Mozambique.

Other vulnerability and adaptation assessments have not yet been published but are present either in the Initial National Communications to the UNFCCC or in the form of reports.

The coastal zone includes at a minimum, ‘all the inter-tidal and supra-tidal areas of the water’s edge; specifically all the coastal floodplains, mangroves, marshes and tide-flats as well as beaches and dunes and fringing coral reefs’. (Clark, 1996). Sub-Saharan Africa has a total coastal length of 63,124 km, consisting mainly of a narrow low-lying coastal belt, which includes the coastal shelf of 32 mainland countries and a number of island states. The coastline of Senegal is 531 km long, the Gambia 80 km, Guinea Bissau 350 km and Cape Verde Islands 965 km.  Total for the five states 2,680 km (The World Fact book CIA).)

According to the Intergovernmental Panel on Climate Change (IPCC), the average global sea level has risen by 1–2 mm per year during the last century. The most likely cause of this is expansion of seawater and widespread loss of land ice caused by higher mean global temperatures. The IPCC also predicts that, by 2100, the global sea level could rise by up to one metre (IPCC 2001a). The consequent flooding and changes in salinity, wave conditions and ocean circulation will put natural habitats and human settlements at risk of flooding and accelerated erosion. The extent and severity of the impacts of storms will also increase as a result of further climatic changes, and because the buffering capacity of coral reefs and mangrove systems will have been lost. Human settlements and economic activities in the Gulf of Guinea, Senegal, Gambia, Egypt, and along the eastern African coast, including the Western Indian Ocean, are likely to be most severely affected (IPCC 2001b). Some of these countries may be unable to cope with the financial and technical burden of implementation of mitigation measures (Leatherman & Nicholls 1995) – quoted from Africa Environment Outlook (UNEP, 2000)

Africa Environment Outlook (UNEP, 2000/UNEP, 2006)

It is estimated that over half a million people in Mauritania, Guinea-Bissau and Senegal depend directly on fisheries for incomes and food supply.

Population pressures are among the factors that have and will continue to contribute to substantial resource degradation in the coastal zones of Western Africa. For example, the coastal region of Dakar (Senegal) is home to about 4.5 million people (66.6 per cent of Senegal’s population) and 90 per cent of the country’s industries (IPCC 1998).

Smith, Huq, Lenhart, Mata, Nemesova & Toure (1996) - quoted in Africa Environmental Outlook (2000)

Wellens-Mensah (1994) – quoted in Africa Environmental Outlook (2000)

Allersman and Tilsmans (1993) – quoted in Africa Environmental Outlook (2000)

Dennis, Niang-Diop & Nicholls (1995) – quoted in Africa Environmental Outlook (2000)

UNDP-GEF PDF-B Proposal ‘Conservation of biodiversity through integrated participatory community management in Cape Verde’

The Gambia National Report. GEF MSP Sub-Saharan Africa Project, 2001

Senegal National Report. GEF MSP Sub-Saharan Africa Project, 2001

The criteria for the selection of the hotspots are driven primarily by vulnerability to climate change impacts.

The Gambia country report mentions that cross-sectoral linkages are especially weak in fostering a collaborative approach to tackling key climate change issues

On the one hand, available projections are quite generic and do not cover the spatial or temporal scale necessary for planning purposes. The other issue is that, even with perfect information, there is a gap in knowledge of what to do with it in so far as coastal management is concerned.  The intention of this project is to contribute to bridging this gap.

A control site in each country will be used to measure progress made towards improving adaptive capacity and achieving global environmental benefits.

To be undertaken during the planning meeting for the project after Council approval. The selection will be made after CEO approval and a final list will be provided to the GEF.

Several sites are currently vulnerable to loss of biodiversity due to the planting of exotic and invasive species. (e.g. planting of appropriate local species such as Cocus nocifera, tamarisk (salt cedar), Phoenix dactiligraphe, Parkinsonea aculeate and other local species) (to be implemented in Ribiera da Lagoa (Cape Verde); Bald Cape to Cape Point, (The Gambia); Nouakchott (Mauritania); Mboro, Lake Ourouaye, Kayar, Cape Vert Peninsula, Delta Saloum (Senegal)).

ICAM will be developed for countries that do not have any plans. In other cases, eg. Mauritania where plans do exist, the intention is to help implement.

Dates of ratification / entry into force of the UNFCCC - Cape Verde(March 1995/June 1995) / Guinea Bissau (October 1995/January 1996) / Gambia (June 1994 / September 1994) / Mauritania (January 1994 / April 1994) / Senegal (October 1994 / January 1995)

Correspondence from the Chairperson of AMCEN to IOC Executive Secretary (29 December 2003)

The report of the Dakar meeting is available upon request.

At the 2nd meeting of the Steering Committee (PDF-B phase), Guinea Bissau stated that a DEX national implementation mechanism would be preffered on the grounds that national authorities lacked the capacity to carry out the project. In this case, the UNDP Country Office will assume overall management responsibility and accountability for project implementation. The country office will need to define responsibilities for a) planning and supervising project activities and taking decisions; b) technical and operational implementation of activities; c) monitoring progress and d) evaluation and audit. A National Project Manager will be recruited locally according to UNDP procedures.  In addition to these functions, administrative support services are required, as well as other items such as additional office space, supplies and equipment.  To ensure transparency, efficiency and appropriate level of consultation, the UNDP country office will make full use of existing mechanisms for project monitoring and accountability in particular through the establishment of the National Steering Committee.

To the extent possible, these reviews drew on ongoing work in National Communications and National Capacity Self-Assessments.

To the extent possible, these reviews drew on ongoing work in National Communications, the very preliminary NAPA consultations and National Capacity Self-Assessments.

# Text boxes

Funded by the Strategic Priority on Adaptation, this pilot project focuses on implementing measures to strengthen the resilience of vulnerable communities to the impacts of climate change on coastal resources.  This pilot project will be implemented in Mauritania, Senegal, The Gambia, Guinea Bissau, and Cape Verde over a duration of 4 years by a multi-agency Project Team. The experience of UNDP, in close collaboration with UNESCO/IOC, will guide the implementation of this project through a set of nationally and regionally executed activities.

# COUNTRY Y

# National Lead Agency (DEX= UNDP CO)

National Project Director

National

Project Management Team

## National

## Steering

## Committee

Regional

Project Steering Committee

(IA, ExAs, Countries, Obs.)

# COUNTRY X

# National Lead Agency (NEX)

National Project Director

#### National

Project Management Team

## National

## Steering

## Committee

Box 1: The Adaptation Learning Mechanism (ALM)

Learning is an important goal of this GEF pilot phase on adaptation. Each adaptation project should incorporate a significant learning component in its project design, using monitoring and evaluation good practices. Rigorous evaluation will enable the GEF and other agencies to measure progress and the GEF to learn how to strengthen and widen its portfolio. The UNDP-GEF's Adaptation Learning Mechanism (ALM) has been launched to facilitate this learning process.

The Adaptation Learning Mechanism (ALM) will help maximise global learning from GEF’s Strategic Priority on Adaptation (SPA), Least Developed Countries Fund (LDCF), and Special Climate Change Fund (SCCF). It will contribute to incorporating adaptation into planning and provide good practices for adaptation. Developed as a new “knowledge base”, the ALM will provide tools and establish a learning platform. It will be designed as a collaborative, open-source knowledge network with Southern institutions in the lead. Partners include the Stockholm Environment Institute (SEI) and the Regional and International Networking Group (RING).

The ALM is designed to contribute to the integration of adaptation to climate change including variability within development planning of non-Annex I countries, and within the GEF’s portfolio as a whole. To support this goal, adaptation-related activities should generate knowledge that can help guide implementation of the GEF’s adaptation to climate change initiatives. From the GEF family perspective, sharing knowledge among users will ensure that the GEF portfolio, as a whole, can benefit from the comparative strengths and experience of the various Implementing Agencies.

(1) Lessons learned from projects should be classified into the following criteria. 
Does the adaptation deal with:

- climate change including variability (inter-annual and/or multi-decadal) risks?

- single sectoral and/or socio-economic issues?

- ecosystems?

(2) What are the best practices in:

- integrating adaptation into national and local development policy?

- project design and implementation mechanisms?

The above should include lessons on how to prioritise adaptation options (strategies/policies or operations), the scope of the adaptation project (local, sub-regional, national to sub-regional scales), and capacity development approaches on adaptation, including engaging key stakeholders on adaptation. This will also include lessons on:

project- and programme-level impact indicators.

(3) Share knowledge and experiences on adaptation, especially lessons learned on the following:

- which are the most common barriers to adaptation, at the information supply or uptake end? (What lessons emerge that have relevance to the role of UNDP, GEF and/or local partners with respect to designing and implementing adaptation project)?

- what are the conditions for success (or failure), including replication and scaling up?

- when do current coping strategies become ‘off-limit’, and over what time scales?

See Annex A10 for template on integration of  lessons learned from the project implementation into the ALM.

Regional Project Management Unit

Based at UNESCO BREDA Office

Figure 2: A hypothetical country with overlays of high vulnerability and high potential for global environmental benefits identifies the northwest as the top priority for SPA funded adaptation activities.

UNDP 
CO

## UNDP-GEF

## Implementing Agency

Capacity Development and Adaptation Cluster

Programme Period: 2007-2011

Programme Component:_________

Project Title: _ Adaptation to Climate Change- Responding to Coastline Change in its human dimensions in West Africa through Integrated Coastal Area Management (ACCC)

Project ID: tbd

Project Duration:	4 years

Management Arrangement: Mixed: NEX, DEX, Agency execution

UNESCO/IOC

1.

2.

3.

Total budget:			   14,029,517

Allocated resources:

PDF

- GEF	                                     700,000

- Government                             110,000

- Others                                                190,000

FSP

- GEF	                                  3,300,000

- UNESCO cash 	      	          60,000

- UNDP cash 		                      100,000

- Government cash                                66,668

- UNECO in kind	                      250,000

- Government in kind      	     6,117,849

- Bilateral parallel                             1,500,000

- NGO parallel                                  1,635,000