UNDP Project Document

Government of Sudan

United Nations Development Programme

3925: Implementing NAPA Priority Interventions to Build Resilience in the Agriculture and Water Sectors to the Adverse Impacts of Climate Change in Sudan

Sudan Higher Council for Environment and Natural Resources

Table of Contents

page

List of Acronyms	3

SECTION I: Elaboration of the Narrative	3

Part I: Situation Analysis	3

Country context	3

Project area context: vulnerable communities in five ecological zones	3

Development context: development indicators, economic growth, key economic sectors	3

Climate change context	3

Underlying Causes of Vulnerability and future risks	3

Current adaptive capacity and key gaps and barriers	3

Stakeholder analysis	3

Baseline analysis	3

Part II: Strategy	3

Institutional ,sectoral and policy context	Error! Bookmark not defined.

Project Rationale and Policy Conformity	3

Project Goal, Objective, Outcomes and Outputs/activities	3

Project Indicators, Risks and Assumptions	3

Additional Cost Reasoning and expected national and local benefits	3

Country Ownership: Country Eligibility and Country Drivenness	3

Sustainability	3

Replicability	3

Part III: Management Arrangements	3

Implementing Agency	3

Executing Arrangements	3

National and regional level project management and coordination	3

Collaborative arrangements with related projects	3

PART IV: Monitoring and Evaluation Plan and Budget	3

Learning and Knowledge Sharing	3

PART V: Legal Context	3

SECTION II: STRATEGIC RESULTS FRAMEWORK (SRF)	3

SECTION III: TOTAL BUDGET AND WORKPLAN	3

Annex A: Description of priority areas selected for the implementation of the project	3

## List of Acronyms

ALM 	Adaptation Learning Mechanism

APR	Annual Project Review

CBO	Community based organization

CCA	Common Country Assessment

CCF	Country Cooperation Framework

CPD	Country Programme Document

CPAP 	Country Programme of Action Plan

fd	feddan (local land area measurement of 4200 meter2 or [0.42 ha])

GEF	Global Environment Facility

GOS	Government of Sudan

GoNU	Government of National Unity of Sudan

GoSS	Government of Southern Sudan

HCENR	Higher Council for Environment and Natural Resources

IFAD	International Fund for Agriculture Development

INC	Initial National Communication (to the UNFCCC)

IPRSP	Interim Poverty Reduction Strategy Paper

MDG	Millennium Development Goals

M&E	Monitoring and Evaluation

MEA	Multilateral Environmental Agreements

MIWR 	Ministry of Irrigation and Water Resources

MOU	Memorandum of Understanding

NAPA	National Adaptation Programme of Action

NGO	Non-governmental Organization

PCC	Project Coordinating Committee

PD	Project Director

PPG	Project Preparation Grant

PIR	Project Implementation Review

SNC	Second National Communication (to the UNFCCC)

UNDAF	United Nations Development Assistance Framework

UNDP	United Nations Development Programme

UNFCCC	United Nations Framework Convention on Climate Change

# SECTION I: Elaboration of the Narrative

Part I: Situation Analysis

- Sudan’s Initial National Communication identified agriculture, water and health as the highest priority sectors where urgent and immediate action is needed to manage the risks of increasing climatic variability and long-term climate change. Sudan’s National Adaptation Programme of Action (NAPA), submitted to the UNFCCC in July 2007, identified 32 urgent priority project profiles in these sectors which, according to widespread local stakeholder consensus, are anticipated to reduce the increasing vulnerability of the rural communities to current and future climate change risks. Consistent with guidance for the LDCF (GEF/C.28/18, 2006), the NAPA process also yielded a consensus that the highest priority intervention should be a programme of adaptation-focused interventions with a major focus on the enhancement of food security. Moreover, the programme should buildadaptive capacities of the rural population, particularly of rainfed farming and pastoral communities.

- This LDCF project seeks to implement such a programme. It will be implemented in five specific rural areas that were identified during the NAPA process as likely to be the hardest hit by recurring climate change induced pressures on food security. Pilot adaptation interventions in the five areas are premised on the underlying rationale that the populations in these areas depend upon rainfed agriculture and climate change impacts e.g. additional heat stress, greater rates of evapotranspiration, and reduction in water availability, are poised to impose additional risks on already vulnerable livelihoods. There is an urgent need, therefore, to build resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks.

- The goal of the project is to enhance Sudan’s resilience and reduce vulnerability to climate change impacts. The objective of the project is to implement an urgent set of adaptation measures, building off priority measures identified during the NAPA process, that will minimize and reverse the food insecurity of small-scale farmers and pastoralists, thereby reducing vulnerability of rural communities from increasing climatic variability and climate change. More specifically, The project has a major focus on building resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks.

- The project will have three major outcomes. First, the resilience of food-production systems and food-insecure communities will be enhanced. This will achieved principally through the implementation of pilot adaptation measures. Second, institutional and individual capacities to support and promote climate risk management responses in the agriculture sector will be strengthened by capacity building to incorporate climate change risks into ongoing and future national development planning. Third, a systematic understanding of lessons learned and emerging best practices will be synthesized in order to provide important lessons on what does and does not work in improving resilience of vulnerable communities in Sudan.

- The first outcome targets the implementation of proactive adaptation measures to enhance the resilience and adaptive capacity of smallholder farmers in the five areas who are particularly vulnerable to the impacts of climate change, especially drought. The second and the third outcomes target the adaptive capacity of the individuals and institutions responsible for integrating climate risks into ongoing development planning.

## Country context

- Sudan, Africa’s largest country, encompasses an area of about 250.6 million hectares, bounded on the east by the Red Sea and on the other sides by nine African nations: Eritrea and Ethiopia to the East, Kenya, Uganda, and the Republic of Congo to the South, the Central African Republic and Chad to the West, and Libya and Egypt to the North. The country is divided administratively into 26 States. It is composed of vast plains interrupted by a few widely separated ranges of hills and mountains.

- Population has grown from 10.26 million in 1956 to 25.6 million in 1993. At present, the country’s population is 30.3 million and its annual growth rate has increased from 1.9% during the 1960s and 1970s, to 2.7% in more recent years. Rural-to-urban migration has been steady and high, with urban population growth of 4% between 1983/1995. The urban population has grown from less than one million (854,000) in 1956 to 7.5 million in 1993. The rural population in 1993 constitutes 71% of Sudanese, (11% nomads, 60% rural settlers), whereas the urban population is 29%.

- It is predicted that urban populations will double every 26 years. This trend of high rural-urban migration is due mainly to recurring droughts (which are increasing in frequency), major civil conflicts, budget cuts, and declining developmental investment in the rural areas. Women tend to feel much of this impact. Male migration and displacement (both ecological and political) have increased the number woman-headed households. The national comprehensive strategy (for 1992-2002) acknowledged the need for prioritizing rural issues of rural poverty and exodus.

- Sudan has been shaped by multiple ethnic, religious and socio-economic divides. These divides, exacerbated by the competition for scarce natural resources (about 80% of Sudan’s population is directly dependent on the natural environment for survival), have been the underlying drivers for the country’s main conflicts since its independence in 1956 Conflict is widely recognized as an important source of poverty and risk to rural communities living on the rain lands of Sudan (around 50% of the country’s total population) (CPAP Sudan, Draft Jan 2009).

- Most of these conflicts are resource-based in nature, often between pastoralists and farmers. Whilst triggers are manifold, the resort to violence is aggravated by feelings of communal marginalization, a lack of clear policy regulating access, ownership and usage rights of natural resources and the lack of coordination and capacity of conflict management mechanisms. At the same time, the traditional structures, which were historically involved in resolving land disputes, have been weakened and there is a lack of coordination between official institutions involved in natural resource management.   Accordingly, there is a need to find creative ways of bringing communities together in a spirit of partnership, to share finite resources and encourage a collective responsibility towards management of local services and structures, in a way that will encourage investment in the broader peace process.

- National efforts are already well underway to address the non-climatic factors identified in Box 1, as reflected notably in the 5-year Plan (2007-2011) developed by the Sudanese National Council for Strategic Planning, the Strategic Goals of the 25-year Vision, as well as ongoing national policy processes that have parallel aims to climate change adaptation (i.e., Poverty Reduction Strategy Paper and rural development initiatives). The NAPA follow-up project is clearly embedded in baseline activities and through its focus on reducing the additional risks associated with climate change; it will enhance the effectiveness of on-going development investments (Sudan PIF, 2007).

## Project area context: vulnerable communities in five ecological zones

- During the NAPA process, faming communities within 5 distinct ecological zones had been identified to be particularly vulnerable to the impacts of climate change and in need of urgent and immediate adaptation measures. These zones are illustrated in Figure 1. During the PPG phase, scoping activities were conducted to identify specific regions within each of these ecological zones in which project activities would be implemented. A brief description of each project area is provided below. Detailed ecological and socio-economic descriptions of each of the five project areas is provided in Figure 1:

- River Nile state: areas of lower River Atbara (region 1 on map at right).

- North Kordofan State: areas of Bara, Gabrat Alsheikh and Sawderyas (region 2).

- Gedarif State: area of Butana (region 3).

- South Darfur State: areas of Shairiah, Muhagriah, Malam, Darbat, Marshung (region 4).

- Central Equatoria State: communities Kudda, Legge and Tigore, located west of Juba (region 5).

## Development context: development indicators, economic growth, key economic sectors

- Sudan’s economy is heavily dependent on the agriculture and forestry sectors. Agriculture provides 90% of the raw material for local industries, and employment and income for more than 80% of the population. In addition, agricultural products are a dominant component of foreign trade, contributing more than 80% of Sudan’s exports, primarily in the form of raw materials (gum Arabic, oil seeds and cotton). Agriculture and forestry (both natural and planted trees) account for almost all of domestic supply of staple food (sorghum, millet and animal production), and to more than 70% of the national energy consumption, in form of fuel-wood and other biomass sources.

- Between 2000 and 2006, economic growth averaged roughly 7 % per annum and approximately 10% in 2007. The overall economic growth has not been translated into equivalent human development improvements and poverty reduction. Additionally, the weak capacity of government institutions and the poor status of infrastructure, consequences of decades of conflict, have reduced the ability to formulate and implement macro-economic reforms and poverty eradication policies and to deliver services efficiently (CPAP Sudan, Draft Jan 2009). Impoverished communities are poorly equipped to adapt to climate change.

- Sudan's current water resources, as well as its ability to harness them, are limited and prone to severe shortage. Annual water availability is provided mostly from surface waters and, to a lesser extent, from groundwater resources (El Toum, 1999). The Nile water basin contributes most of Sudan’s available surface water. However, though the Nile transports over 93 billion cubic meters (bcm) of water per year on average, Sudan’s share is only 20.5 bcm per year, in accordance with a 1959 water use treaty with Egypt. Beyond the Nile watershed, the total annual flow in seasonal streambeds ranges between 3 and 7 billion cubic meters (bcm) per year in three major rivers - the Gash, Baraka and Azum (El Toum 1999). The water resource situation for remote areas is especially precarious, as flow from seasonal streams is limited in quantity and duration and varies in terms of turbidity. Thus, Sudan's available surface water ranges between 23.5 and 27.5 bcm per year (INC, 2003).

- With a current population of roughly 30 million, Sudan's available surface water - if fully accessed and utilized - can provide between 920 and 1,050 cubic meters per capita - a level well below the limit of water scarcity and in the range of water’s stress as classified by the FAO water stress scale (Raskin et al, 1997). Sudan is currently able to utilize only around half of its available water, primarily due to limited water storage capacity. To supplement surface water, annual groundwater abstraction has grown to roughly 16 bcm. With an annual recharge rate of about 4 bcm (El Toum, 1999), it is clear that Sudan is not harvesting its groundwater resources in a sustainable manner. Ground water withdrawal in Sudan is quite costly, as most aquifers are located at depths between 40 and 400 meters. However, under current trends, reliance on groundwater resources is unlikely to abate. If available surface water is fully utilized by expanding the storage capacity through new technology, investment, and other practical measures, the water available per capita will still only approach the water scarcity level. Moreover, as the structure of water demand evolves from its current dominance by agricultural uses (about 94%) to more intensive future uses in the industrial and residential sectors (together accounting for a future 31% share), water pressures will clearly increase. It is anticipated that the unsustainable nature of groundwater withdrawal will become even more acute (INC, 2003).

- Gender disparities are marked in Sudan, with differences within regions and by ethnic group. MDG indicators show pronounced inequalities between men and women. Women in Southern Sudan experience one of the poorest quality of life indices in the world and have suffered disproportionally from the effects of the war through abduction, heavy workload, physical and psychological violence, little legal protection and lack of access to basic social services. The majority of women still remain outside the political process in Sudan. The Interim Constitution of Southern Sudan (ICSS) provides for a minimum quota of 25% women in government service as well as a bill of rights that promotes gender equality and equal protection provides the legal basis for government efforts at balancing the gender equation. Yet, women remain a minority in all aspects of governance, civil service, leadership, and in seeking access to justice, whether it is through the statutory institutions or customary mechanisms of dispute resolution. This is particularly the case at the state and local levels of governance.

## Climate change context

- Sudan’s Initial National Communication (INC) to the UNFCCC, submitted in July 2003, provided an assessment of likely impacts of climate change on several sectors including decreasing annual rainfall, increasing rainfall variability, and increasing average annual temperatures-- all of which contribute to drought conditions in many areas.  An examination of Sudan’s ecological zones indicated that the majority of its land is quite vulnerable to changes in temperature and precipitation. Changes in temperature and rainfall patterns also represent a priority threat to food security in Sudan’s agriculture-based economy.  Current increasing variability is a manifestation of long term change of climatic conditions in the country, region, and globally. Changes in average temperature or precipitation often do not show strong signals, but the well-observed trends of decreasing annual rainfall and increased rainfall variability have contributed to drought conditions in many parts of Sudan.

- Of its diverse ecological zones more than half the country can be classified as desert or semi-desert, with another quarter, arid savannah. Changes in temperature and rainfall are likely to lead to desertification in some regions, while in the South; the spread of vector-borne diseases is likely. The country’s inherent vulnerability may best be captured by the fact that food security in Sudan is mainly determined by rainfall, particularly in rural areas, where 70% of the total population lives. Changes in temperature and precipitation could cause shifts in the precarious distribution of these ecological zones, in the productive capacity of rainfed agriculture, and thus, in the security of the nation’s food supply.

- Historically, average annual rainfall has declined from about 425 mm/year during the 1941-1970 period to about 360 mm/year in the 1970-2000 period. This represents a decrease of annual rainfall of about 0.5% per year. At the national level, there is a trend of greater rainfall variability in Sudan, increasing at a rate of about 0.2% per year. For the completion of the INC, Sudan developed scenarios to project future temperature and precipitation, due to climate change, in 2030 and 2060, based on a doubling of CO2 emissions (IS92A scenario), milestone years 2030 and 2060 are used (in place of IPCC recommended 2015, 2050 and 2100) (INC, 2003).

- Relative to baseline expectations, the INC indicated an average warming range of 1-3˚C and average change in precipitation of -5.8% by 2030 in some areas. As rainfall is already extremely erratic and varies widely from the northern to southern ranges of the country. The severity of drought experienced depends on the variability of rainfall both in amount, distribution and frequency.

- The Sahelian belt which runs through Sudan is very likely to suffer the impact of climate change. Since the 1930s, the Sahara Desert has encroached southwards by between 50 and 200 kilometres, eating into semi-desert and savannah land. Climate change is likely to exacerbate this desertification trend. According to the INC, between 1961 and 1998, episodes of drought have inflicted Sudan with varying severity. This period witnessed two widespread droughts during 1967-1973 and 1980-1984 - the latter being the more severe. The same period witnessed a series of localized droughts during 1987, 1989, 1990, 1991, and 1993, mainly in western Sudan (Kordofan and Darfur) and parts of central Sudan. Drought threatens the remaining cultivation of about 12 million hectare of rainfed, mechanized farming and 6.6 million hectares of traditional rainfed lands. Pastoral and nomadic groups in the semi-arid areas of Sudan are also affected.

- Climate change is expected to influence the frequency of flood hazards, dust storms, thunderstorms, and even rare heat waves and wind storms are expected. Climate change is likely to entail increased climate variability, particularly of rainfall, and the incidence of droughts and floods, which have been occurring increasingly in Sudan since the 1970s. Floods are already causing increased erosion of the banks of the Nile and consequently a loss of farmland. As with drought, two types of floods affect the country: localized floods, caused by exceptionally heavy rainfall and runoff (flash flood), and widespread floods caused by overflow of the River Nile and its tributaries. Floods in both forms are highly unpredictable due to the nature of rainfall variability in time and space. Floods caused by localized heavy rainfall affect parts of central, eastern, and western Sudan. Of the most severe floods recorded for the River Nile since the 1800s, three occurred within the past 20 years (1988, 1994 and 1998). Even in northern Sudan there have been cases where heavy rain caused localized floods (e.g., October 1999). Floods are causing increased erosion of the banks of the Nile and consequently a loss of farmland; as such, the most vulnerable groups to both forms of flooding are people who live in low lands and along the riverbanks (CPAP Sudan, Draft Jan 2009).

- Sudan’s economy is heavily dependent on the agriculture and forestry sectors. Agriculture provides 90% of the raw material for local industries, and employment and income for more than 80% of the population. Roughly 90% of cultivated areas depend exclusively on rainfall (a system of farming referred to as the traditional rainfed sector). Quantity and distribution of rain is thus a central determinant of crop success in Sudan, with fluctuation in crop yield attributed almost solely to fluctuation in rainfall. One of Sudan’s most pressing concerns as it examines the impact of temperature and rainfall patterns is the security of its agricultural lands. Crop production is expected to be directly affected by climate change, through changes in temperature and precipitation (as discussed above), as well as indirectly, through increased pests, pathogens, and other pressures. Potential effects include the following:

- Reduction in ecosystem integrity and resilience, and a decline in biodiversity,

- Decrease in forest area and area under cultivation,

- Decline in crop and gum yield,

- Frequent spells of drought (with impacts such as severe shortages in drinking water),

- Change in the planting dates of annual crops,

- Fungal outbreaks and insect infestations due to changes in temperature and humidity, and

- Increased risk of food shortage and famine.

- The results of the vulnerability study conducted for the INC suggest that the nation as a whole may be hard hit by even modest changes in temperature and precipitation. The Agriculture & Forestry Vulnerability Assessment results suggest that, in 2030 and 2060, the humid agro climatic zones shift southward, rendering areas of the North increasingly unsuitable for agriculture. Crop production is predicted to decline by between 15% and 62% for millet and between 29% and 71% for sorghum. The most vulnerable groups are traditional rainfed farmers and pastoralists. The predicted population increase is inversely proportional to predicted crop production in the region. As a backdrop to this, increased temperature and variability in precipitation, combined with growing socioeconomic pressures are likely to intensify the ongoing process of desertification in the region and beyond.  Given the projected increases in population, desertification and assorted environmental and socioeconomic pressures, these preliminary findings provided a warning signal to stakeholders and decision-makers and have helped to sharpen attempts at identifying and now implementing adaptation measures.

## Underlying Causes of Vulnerability and future risks

- The root causes of the vulnerability of Sudan’s rural farmers to climate change is due to a combination of deep poverty and a reliance on livelihood activities that are highly sensitive to climatic conditions. Poverty is deeply entrenched in rural areas, home to over 20 million people living on less than US$1 a day. Production remains consistently quite low due to development challenges that are taking place simultaneously with increasing climate risks. Sudan’s agricultural sector is dominated by small-scale subsistence farmers who rely largely on rainfed and traditional practices. Production is consistently quite low because rainfall is unreliable and concentrated in short growing seasons. Additionally, farmers’ access to tools and extension services designed to build adaptive capacity remains quite low. Regarding climate change, the growing vulnerability of Sudan’s farmer/pastoralist communities is due to the fact that increasing climatic variability has become incompatible with traditional practices regarding crop selection, water resource management, communal rangeland management, drought preparedness, and household income generation. In addition to this, there is a lack of awareness, technical capacities and knowledge to make informed decisions.

- About 80% of Sudan’s population is directly dependent on the natural environment for survival and competition over limited local resources is a key driver of conflict in Sudan. Conflict is widely recognized as an important source of poverty and risk to rural communities living on the rain lands of Sudan (around 50% of the country’s total population). Most conflicts are resource-based in nature, and often between pastoralists and farmers. Whilst catalysts for conflict are manifold, the resort to violence is aggravated by feelings of communal marginalization, a lack of clear policy regulating access, ownership and usage rights of natural resources and the lack of coordination and capacity of conflict management mechanisms. The traditional structures that have historically been involved in resolving land disputes have been weakened and there is a lack of coordination between official natural resource management institutions.   Accordingly, there is a need to find creative ways of bringing communities together in a spirit of partnership, to share finite resources and encourage a collective responsibility towards management of local services and structures, in a way that will encourage investment in the broader peace process. The increasingly felt impacts of climate change only aggravate this situation, rendering the need for adaptation in a broader sustainable development context all the more urgent.

- At present, the Government of Sudan and a number of bilateral donors are tackling these root-causes through the implementaiton of activities that would be implemented in the absence of climate change (baseline), including:  stimulating rural economies by providing basic infrastructure, market access, and developing technical as well administrative capacity in rural areas; improving agricultural productivity by implementing soil conservation and water harvesting measures in large-scale agricultural schemes; and providing alternative water sources for rural communities.  While necessary for the overall development of the sector, these baseline interventions are not sufficient to ensure resilience of the agriculture sector to future climate risks. Addressing the above root causes will involve the introduction of resilience-building corrective practices that are more consistent with threats from a changing climate.

- Sudan is already highly vulnerable to current climatic shocks and will become even more vulnerable in the face of future climate change. The nation’s vulnerability to climate change could jeopardize national development efforts and already pose a serious challenge to development priorities in agriculture, forestry, and water resource management.  For Sudan, climate change is not merely an environmental issue defined by projections and scenarios - it represents a serious sustainable development problem. Indeed, a primary feature of the design of the proposed NAPA follow-up project is that the core project activities are complementary of government development strategies and investments in the project areas. The eradication of poverty and improved food security is among Sudan’s primary development objectives.

## Current adaptive capacity and key gaps and barriers

- Subsistence farming communities are reliant upon ecosystems that are, in many cases, fragile or degraded, such that the added challenge of increased ecological stress from climate change represents an existential threat. Local populations have existing coping mechanisms and the capacity to adapt to climate variability within the range of what humans have been experiencing for millennia.  Therefore, it can be said that some autonomous adaptation is taking place. Local communities, however, have limited capacity and resources to adapt to climate change induced variability. Modern challenges like rapid population growth and forced displacement when coupled with resource scarcity and climate variability outside the realm of prior experience, coping measures have begun to be ineffective and do not sustain the livelihood systems either in short or long term. Farmers have limited capacity and resources to modify their current land and water management practices that are viable under the changing climatic conditions. Existing cropping patterns and applied agronomic measures are inadequate and expose farmers to climatic shocks, and render them vulnerable to weather hazards like extreme droughts and floods.

- In Sudan, subsistence farmer coping strategies for food insecurity have been developed in the context of the severe droughts of the 1980s and the recurrent droughts of more recent years. Essentially, coping strategies for rainfed crop production failure in drought-prone zones in the five project areas involve a hierarchy of activities that can be broadly categorized as risk minimization strategies, risk absorption strategies, and adoption of new risk strategies. Farmers navigate progressively through this spectrum of strategies depending on the nature of the perceived threat to their food security. As they do so, their coping options necessarily become increasingly narrower. At one end of the spectrum, the aim of their coping strategies is to constrain the potential damage caused by a drought with the majority of household assets kept intact; at the other end, the aim of their coping strategies is to save life even if it comes at the expense of the dissolution of all of the household’s accumulated assets because all other options have been exhausted.

- National efforts are already underway to address the non-climatic, underlying factors that contribute to the vulnerability of communities in Sudan, and to creating an enabling environment that can both complement and reinforce local coping strategies such that the need to proceed long the hierarchy of coping options - from constraining damage to extreme life-saving measures - is lessened due to increased resilience against climatic shocks. While a limited effort has been spent to foster awareness and understanding of climate risks to food security, government institutions are subject to frequent changes due to political instability, policies and strategies do not effectively incorporate climate change risk management options. The number and qualifications of staff involved in climate change are inadequate. There is a need to recruit qualified staff and conduct intensive training. Capacity building is needed in the areas of information technology and networking.

- Sudan is now mobilizing internal and external funding resources to improve local food production and food security, and actively collaborating with donors to implement the recommendations of its Poverty Reduction Strategy Paper (PRSP) and promote the achievement of its Millennium Development Goals (MDG). While necessary for the overall development of the sector, these interventions are not sufficient to ensure resilience of the agriculture and water sector to future climate risks due to the fact that current food security policies do not ensure the provision of safe water supplies in rural areas, towns, and tribal migrating routes. This is due in large part to the lack of coordination among the number of institutions charged with promoting food security (see table below). At some level, this lack of effective coordination is a factor that contributes to increasing food insecurity, rangeland degradation and the incidence of conflicts and frictions between farmers and herders. The following ministries and agencies, funded by the Government of Sudan (GoS) are responsible, directly or indirectly, for ensuring food security are noted in the Table below. For some Ministries their annual funding levels in 2007 are denoted.

| Government Agency | Funding/ Investment level in 2009 (US$) | Institutional food security mandate |
| --- | --- | --- |
| Ministry of Agriculture and Forests (MOAF) | 83.052 | Responsible for managing agricultural development policy and infrastructure investments |
| Ministry of Animal Resources and Fisheries (MARF), | 42.399 | Responsible for livestock management, oversight of veterinary services, and regulation of fishing industry |
| Ministry of Irrigation and Water Resources (MOIWR), | 264.216 | Responsible for water resource management, including Nile-based hydropower resources |
| Ministry of Finance and National Economy (MOFNE), | 143.759 | Responsible for macroeconomic policy setting |
| Ministry of Humanitarian Affairs (MOHA), | 2.401 | Responsible for displaced person policies, humanitarian assistance, and coordination with international assistance |
| Ministry of Health | 49.060 | Responsible for public health policies, information, programmes, and epidemiological studies |
| Strategic Reserve Authority (SRA), | 72.280 | Autonomous body answerable to the MOFNE, responsible for strategic commodity reserves, information, and provision of services. |
| Agricultural Bank of Sudan (ABS), | 4.8 | National bank responsible for commercial lending in the agricultural sector |
| Ministry of Science and Technology (MST), | 29.586 | Responsible for technology transfer and evaluation of applicability of scientific advances |
| Ministry of Foreign Trade (MFT), | 2.678 | Responsible for regulaing foreign trade and tariff conditions |
| Government of Southern Sudan (GSS) | 1217.88 | Autonomous state government in Southern Sudan |
| State Governments in Northern Sudan | 2508.68 | Semi-autonomous state government in northern Sudan |

- There is an urgent need in Sudan for a coherent national food security strategy and improved links between responsible government entities in its execution. Currently in Sudan, there does not exist a comprehensive national food security strategy. Instead, food security policy is distributed among the numerous institutions at the federal and state levels as noted in the table above. Coordination across these various institutions was supposed to be facilitated by a National Council for Food Security, an entity that was first proposed in September 2001 under the chairmanship of the Minister of Agriculture with other concerned ministers as members. Though only a proposed entity, a Technical subcommittee was formed for monitoring and evaluation of food security threats, developing an early warning system for food security, and submission of recommendations to the National Council for future action. Unfortunately, to date the National Council has not been approved by the Council of Ministers and the Technical Committee has only met occasionally for the purpose of information exchange. Its input into decision-making was limited primarily because of the absence of a national food security strategy but also because of an inadequate political commitment from senior policymakers. This situation has led to a predictable set of undesirable consequences for Sudan including poor food aid targeting, late and/or inadequate funding needed for interventions, and inadequate coordination of donor activities.

- In addition to underlying vulnerabilities contributing to current conditions of food insecurity there are three main barriers affecting the ability of Sudanese institutions to respond to food security threats (El Bashir and Ahmed, 2006):

  - Institutions and local communities are not aware of more effective adaptation options. As a result current coping strategies of local communities are inadequate to effectively cope with current climate variability and future change. When droughts are not particularly severe or recurrent over several years, smallholder farmers typically employ risk minimization strategies in rural areas of Sudan. They do so in a development context in which they have little to no recourse to rural credit and insurance markets, if such exist at all in their particular location. At a broad level, these coping mechanisms typically involve efforts to accumulate savings and diversify productions systems. Specific coping strategies in rural Sudan include, among others, reliance on pastoral systems as a complement to farming (i.e., small herd ownership of sheep, goats, and cattle), maintenance of small-scale household vegetable gardens, and development of small-scale cottage industries. The driving premise for such activities is both meeting near-term needs as well as longer-term risk hedging.

When droughts are severe or annually recurrent in Sudan, normal systems of production are threatened with collapse. In such circumstances, smallholder farmers have employed new risk strategies. In the absence of relief food delivery, such strategies involve taking up new and likely extraordinary strategies for survival. Diets become increasingly dependant on whatever food stores are available as well as wild foods. Households begin to sell their assets in the form of livestock, fields, and homesteads to gain access to currency. If possible, some move to other regions to stay with distant relatives. Others have no option but to migrate to refugee camps on the outskirts of Khartoum with whatever possessions remain to them; the return to their original homesteads is highly uncertain. Between these extreme options, household coping strategies involve a combination of reducing non-essential household purchases and drawing down whatever stores of food have been accumulated. Efforts intensify to secure off-farm income.

Some examples illustrate that many of options to cope become increasingly irreversible as conditions worsen. A good example is the drought that affected small farmers in North Kordofan in the 1980s. Many farmers were forced to sell or slaughter their sheep and cattle herds to cope with diminished fodder and water availability. Many farmers abandoned their homesteads and migrated to urban areas. As households proceeded along the hierarchy of coping strategies to reach such decisions, it’s clear that they did so because of increasing vulnerability to food insecurity. Unless conditions change or external resources arrive, the viability of such strategies in the face of recurring droughts is low, at best delaying the onset of the next phase.

To enhance the effectiveness of farmer risk minimization strategies (i.e., the first phase in the above hierarchy of coping strategies in Sudan), a variety of resources are needed. These range from improved knowledge systems (e.g., extension services on optimal crop choices, pastoral rotation options to enhance fodder productivity, trends in seasonal rainfall forecasts), to resources to enhance household income diversification (micro-credit schemes, revolving funds, crop insurance), to poverty alleviation programs that provide much-needed rural development resources and infrastructure that are able to exploit synergies between global climate change concerns and local poverty alleviation.

  - Weak drought contingency planning framework: Sudan’s current drought contingency planning framework contains a weak component for ensuring food reserves in the face of drought. The Strategic Reserve Authority (SRA) was established in September 2000 and is an autonomous body answerable to the Minister of Finance and National Economy. Its key objectives are to build a strategic reserve of commodities, collecting data on production, estimate consumption and determine surplus/deficits, provide services on the basis of cost recovery, contribute to national income, and invest in neglected services. To date, the SRA has been ineffective in achieving these objectives due to the lack of a clear strategic vision, a shortage of funds, and a lack of a transparent system to allocate scarce food stores among competing entities.

  - Low Institutional Capacity: Institutional capacities to address some of the urgent adaptation needs are inadequate as they relate to food security issues. There is an urgent need in Sudan for improving the link between the adaptation needs and national policymaking. Thus far, progress has been limited by a general weakness of capacity in areas including strategic development planning and coordination across state/federal ministries. Despite a fairly well-developed adaptation action plan and substantial efforts to sensitize policymakers to the threats the institutions do not have clear mandate to consider climate change related risks. They also lack adequate skills sets, tools and conducive institutional set-up to systematically assess risk, cost the potential impacts and identify and enforce cost-effective adaptation policy measures. This calls for urgent institutional capacity development efforts at national and sub-national levels.

## Stakeholder analysis

- There are several stakeholders that have been consulted during the project preparation phase. National experts from the HCENR, the Sudanese Environmental Conservation Society, the University of Khartoum, the Range and Pasture Adminsitration, the Ministry of Agriculture Animal Resources and Irrigation, the Ministry of Health, and the Government of the State of Southern Sudan have been heavily involved from the outset in the development of the design of project activities. They were involved in undertaking scoping missions in each of the project areas to consult with local authories, community stakeholders, other relevant government agencies. The results of these consultations are sumarized below together with an outline of local roles in project implementation.

- River Nile state: Project activities will take place in the communities of Adarama and Salalat on the eastern bank of the River Atbara and in Shababeet and Morzooga on the western bank. Ministry of Agriculture, Animal Resources and Irrigation will allocate the funds for local component and supervise implementation of the project. The stakeholders targeted in the proposed adaptation project are 10,000 local poor farmers living in lower Atbara region and 5,000 landless people from neighbouring areas who currently make use of flooded areas. The landless population have no access to land and are in a similarly vulnerable situation to the local poor who subsist on small land holdings. Other entities in the area who have committed to being engaged during and after the project’s implementation include the Irrigation Department and the famer’s union. Farmer’s union will be key to outreaching the local farmers, disseminating information, demonstrating advantages and feasibility of some of the on-farm adaptation measures, and training farmer groups in improved production and crop diversification. A technical committee, comprised of local stakeholders, has been formed to support project implementation from the following entities: Irrigation department, Crop protection, Soil protection, farmer’s union, Local Governmental administration office. The stakeholders involved include individuals from the Ministry of Agriculture and Animal Resources, Ministry of Finance and Economy, Hediba research station, River Nile University, and local volunteer groups and community organizations.

- North Kordofan State: The NAPA consultation process revealed that the most vulnerable groups live in Bara, Sodari and Gabrat Elsheikh localities. In consultation with local stakeholders, it was agreed that the Bara administration unit will take the leadership role and house the project. This area was selected on the basis of the following vulnerability-related criteria:  availability of underground water, sand dune encroachment, availability of rangelands, stable land tenure systems, community homogeneity (i.e., from a single tribe, the Dar Hamid; and a sub-tribe, the Frahna), relatively high awareness of community about climate related risks. Fifteen specific communities were selected: El Bashiri, El Humara, El Hidaid, Um Nabag, Shag-elnom, Abu Dalam Elmofatih, Abu Dalam Elaama, Um Rub, Mashga, Goz Khalefa, Abu Gayda, Moga, Foja, Hasheiti and El Raeila.

- Gedarif State: As a result of consultations, the core consultative group was established consisting of the director of animal health administration of the Ministry of Animal Resources, the director of preventive medicine of the Ministry of health, the directors of soil conservation and pasture administrations of the Ministry of Agriculture, the director of planning of the Ministry of Finance, representatives of water corporation departments of ground water and wadi, the director of the state environmental council, the representative of the Sudanese Environment Conservation Society in Gedarif State, and the commissioner of the Butana Locality. Four communities around the Al Sadda village were selected. Additional consultative meetings were held with local administrators, religious groups. The State Council for Environment, Gedarif State, will act as the main coordinating body facilitating the implementation of project activities.

- South Darfur State: The State Ministry of Agriculture has taken a lead role in engaging project beneficiaries and securing local buy-in for the proposed adaptation measures. Through stakeholder consultations with different groups, the project stakeholders have expressed their willingness to participate in the project and adopt new approaches and innovations, particularly in the area of water harvesting and agronomic measures. Project activities will take place among several tribes (Dago, Fur, Birgid, Messairia, Zhagawa, Berti and Burnu) spread across 15 villages in the region of south of Jbel Marra. Stakeholders from the 15 villages, in principle, agreed that water harvesting is the most important to them. The project will identify the best combination of traditional water harvesting techniques (reservoirs, or hand dug wells) with improved wells that can be equipped with hand-pumps, dams and reservoirs.

- Central Equatoria State: Project activities will take place among the communities Kudda, Legge and Tigore, which are situated 25 – 80 miles west of the town of Juba.  The Rural NAPA team, based in Juba, held stakeholder consultations with Chiefs, community leaders, and local authorities and conducted Participatory Rural Appraisals (PRA) during which the beneficiaries agreed to participate in implementation of the project via the village development committee: 25 people from development committee and 10 from the women’s association. In Kudda, the women’s associations are the most organized community structure. Women, children and the elderly are the most affected vulnerable groups. The local stakeholders involved from the Central Equatoria State are the vulnerable groups, namely the agro-pastoralists in Kudda (Bari and Nayangwara), Legge (Paljulo), and migrant Mundari who keep the cattle.  The majority of community members are low-income groups whose livelihoods rely on small-scale farming, forest resources, and raising goats, cattle and sheep. Community members typically depend on NGOs for coping mechanisms; however, currently there are no NGOs in the areas to support the vulnerable population. Other stakeholders include the Ministry of Agriculture, Animal Resources and Irrigation, and the Ministry of Health.

## Baseline analysis

- During the Project Preparation (PPG) phase, detailed assessments were undertaken of ongoing and planned projects, policies, laws, executive regulations and decrees relevant to food security and sustainable agriculture and clarify baseline (non-climate driven) development issues pertaining to livelihood and agriculture sector resilience. The results of these assessments were summarized into four main project scoping reports: 1) Livelihood sector in select Sudan states; 2) Impact of Climate Change on Food Security; 3) Report on water related issues; and 4) Agricultural Issues. These assessments also investigated the proposed NAPA follow up projects’ synergies with national plans and policies including the Country Program Document (CPD), Common Country Assessment (CCA), and the UN Development Assistance Framework (UNDAF).

- In meeting the overall objective within the five (5) distinct vulnerable locations, the project has tailored specific activities to address the nature of climate change vulnerability that exists in the each of the site locations. A summary of the baseline for each site is outlined below. Absent the adaptation measures discussed in the Strategy section that follows in response to these baseline circumstances, further food insecurity is expected to increase in the form of annual damage form flash flooding, consistently low crop yields, poor rangeland productivity and increasing degradation of such areas, and low water supply efficiency.

- River Nile state: The baseline situation for this component of the project is that of chronic food shortages and water borne diseases associated with the River Atbara regularly flash flooding its embankments, creating loss of property and destroying crops. With only about 40% of the River’s annual discharge currently used for irrigation purposes, the potential to increase regional food security through harnessing water discharges is high.

- North Kordofan State: The baseline situation for this component of the project is that of frequent drought cycles seriously affecting farming, pastoralism, forestry, and gum collection activities. The region experiences extreme rainfall fluctuations varying from 75-450 mm/year. Such climatic conditions combined with overgrazing, over-cropping, and deforestation have caused substantial vegetation cover loss, including the loss of many endemic woody and grass species that were once dominant.

- Gedarif State: The baseline situation for this component of the project is that of recurring drought and high temperatures producing adverse effects on vegetation, rangelands, and local livelihoods. Due to deteriorated rangelands, overgrazing is common leading to the disappearance of suitable species and increasing conflicts over limited rangeland resources.

- South Darfur State: The baseline situation for this component of the project is that most of the population practices traditional agriculture and pastoralism; 25% of the population depends on animal husbandry as the major livelihood source. Rainfed agriculture is widely practiced to produce food and cash crops; irrigated agriculture is practiced to a lesser extent along creeks (wadis) and in small areas irrigated by hand-dug wells. Vulnerability to climate change is increasing due to changing climatic conditions against a background of resource conflict, human population growth, migration of people from more vulnerable areas in the north to less vulnerable areas in the south, limited government interventions, limited technical packages to help in adaptation in agriculture and animal production, and limited knowledge in water harvesting and improved use of surface water.

- Central Equatorial State: The baseline situation for this component of the project is that much of land in the Central Equatorial State is flood-prone due to an annual rainfall over 1,000 mm per year, poor water resource management infrastructure, and unsustainable exploitation of forest resources. Climate change impacts are overlain on conditions of chronic poverty, water-insecurity, lack of adequate potable water, poor rural marketing strategies, and lack of awareness about climate change.  Anecdotal evidence suggests that rampant deforestation may have also induced changes in the microclimate resulting in raised temperatures, lowered humidity levels and rainfall, and recurrent drought conditions. Such changes have left local communities in need of adaptation interventions to protect and better manage available water resources.

Part II: Strategy

- Based on the above situation and barrier analysis, the proposed project strategy is to take an “adaptive capacity approach”. The adaptation process requires the capacity to learn from ongoing experiences to cope with current climate, and to apply these lessons to cope with future climate, including surprises.  The adaptive capacity inherent in a system represents the set of resources available for adaptation, as well as the ability or capacity of that system to use these resources effectively in the pursuit of adaptation. The key component of adaptation in this approach, therefore, is capacity development aimed at expanding the coping range of the involved stakeholders given anticipated climate change risks to food security across the country.

- Additionally, the project aims to promote the mainstreaming of short-term climate risks into policy and planning frameworks, enhance institutional capacity building, and implement a monitoring and evaluation (M&E) system to account for lessons learnt. The adaptation activities are to be undertaken in close synergy with the National Strategic Plan for Sudan, which provides a framework for focusing, and coordinating Sudan’s development efforts over the next five years, and which builds upon the Comprehensive Peace Agreement (CPA) signed in 2004.

- The Least Developed Countries’ Fund (LDCF) was established under the United Nations Framework Convention on Climate Change (UNFCCC) at it seventh session in Marrakech and is managed by the Global Environment Facility (GEF). The fund addresses the special needs of the 48 Least Developed Countries (LDCs), including Sudan, which are especially vulnerable to the adverse impacts of climate change

- LDCF financing will be used to finance the implementation of on-the-ground, innovative adaptation measures that will be monitored and evaluated to assess implementation success and potential for replication in other areas of the country. The GEF/LDCF intervention is required for supporting the development and demonstration of adaptive capacity, as well as the implementation of adaptation measures that address Sudan’s looming food security crisis. GEF/LDCF intervention will support the integration of climate risks into agriculture and animal husbandry extension services that are aimed to support farmers and herders implement necessary adaptation measures. In this context, the GEF/LDCF funds will serve as a catalyst for revising the national approach to ensuring food security and addressing the root causes of vulnerability for at-risk livelihoods to reduce adverse social and economic impacts of climate change on the poorest rural communities.

## Project Rationale and Policy Conformity

- Given its vulnerability to climate change, it is clear that Sudan’s challenges are compelling. The INC identified agriculture, water and health as the highest priority sectors where urgent and immediate action is needed. Sudan’s National Adaptation Programme of Action (NAPA), submitted to the UNFCCC in July 2007, identified 32 urgent adaptation initiatives, across the country, in these sectors to reduce the increasing vulnerability of the rural communities to current and future climatic risks. Consistent with guidance for the LDCF (GEF/C.28/18, 2006), the NAPA process also yielded a consensus that the highest priority intervention should be a programme of adaptation-focused interventions with a major focus on the enhancement of food security by building the adaptive capacities of the rural population, particularly of rainfed farming and pastoral communities, relative to current and future climate risks.

- The highest priority area for NAPA follow-up intervention in Sudan is to improve food security. This project will promote key elements of a programmatic approach to adaptation to climate change in Sudan. The project has therefore a major focus on building resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks. By its simultaneous focus on enhancing food security, improving rural household livelihoods, lowering climate risks, and use of appropriate water harvesting technology, the project brings together the crucial elements needed for both targeted effectiveness and replicability potential.

- The project will be implanted in 5 priority areas, as mentioned previously in the Situation Analysis. Livelihoods systems in project’s five (5) focal areas are diverse, complex, and highly vulnerable, with few ready opportunities for household income diversification and adaptation. Four of the project sites range from semi-desert and low rainfall savannahs that are considered at risk of recurrent drought and further desertification. Subsistence farmers and pastoralists compete to access and use available resources which are subject to evolving management arrangements. Despite their vulnerability, local populations have little access to measures and practices that can increase their reliance in the face of climate change.

  - River Nile state: (e.g. areas of lower River Atbara). These are highly arid ecosystems in the far northern part of the country and represent over 25% of total land area with about 60 million hectares. Project activities will take place in the communities of Adarama and Salalat on the eastern bank of the River Atbara and in Shababeet and Morzooga on the western bank.

  - North Kordofan State: (e.g. areas of Bara, Gabrat Alsheikh and Sawdery). These are semi-arid areas in the central part of the country; representing over 20% of total area of Sudan with about 65 million hectares. Project activities will take place in a number of villages in the Bara locality (i.e., El Bashiri, El Humara, El Hidaid, Um Nabag, Shag-elnom, Abu Dalam Elmofatih, Abu Dalam Elaama, Um Rub, Mashga, Goz Khalefa, Abu Gayda, Moga, Foja, Hasheiti and El Raeila).

  - Gedarif State: (e.g. area. of Butana). These are essentially savannah-based ecosystems underlain by clayey soils.  These areas are typified by low rainfall and the prevalence of clay soils. They represent about 5% of total area with about 12 million hectares.  Project activities will take place in four communities around the Al Sadda village.

  - South Darfur State: (e.g. areas of Shairiah, Muhagriah, Malam, Darbat, Marshung). These are overwhelmingly savannah-based ecosystems underlain by sandy soils. These areas are typified by low rainfall and the prevalence of sandy soils; they represent about 3% of total area with about 8 million hectares. Project activities will take place among several tribes (Dago, Fur, Birgid, Messairia, Zhagawa, Berti and Burnu) apread across in 15 villages in the region south of Jbel Marra.

  - Central Equatoria State: These are essentially flood-prone ecosystems in the southern part of the country. These areas are located below latitude 10o north and represent about 3% of the total area with about 8.5 million hectares. Project activities will take place among the communities Kudda, Legge and Tigore, which are situated 25 – 80 miles west of the town of Juba.

- These rural sites were identified as being the hardest hit by recurring food insecurity issues during Sudan’s extensive NAPA consultative process. Pilot adaptation interventions in the five areas are designed to address particularly vulnerable populations in need of urgent and immediate adaptation to increasing climatic variability as well as climate change. The underlying rationale behind targeting these populations is based on the fact that the majority of Sudan’s population depends upon rainfed agriculture, and climate change impacts e.g. additional heat stress, greater rates of evapotranspiration, and reduction in water availability, are poised to impose additional risks on already vulnerable livelihoods. There is an urgent need, therefore, to build resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks.

- The stretching of projects resources over 5 distinct geographic areas is justified on the basis of several reasons. First, given Sudan’s diverse ecological settings, the nature of vulnerability to climate change varies significantly depending on the particular agro-ecological zone considered. Extensive stakeholder consultations have revealed that priority adaptation strategies to reduce rural food insecurity in the face of climate change are highly correlated with geographic locale. In the northern part of the country, confronting climate change-induced food insecurity implies a focus on alternative cropping strategies; in the western part of the country it implies alternative water catchment techniques; in the eastern part of the country it implies improved rangeland management, and so on. Focusing on a single region, with its implied attention to a single locally-driven adaptation strategy, diminishes the potential to capture the range of valuable lessons that can be learned by the implementation of locally-driven adaptation strategies to confront food insecurity across spatial scales.

- Second, the five project areas represent the outcome of extensive stakeholder deliberations during the NAPA consultative and prioritization process and which have been confirmed during the PPG design phase. The areas have been identified as being the key areas currently hardest hit by recurring food insecurity issues, and likely representing the regions in most urgent need of better understanding the range of cost-effective adaptation strategies. Third, the five project areas were selected, out of numerous other potential areas, based on the collective judgment of the formal NAPA stakeholder process that they possess highly favourable conditions to a) benefit the largest number of communities and b) replicate the lessons of project interventions to adjacent areas. Fourth, the adaptation interventions to be implemented in each project area are appropriately scaled to be commensurate with budget resources available. Since all the interventions focus on low-tech, non-infrastructural activities, and have been designed at pilot activity scales, the introduction of measures across ecological regimes that target different dimensions of climate change vulnerability offers a cost-effective basis by which to both enhance current adaptive capacity and explore new strategies that will ultimately contribute to future adaptive capacity that can benefit Sudan more broadly.

- Finally, the multi-region focus of the project, as opposed to a focus on any single region in the country, was the strategic aspect of the project design that was instrumental in catalyzing co-financing by the GOS. The project’s twin characteristics of strong complementarity with ongoing government programmes/initiatives (i.e., enhancing food security, improving rural household livelihoods, providing access to suitable technologies) and its focus on five key areas that overlap with the government’s high priority areas for development activities brought together the crucial elements needed for strong political buy-in and high relevance of the project to current development priorities of the GOS.

- The goal of the project is to enhance Sudan’s resilience and reduce vulnerability to Climate Change impacts. The objective of the project is to implement an urgent set of measures that will minimize and reverse the food insecurity and enhance adaptive capacity of small-scale farmers and pastoralists resulting from climate change, including variabilities in 5 vulnerable regions. The project has a major focus on building resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks. As a contribution to the achievement of the overall goal and primary objective, the project design includes three expected outcomes and numerous expected outputs within the five distinct and non-contiguous locations for project activities. This is summarized in the table below and explained in further detail in the paragraphs that follow.

- Sudan has been actively seeking to mainstream adaptation to climate change in the sectoral and development policies (NAPA, 2007). Such policies are embodied in:

  - Poverty Reduction Strategy: major portions of the strategy focused on agriculture, water resources and public health.

  - Some State Environment Councils proposed potential adaptation measures in their sectoral policies including that of water resources and agriculture.

- The project’s strategy for reducing vulnerability to climate change is to climate-proof current productive activities through enhancing the ability of small farmers and pastoralists to cope with increasing climate variability and future climate change. Through the introduction of new management schemes and technologies, the project’s strategy aims to assist in the diversification of household income, reduce pressure on rangelands resources, and mitigate the potential for future conflicts over dwindling resources. This will contribute towards the reduction of the proportion of populations classified as vulnerable to climate change impacts on food security. In turn, the project will contribute by way of lessons that can be scaled up to support the achievement of the MDGs, especially MDG 1: Eradicate extreme poverty and hunger and MDG 7: Ensure environmental sustainability.

- This strategy for the adaptation project is rooted in Sudan’s priority needs and challenges identified in the 2007 Country Analysis and subsequently in the UNDAF. It also draws on the Comprehensive Peace Agreement (CPA), Darfur Peace Agreement (DPA), Joint Assessment Mission (JAM), National Strategic Plan (NSP) and others. The project strategy is consistent with the priorities established as part of the Sudan NAPA as well as compatible with national action plans that have been developed as part of multilateral environmental agreements (MEAs) to Combat Desertification and preserve Biological Diversity. Finally, the proposed project is consistent with the goals embedded in Sudan’s Poverty Reduction Strategy, the 5-year Plan (2007-2011), and the UNDP’s Sudan Country Cooperation framework  Bridging Programme (2007-2008) which states: “Capacities in govt. and civil society to manage natural resources for sustainable livelihoods and to meet global environmental commitments strengthened”.

- Moreover, the project strategy is aligned with the UN Development Assistance Framework (UNDAF) principle of environmental sustainability for the period 2007-2011, Objective 2 of the Sudan CCA/UNDAF 2002-2006, climate adaptation priorities outlined in the Sudan INC and SNC to the UNFCCC, and is consistent with guidance for the LDCF (GEF/C.23/18, May 12, 2006). This LCDF project promotes key elements of a programmatic approach to adaptation in Sudan because existing government development interventions that address vulnerability do not account for the additional risks of climate change in their design. The project incorporates this programmatic approach in Outcome 3, which has been designed to ensure institutionalization of lessons learned for both the ALM and for relevant Sudanese government entities.

## Project Goal, Objective, Outcomes and Outputs/activities

- The goal of the project is to enhance Sudan’s resilience and reduce vulnerability to Climate Change impacts. The objective of the project is to implement an urgent set of adaptation measures that will minimize and reverse the food insecurity of small-scale farmers and pastoralists. If the project objective is met successfully, vulnerability of rural communities from increasing climatic variability and climate change is anticipated to reduce.

- The project has a major focus on building resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks. As a contribution to the achievement of the overall goal and primary objective, the project design includes three expected outcomes and expected outputs within the five distinct and non-contiguous locations for project activities. This is summarized in the table below and explained in further detail in the paragraphs that follow.

- In meeting this overall objective, the project focuses on three key areas identified in the Sudan NAPA as urgent and immediate priorities and which are intimately linked to food security, namely: (i) water resource management; (ii) rainfed agricultural production, (iii) rangeland productivity. To achieve the project objective, the following three outcomes will be pursued in the five vulnerable areas identified below.

  - Outcome 1. Resilience of food-production systems and food-insecure communities enhanced in the face of climate change.

  - Outcome 2. Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened

  - Outcome3. A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level

- These outcomes and subsequent outputs is summarized in the table below and explained in further detail in the paragraphs that follow.

| Project Components | Expected Outcomes | Expected Outputs |
| --- | --- | --- |
| 1. On the ground adaptation measures | Resilience of food-production systems and food-insecure communities enhanced in the face of climate change through the implementation of pilot adaptation measures in demonstration sites | Measures, such as such as borehole irrigation, rainfall and water catchment basins to enhance communal water storage systems , water supply and reduce vulnerability to water scarcity (and flash-flood frequency) in the River Nile State, Northern Kordofan State, Gedarif State, Southern Darfur State, and Central Equatoria State Measures, such as modification of livestock size and profile introduced to improve animal production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State Measures, such as introduction of drought resistant varieties and integrated pest management techniques introduced to improve crop production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State Measures, such as re-introduction of stress resistant rangeland seedling varieties introduced to enhance rangelands productivity in the Northern Kordofan State; Gedarif State Measures, such as sand stabilization to combat sand dune encroachment on arable lands in the Northern Kordofan State and Southern Darfur State A village level micro-finance institutions (revolving, risk absorption, livestock fund,) established in target communities to build adaptive capacity and livelihood resilience in Northern Kordofan State |
| 2. Institutional Capacity strengthening | Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened by capacity building to incorporate short term climate change risks into ongoing and future national development planning among local, regional and national NGOs, technical cooperation, Ministry of Agriculture, local governments and communities. | Climate change awareness and risk management integrated into extension programs to strengthen local capacity to address climate risks into livelihood activities. Participatory Early Warning Mechanism designed and tested in the selected pilot regions Local leadership councils and/or Resource Users Association established to facilitate stakeholder engagement and ownership of pilot adaptation projects |
| 3. Knowledge management | A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level by providing important lessons on what does and does not work in improving resilience of vulnerable communities in Sudan to increased climatic variability and climate change | National menu of best practices developed for replication National food security policy prepared on the basis of lessons learned, including budgets for country wide up-scaling Lessons codified and disseminated through the ALM Lessons codified and disseminated throughout Sudanese institutions |

- Outcome 1: Resilience of food-production systems and food-insecure communities enhanced in the face of climate change through  the implementation of pilot adaptation measures in demonstration sites

- Baseline: The proposed project will be implemented at the level of five specific rural areas in each of the vulnerable agro-ecological zones. Changes in temperature and rainfall are likely to lead to desertification in some regions, while in others, flash flooding will increase in frequency and intensity. The country’s inherent vulnerability may best be captured by the fact that food security in Sudan is mainly determined by rainfall, particularly in rural areas, where 70% of the total population lives. Changes in temperature and precipitation could cause shifts in the precarious distribution of these ecological zones, in the productive capacity of rainfed agriculture, and thus, in the security of the nation’s food supply. Additionally, some of the root causes for the growing vulnerability of Sudan’s farmer/pastoralist communities to climate change include ongoing practices that are mal-adapted to increasing climatic variability regarding crop selection, water resource management, communal rangeland management, drought preparedness, and household income generation. In addition to this, there is a lack of awareness, technical capacities and knowledge to make informed decisions.

- Adaptation Alternative: Innovative coping mechanisms and practices with respect to adaptation to climate change risks to food security, e.g. rainwater harvesting, improved irrigation techniques, climate-resilient cropping and grazing systems, livelihood diversification, will be field- tested in 5 high-risks areas. Outcome 1 of the proposed project calls for the implementation of these measures at the level of five (5) specific rural areas, identified as being the hardest hit by recurring food insecurity issues:  1) River Nile state (e.g. areas of lower River Atbara); 2) North Kordofan State (e.g. areas of Bara, Gabrat Alsheikh and Sawdery); 3) Gedarif State (e.g. area. of Butana); 4) South Darfur State (e.g. areas of Shairiah, Muhagriah, Malam, Darbat, Marshung); 5) Central Equatorial State (e.g. area of Juba County).  A major part of this outcome will be the engagement and mobilization of the local communities, as facilitated by the components of Outcome 2. Each of the pilot adaptation projects will engage communities throughout the project cycle; starting from the design of the actual on-the-ground measures, proceeding to implementation activities, and including the development and implementation of community-run monitoring and evaluation schemes to gauge the actual effectiveness of the implemented strategies. A high level of local engagement is critical to ensuring the ongoing viability of the pilot adaptation measures that will be maintained through the duration of the project and thereafter.

Under each of the outputs that follow, (i.e., Outputs 1.1 through 1.6), is a brief description of each of the activities to take place in each of the project locations.

- Output 1.1: Measures, such as borehole irrigation, rainfall and water catchment basins introduced to enhance communal water storage systems, water supply and reduce vulnerability to water scarcity (and flash-flood frequency) in the River Nile State, Northern Kordofan State, Gedarif State, Southern Darfur State, and Central Equatoria State: Communities and their livelihoods are at risk during long periods of drought, and during the flood season. In the communities where the pilot projects are to implemented, water scarcity is increasing. Fluctuation of rainfall and increased frequency of drought have contributed to an increase in crop failure and soil degradation. Output 1.1 addresses these issues through the introduction of small-scale water harvesting techniques, which then allows for the amount of acreage under cultivation to extend and increased availability of water for human and livestock needs. Each of the five specific rural areas chosen for project implementation face unique challenges with respect to water scarcity and storage, and as such their unique project components are explained in the bullet points below by region:

- In the River Nile State, the project includes rapid rural appraisals / feasibility studies to identify/review viable and innovative region-specific water-harvesting techniques (e.g., small water catchment basins, rainfall capture,  groundwater boreholes); design and implement new water harvesting systems to increase potential for small-scale irrigation and animal watering systems

- In the Gedarif State, the project will include rapid rural appraisals / feasibility studies in the 4 communities in the Al Sadda village area to identify/review viable and innovative region-specific water-harvesting techniques (e.g., rainfall capture,  small water catchment basins, groundwater boreholes) that will increase groundwater recharge and reduce soil erosion; in collaboration with project staff, villagers will design and implement new water harvesting systems throughout the study area to increase water availability for human and livestock needs as well as design and implement a water supply/demand monitoring programme to evaluate changes in water availability due to the water harvesting interventions

- In the South Darfur State, the project includes rapid rural appraisals / feasibility studies for several tribes (Dago, Fur, Birgid, Messairia, Zhagawa, Berti and Burnu) in 15 villages to identify/review viable and innovative region-specific water-harvesting techniques (e.g., rainfall capture,  small water catchment basins, groundwater boreholes) to increase groundwater recharge and reduce soil erosion. Villages, in collaboration with project staff, will design and implement new water harvesting systems throughout the study area to increase water availability for human and livestock needs as well as design and implement a water supply/demand monitoring programme to evaluate changes in water availability due to the water harvesting interventions

- In North Kordofan State, the project includes the following activities: a rapid rural appraisals / feasibility study in the Bara area to identify optimal designs for small-scale water borehole-base irrigation schemes and cropping schemes resilient to climate change; design and establish multiple pilot small -scale borehole-irrigation systems in the project area supported by climate change resilient cropping and rotation patterns; design and establish communal and women-managed borehole-irrigation systems in each of the project area’s 15 villages; and the design and implement a water supply monitoring programme to evaluate changes in water availability due to the water supply interventions and improvements in public health from reductions in waterborne diseases.

- In Central Equatoria, the project includes a rapid rural appraisals / feasibility studies in the Kudda, Legge and Tigore communities to identify/review viable and innovative region-specific water supply and treatment methods (e.g., rainfall capture, small water catchment basins, rehabilitation of groundwater boreholes) to increase water capture and availability; and the design and implement new water supply and treatment systems throughout the study area to increase water availability for human needs.

- Output 1.2: Measures, such as modification of livestock size and profile introduced to improve animal production implemented in the River Nile State (RNS) and Southern Darfur State (SDS)

- In the River Nile State, project staff will undertake rapid rural feasibility studies in Khor Elfeel, Salalat, Bali and Shababeet to identify optimal livestock types and husbandry systems in the face of current and future climatic changes and local resource constraint with the objective to increase milk and meat productivity from livestock raised, thereby enhancing food security and livelihood resilience. Given the range of physical, socio-economic, and climate change factors, communities will be aware of the preferred livestock types (species)  and husbandry systems. After the completion of the studies, the project will introduce targeted pilot interventions for improved methods for animal husbandry in Khor Elfeel, Salalat, Bali and Shababeet to support the following: a) improved access to veterinary services, b) a vaccination program to support livestock health (Since the livestock health critical baseline conditions upon which the additional adaptation measures should build on, these will be funded from the government and UNDP co-financing, as part of the project); and c) new animal water hole established in each of the four villages. A region-specific monitoring and evaluation protocol for the installed systems will be designed during project inception, and implemented with the support of local community members.

- In Southern Darfur State, project staff will undertake rapid rural feasibility studies to identify/review viable and innovative region-specific livestock types (e.g. community-based natural resources management, optimal livestock type/number profiles) to build long-term livelihood resilience against climatic shocks. New agricultural techniques and livestock types throughout the study area will be introduced to sustain smallholder farm productivity in the face of climate change. Successful adoption and population increase of new livestock varieties; improved animal varieties and productivity; reduced conflict between farmers and pastoralists. The project will contribute to the development of a robust livestock monitoring and evaluation programme that lays out the range of key indicators to evaluate changes in smallholder farm productivity due to the interventions and to measure how well the systems perform regarding the enhancement of local adaptive capacity.

- Output 1.3: Measures, such as introduction of drought resistant varieties and integrated pest management techniques, introduced to improve crop production implemented in the River Nile State (RNS) and South Darfur State (SDS)

- In the River Nile State, extension services will work with local farmers to establish knowledge and awareness of current climate threats to crops, and results will be used to identify how existing threats will be affected by climate change. Appropriate Sorghum varieties will be tested as an alternative crop that performs under expected climate change conditions including testing of optimal plant density under different soil moisture trials to test for optimum planting time, improved varieties, optimum seeding rate, and pest monitored for productivity enhancements. Project staff will also conduct weed, disease and insect surveys in Adarama, Gadad, Seidon, Baaluk, Abu-sinoon, and Morzoog and use laboratory testing on selected alternative crop varieties to assess performance under range of expected stress conditions (including climate stress) and explore benefits of alternative crop diversification schemes. The project will then introduce new drought-resistant seed varieties into controlled pilot scale field experiments in the communities of Adarama, Gadad, Seidon, Baaluk, Abu-sinoon, and Morzoog to assess in-situ performance with the help of extension workers who can support local farmers in adopting the new varieties. The adoption of drought-resistant crop varieties and improved awareness of climate threats will enable communities to effectively plan to adapt- rather than the most costly reactive post-disaster recovery. The services of specialised agencies such as the Food and Agriculture Organization and/or others are likely to be solicited, under conditions to be determined during project implementation, for technical backstopping.

- In Southern Darfur State, extension services will work with local farmers to improved knowledge and awareness of current threats to crops, results used to identify how existing threats will be affected by climate change. The initial part of the project involves a feasibility study to identify/review viable and innovative region-specific agricultural techniques e.g., drought resistant seeds, integrated pest management, community-based natural resources management to build long-term livelihood resilience against anticipated climatic shocks. Once these have been identified, extension workers will work with local farmers to implement appropriate agricultural techniques that are likely to be effective under conditions of climate change. Funds will be used to also design and implement an agricultural monitoring programme to evaluate changes in smallholder farm productivity due to the interventions.  Successful adoption of new crop varieties and techniques can contribute to reduced conflict between farmers and pastoralists and ultimately, the widespread adoption of new techniques and climate-resilient species can be considered a planned adaptation strategy.

- Output 1.4: Measures, such as re-introduction of stress resistant rangeland seedling varieties introduced to enhance rangelands productivity in the Northern Kordofan State (NKS), Gedarif State (GS)

- In Northern Kordofan State, over the past several decades livelihoods have been adversely affected by frequent drought cycles.  Severe climatic conditions and land mismanagement (overgrazing, over-cropping, and deforestation) have caused vegetation cover in the region to became very poor and the loss of many endemic species (woody, rangeland species) that were once dominant. Current rangeland management systems are ill-suited to changing climatic conditions (as evidenced by historical livelihood loss after extreme weather events like droughts and floods) and contribute to communal land degradation. There is, for example, no fenced area for communal grazing which contributes to resource conflicts between herders and farmers.  The project will conduct a feasibility study for the 15 communities in the Bara area to identify rangeland rehabilitation and management systems most resilient to projected climatic stresses and variability. Funds will be used to identify suitable sites in the region as well as necessary interventions to ensure that anticipated pressures that are otherwise likely to manifest under climate change will be minimal. Once suitable sites have been identified among the 15 communities, the project will set up and/or support a central nursery in a central location in the Bara area to conduct testing on rangeland seedling varieties and shrub/tree varieties to assess performance under range of expected climatic stress conditions. As part of Output 2.1, which supports this output in NKS, training will be provided for local peoples to manage their natural resources under conditions of climate change and to supports the different activities of the project including implement a resilient rangeland management system through establishment of a fenced communal grazing allotment over a 25 square km area supported by range of feasibility study recommendations (e.g., fodder rotation systems, new groundwater supply, new drought-resistant seedlings/trees, etc). Finally, once output 2.3 has led to the establishment of local national resource leadership councils, (see the output 2.3.) communal grazing area will be established to ensure resilience of rangelands to both support livelihood activities and self-regenerate after periods of drought and flooding.  Community members will also be engaged in the design and implementation of a rangeland monitoring programme to evaluate changes in pasture availability due to the interventions.

- In Gedarif State, most of the population in the project area depends on pastoralism and raise cattle, goats, sheep and camels. Transhumance pastoralists also live in the area and number roughly 16,000 pastoralists (excluding families).  The density of  the livestock population approaches 2 million during the rainy season. Due to deteriorated range resources, overgrazing is leading towards adverse impacts on range resources including frequency of conflicts. Loss of palatable range species is occurring. Traditional coping mechanisms including selling of animals and changing the herd composition are no longer viable temporary measures of relief. The project will finance a feasibility study to identify optimal agricultural production schemes (e.g., fodder crops, vegetables, fruit trees) resilient to climate change in the project area. Once the range of options has been identified, they will be piloted. Likely solutions with longer-term benefits for communities, in the context of reducing climate change pressures include small-scale integrated fodder management systems for bio-fertilizer production, irrigated fodder production, and bailing/storage. The eventual systems to be put in place will be supported by a community-designed fodder management monitoring programme that will evaluate changes in fodder management practices and effect on conflicts between seasonal and sedentary grazing communities. Other potential solutions are also likely to become evident as the results of the feasibility assessment become available.

- Output 1.5: Measures, such as sand stabilization to combat sand dune encroachment on arable lands in the Northern Kordofan State (NKS) and Southern Darfur State (SDS)

- In Northern Kordofan State, land degradation and desertification and the ongoing (and future) impact of climatic change threaten the people’s abilities for sustainable resource management and food security. Severe climatic conditions and land mismanagement (over grazing, overcropping, deforestation) have caused vegetation cover in the region to become very poor and the loss of many endemic species (woody, rangeland species) that were once dominant. Furthermore, as the region is bordering the desert zone, there is a persistent threat associated with shifting sand dunes and desertification. The area chosen for pilot project implementation is already moderately affected by desertification and suffers from deforestation due to unrestricted grazing and unrestricted biomass use. To control dune movement, the project will preserve local forested areas by establishing community-based grazing allotments, find and implement viable options to reduce dependency on biomass. For example, the project will introduce alternatives to the use of biomass for building construction materials, e.g. mud, bricks etc through several pilot structures. Additionally, policies in place that allocate land for grazing and separate land for forests such that no forest cover is lost from the baseline by the end of the project implementation period. This is an output that will be financed largely co-financing.

- In Southern Darfur State, rangelands are considered as traditional rainy season grazing for transhumance pastoralists. Rangeland degradation is widely evident due to poor management practices as evidenced by loss of biodiversity, as several desirable species had disappeared. Tree felling is also widely practiced due to poverty and fuel wood and charcoal demand, which leads to soil erosion in times of flooding. The project will preserve local forested areas by rehabilitation of the Gum Arabic belt through re-cultivation of Hashab trees (Acacia Senegal); and rehabilitate rangelands by seeding communal rangelands with drought-resistant varieties and implement communal rangeland management schemes (e.g., fodder rotation, exclusion zones);

- Output 1.6: A village level micro-finance institutions (revolving, risk absorption, livestock fund) established in target communities to build adaptive capacity and livelihood resilience in Northern Kordofan State: This output is based on a successful practice introduced by the UNDP-GEF project (1992-2000) on Community-Based Rangeland Rehabilitation for Carbon Sequestration in North Kordofan. For the NAPA follow-up project, the idea is to build on already existing MFIs and establish a number of village-level, local shock absorption, revolving funds, up to one in each of the target villages with well trained management committees and a total fund capitalization of approximately $50,000. The aim of these revolving funds is to provide household access to credit, particularly to households headed by women, for the same pilot adaptation measures that have been introduced at the community scales and which can be readily scaled to the household level. Under this output the project will establish small scale shock absorption, revolving funds to provide credits for activities and community initiatives and services centers (agriculture, animal health, human health and others). To best identify the adaptive practices/technologies for local agricultural activities that are viable investments, the project will first undertake a feasibility study to identify optimal socio-economic strategies for crop and livestock management in the face of increasing climatic variability and climate change. Once adaptation options for the pilot area have been identified a MFI to promote local investment in adaptive options, including a livestock component of the revolving micro-credit fund to promote transitioning to more resilient livestock systems. The project will explore and test the options for utilizing MFIs for risk absorption and transfer mechanisms based on rainfall gauges to design transparent and flexible contracts for farmers for index insurance as a means of removing the risks of rainfall deficits. This will be done by carefully studying and customizing successful cases in Ethiopia, Tanzania and Kenya supported by International Research Institute for Climate and Society (Columbia University). The portfolios and service functions of small scale, village level MFIs will be designed based on the current conditions, needs and feasibility assessments

- Outcome 2: Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened by capacity building to incorporate short term climate change risks into ongoing and future national development planning among local, regional and national NGOs, technical cooperation, Ministry of Agriculture, local governments and communities.

- Baseline: Climate change adaptation and risk management in Sudan are not currently practiced at a level that is commensurate with the risks posed by increasing climate variability and climate change in the vulnerable regions identified above. Local populations have existing coping mechanisms and the capacity to adapt to climate variability within the range of what humans have been experiencing for millennia.  Therefore, it can be said that some autonomous adaptation is taking place. Local communities, however, have limited capacity and resources to adapt to climate change induced variability. While there are national early warning systems (EWS) in some of the institutions that provide warnings regarding the food security situation, droughts, floods, epidemics, fires and emergencies, these systems lack the robustness and the integration needed for forecasting and addressing looming food security threats on a real-time basis. There is an urgent need to upgrade the existing adaptive capacity so that they could effectively inform, and alert local communities on the expected climate and food security situations and recommend effective coping strategies and measures.

- Adaptation Alternative: In contrast to the current situation where no local, regional and national entities have the capacity to adequately integrate climate change risks into policy and programming, under this Outcome, this institutional gap will be addressed at various levels such that relevant agencies’ and stakeholders’ awareness of climate change risks are enhanced and incorporated into development plans as well as skill sets for climate change risk management improved, especially as relate to food security. Particular attention will be paid to the extension programmes and services that may play a pivotal role in decentralised and locally customized advice and support to local communities in their efforts to build stronger resilience of their food production systems to the increasing climate variability and long term change. While there are national early warning systems (EWS) in some of the institutions that provide warnings regarding the food security situation, droughts, floods, epidemics, fires and emergencies, these systems lack the robustness and the integration needed for forecasting and addressing looming food security threats on a real-time basis. There is an urgent need to upgrade the existing EWS so that they could effectively inform, and alert local communities on the expected climate and food security situations and recommend effective coping strategies and measures. Building institutional and individual capacity to address some of the urgent adaptation needs will improve the link between adaptation and national policymaking, as well as ensure policies are supportive of cooperation and participation in adaptation activities that account for the special needs of local communities. As detailed in the outputs below, this outcome includes training of government staff (including agricultural extension support services), local farmers and pastoralist and demonstration activities on how to use climate information in the design and management of crop production, livestock and rural livelihoods. Training programs will focus on the introduction of a number of tools for incorporating adaptation concerns into provincial/community development and risks management plans. In addition to capacity building trainings, awareness raising workshops for climate change risks and needs pertaining to agriculture, water and rural development improved for policy makers and local communities will be held as a second mechanism to ensure that key adaptation concerns mainstreamed into relevant policies. This outcome includes the development of training and other materials suitable for local communities to support of regional project objectives (e.g., for building awareness of climate change in the context of local productive activities and livelihoods). Specific outputs associated with this outcome include:

- Output 2.1. Climate change awareness and risk management integrated into extension programs to strengthen local capacity to address climate risks into livelihood activities in five vulnerable areas

This output involves undertake intensive capacity-building interventions as an investment in human capital within entities responsible for implementing the on-the-ground adaptation measures, thus producing a viable capacity to adapt to climate change and specifically to the risks due to food insecurity. The components described below will enhance the capacity of technical staff/extension workers, pastoralists and farmers to design and implement priority adaptation measures as outlined in Outcome 1 e.g. water harvesting techniques, water planning and management based on available climate information, reseeding of the rangeland with heat-resistant varieties of grass and legume species, introduction of new crop systems and practices more appropriate in changing climatic conditions.  Awareness of pastoralists, farmers, and women will be enhanced of climate risks and adaptation options through active and informed participation by community members in the proposed pilot adaptation strategies as outlined under Outcome 1. Increased awareness will contribute to the sustainability and replicability of the project by building capacity and creating a sense of ownership for community members. Key components for each of the five areas include the following:

- Train pastoralists and local communities on the storage, utilization and management of natural resources, specifically of water and communal fodder management schemes.

- Involve farmers and pastoralists in pilot scale crop and livestock activities indicated under Outcome 1 to demonstrate new techniques and raise awareness regarding integrating climate risks into productive activities;

- Train extension workers on climate proofing and adaptive techniques for pastoralists, farmers, and women in local communities to assist them in managing their natural resources and support the various activities of the project.

Under this outcome the project will synthesise all existing and generated knowledge from local pilots to improve the county’s policy and institutional framework for food security. This largely bottom-up and decentralised approach has proven a well tested method for succeeding in Sudan.

- Output 2.2 Participatory Early Warning mechanism designed and tested in the selected pilot regions.

Local risk detection mechanisms will be designed with participation of local communities, farmers and pastoralists, to identify and reinforce indigenous knowledge of risk detection. This will be matched with the improved early warning mechanism based on the improved methods of forecasting. For example, real time rainfall estimation methods will be introduced to improve flood and drought warnings and responses. There is already an extensive experience with Early Warning and Response systems in Sudan in relation to diseases, conflicts, fires and floods. The project will build on the existing practices and early detection networks to improve EWS to food security as relate to climate variabilities. In so doing the project will work closely with extension services, Higher Council for Environment and Natural Resources, the Ministry of Irrigation and other relevant organisations to create an improved understanding of the enabling conditions needed for different actors to implement recommendations and guidance under the constraints of their daily work such as limited financial and human capacity, conflicting demands by donors and end users, and divergence in organisational agendas of different stakeholders.

- Output 2.3. Local leadership councils and/or Resource User Associations established to facilitate stakeholder engagement and ownership of pilot adaptation projects.

Stakeholders in each of the five vulnerable regions have expressed their readiness to participate in the implementation and monitoring of the adaptation pilot projects in their communities.  A common example of communal resource over use and the need for the establishment of local leadership councils can be evidenced by the case of South Darfur state where tree felling is widely practiced due to poverty and fuel wood and charcoal demand, such that communal forestry and rangeland management (currently non-existent) needs to be introduced to combat desertification. In response to this natural resource management gap, output 2.3 involves the development of local leadership council made up of selected representatives from each community for decision-making, coordination of activities, and organization of local labor inputs for climate risk management and adaptation options. Such leadership councils will represent a multistakeholder coordination, interest group engagement and wide consensus building platform. The ambition of the project is to test such local leadership and participation arrangement, make it a home-grown institutional mechanism for participatory local planning and decision-making. The project will strive to institutionalise such mechanisms (in certain provinces they already exist informally) and make the national authorities recognise the institutional legitimacy and validity of the decisions made by these councils. Key components in each of the five areas include the following:

- In the River Nile State, the project will help form a functional local stakeholder group to be engaged in decision-making and project activity support.

- In the Gedarif State, the project will help form a local leadership council made up of selected representatives from each community for decision-making, coordination of activities, and organization of local labor inputs.

- In the South Darfur State, the project will help establish local, forest management councils that can help to combat desertification by overseeing communal forestry and rangeland management structures, and engaging stakeholders in the adoption of sustainable management practices that are viable in the face of climate change.

- In North Kordofan State, the project will help form a local Resource Users Association made up of selected representatives from each community for decision-making, coordination of activities, and organization of local labor inputs.

- In Central Equatoria, the project will help form local leadership council made up of selected representatives from each community for decision-making, coordination of activities, and organization of local labor inputs.

- Outcome 3: A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level by providing important lessons on what does and does not work in improving resilience of vulnerable communities in Sudan to increased climatic variability and climate change

- Baseline: No system is in place to date to systematically address the effectiveness of adaptation measures introduced to build resilience against food insecurity.  Lack of attention to this issues as well as lack of political involvement means that knowledge capture institutional integration, and transfer across vulnerable zones/sectors is little to none. A systematic compilation of experiences is a pre-requisite to successful adaptation strategies including the key components of horizontal and vertical knowledge transfer.

- Adaptation Alternative: This outcome aims to ensure that the implementation of project activities and subsequent M&E reports provide important lessons on what does and does not work in improving resilience of vulnerable communities in Sudan to increased climatic variability and climate change.  The systematic compilation of these lessons will form a crucial input to informing Sudan’s plans and strategies to adapt to climate change over the coming years. The project, with the financial support of the LDCF, will play a pivotal role in involving relevant stakeholders, enhancing local knowledge and capacities, which will in turn enable Sudan to scale up and replicate these interventions. This knowledge management component will be implemented in close synergy with the UNDP ‘’Adaptation Learning Mechanism’’ initiative (ALM).  The project will provide valuable inputs to the ALM and will also benefit from the knowledge and best practices generated through this international platform. Consultations and lessons-learned synthesis will begin early in year three (3) in order to be finalized by end of project. Specific outputs associated with this outcome include:

- Output 3.1. National menu of best practices available for replication: Through the consultation of stakeholder and documentation of lessons learned and emerging understanding of best practices, synthesized project results will be made available in a technical report that identifies successful pilot adaptation measures and proposes additional strategies that build off project activities, further reduce local vulnerability to climate change and can be applied elsewhere in the country.

- Output 3.2. Preparation of a national adaptation policy, including budgets for country-wide up-scaling. Successful pilot mechanisms and measures will be institutionalized through preparation a national adaptation action policy that that distils and mainstreams the lesson- learned reports for each of the project sites into a specific set of policy, legislative, and regulatory initiatives. As a result, the national food security policy will take full account of climate change risks and accommodate successful adaptation measures demonstrated by the project as part of the national food security policy.

- Output 3.3: Lessons codified and disseminated through the ALM:  A knowledge management plan to capture lessons learned regarding the implementation of pilot projects (Outcome 1), and effective capacity building training and workshops (Outcome 2), as well as best practices on community-based adaptation in farming and pastoralists system to achieve greater food security will be formulated. The objective of the knowledge management plan is to disseminate lessons to relevant stakeholders on the national and international levels. Towards this end, linkages to UNDP-GEF’s Adaptation Learning Mechanism will be established

- Output 3.4. Lessons codified and disseminated throughout Sudanese Institutions: This output involves the development of a program to build awareness within Sudanese institutions regarding emerging lessons from the application of the pilot adaptation measures in the five proposed sites. The objective of the knowledge management plan is to disseminate lessons to relevant governmental stakeholders responsible for national policies regarding food security and rural livelihood activities.

## Project Indicators, Risks and Assumptions

- At the national level, a strong commitment from the Sudan government limits the likely risks to the proposed project. The major risks are that this commitment is not carried through because of the different perceptions of key decision makers, or that the project does not result in a long-term commitment and strategy to address climate change adaptation for the vulnerable sectors in an integrated and effective manner. However, the commitment to baseline development activities implemented by government, as well as its efforts to secure the necessary co-financing, has served to minimize these risks.

- At the regional level, the major risk that might prevent the project objective(s) from being achieved is the lack of cooperation from local stakeholders in each of the five project areas. The project will require substantial inputs in the form of oversight, consultation, participation in activities within government agencies, NGOs and communities. Relative to this GEF/LDCF project, this risk is likely to be minimized by the strong endorsement received by local authorities during the project preparation scoping missions and the recognition that this project is an opportunity to catalyze additional development programmes and projects that may further reduce risks from a changing climate.

## Additional Cost Reasoning and expected national and local benefits

- Without GEF/LDCF scenario (baseline): As described above, the Government of Sudan, in partnership with several donor organizations, is already in the process of implementing several development projects to improve food security conditions. National efforts to improve food security, however, do not systematically integrate the additional risks of increased climate change, including climate variability. These investments include stimulating rural economies by providing basic infrastructure, market access, and developing technical as well administrative capacity in rural areas. Moreover, efforts are also underway to improve agricultural productivity by implementing soil conservation and water harvesting measures in large-scale agricultural schemes and providing alternative water sources for rural communities. These are both ongoing and proposed investments that represent baseline conditions that need to be supplemented to account for the additional risks posed by climate change.  The GEF/LDCF intervention is essential to ensure that climate change concerns are addressed in the context of rural development and food security interventions in Sudan. Fully in line with the LDCF guidelines the proposed project is to cover the adaptation related cost by building upon the baseline programmes and investments.

- The proposed project will, with financial assistance from the LDCF, address these additional risks and raise the adaptive capacity of rural communities, rendering them less vulnerable to climatically induced food insecurity. The priority measures that have emerged from the NAPA consultation for improving food security in the face of climate change include improved water harvesting techniques, heat resistant plant varieties, new commercial crops, improved small-scale irrigation techniques, wind barriers, intensification of trees planting along irrigation channels, rehabilitation of vegetation cover and communal rangelands for enhancing livestock resilience. The potential efficacy of such measures to reduce rural livelihood vulnerability has been validated by the NAPA stakeholder consultations undertaken over a broad cross-section of Sudan’s ecological zones, and which specifically engaged stakeholders in areas determined to be highly vulnerable to recurrent climatic shocks.

- By funding the additional costs of interventions necessary to meet the urgent and immediate adaptation needs identified in the Sudan NAPA, the project will increase the resilience to climate of key productive activities through enhancing the ability of small farmers and pastoralists to cope with increasing climate variability.  Through the introduction of new water management schemes and drought and flood resistant agricultural practices, it will aid in the diversification of household income, promote climate-proof cropping systems, reduce pressure on rangelands resources, and mitigate the potential for future conflicts over dwindling resources.

- The project will also generate adaptation benefits by ensuring the risks associated with climate change, including variability, are integrated into key development plans and practices at the community, biam (county), and national levels.  By integrating this project’s emphasis on addressing additional risks due to climate change into programmes and activities that promote baseline development needs in the agriculture, the GEF and UNDP will play an important role in catalyzing and assisting Sudan achieve and maintain MDG targets in poverty reduction and food security.

- The project, with the financial support of the LDCF, will play a pivotal role in involving relevant stakeholders, enhancing local knowledge and capacities, which will in turn enable Sudan to scale up and replicate these interventions. This knowledge management component will be implemented in close synergy with the UNDP ‘’Adaptation Learning Mechanism’’ initiative (ALM).  The project will provide valuable inputs to the ALM and will also benefit from the knowledge and best practices generated through this international platform.

- The outcomes and relevant activities described above involve additional, climate related initiatives, and will be supported by UNDP in terms of technical support.  The NAPA project profiles that underpin the outcomes of this proposal will be assessed, evaluated and a plan for implementation formulated during the preparatory (PPG) phase. Additional activities necessary to ensure the sustainability of some of the proposed interventions, including those that focus on management and technical capacity will be identified and incorporated in the project design. The additional cost reasoning provided by the LDCF programming guidelines will also be used to design and cost the interventions.

- It is clear that in the absence of the proposed project, there are expected to be no lessons learned or emerging understanding of best practices and/or national scale-up issues. With the financial support of the LDCF, the project can play a pivotal role in involving relevant stakeholders, enhancing local knowledge and capacities, which will in turn enable Sudan to scale up and replicate these interventions.

## Country Ownership: Country Eligibility and Country Drivenness

- The Government of Sudan ratified the UNFCCC on November 1993. Sudan fulfilled its commitment under the UNFCCC by submitting its Initial National Communication (INC) in February 2003 and NAPA in July 2007. The INC process included climate change climate change vulnerability studies in three priority socio-economic sectors including agriculture, water resource management, and public health, with a particular focus on vulnerable groups in distinct ecological zones in urgent need of adaptation activities. The NAPA process identified 32 priority adaptation initiatives in the agriculture, water and health sectors to reduce the increasing vulnerability of the rural communities to current and future climatic risks.  The efficacy of these measures has already been validated by stakeholders in areas determined to be highly vulnerable to recurrent climatic shocks. There are also a number of Governmental programmes and policies containing measures to address the root causes of growing rural vulnerability. In addition, the Government of Sudan has made a significant commitment to the achievement of the Millennium Development Goals (MDGs) and their related targets by 2015.

- The Higher Council for Environment and Natural Resources (HCENR) is the leading agency in the oversight and implementation of the proposed project.  HCENR is the technical arm of the Ministry of Environment and Physical Development, in the area of policies, legislation and strategic planning in relation to environmental and natural resources conservation and management. HCENR is the government coordinating body concerned with integration of environment into national development. HCENR is the focal point of many MEAs including Rio conventions.  HCENR works in close collaboration with all government institutions at both the federal and States level. The project institutional arrangements and management plan will be further investigated and nailed down during the PPG phase, in close consultation with all relevant stakeholders.

- The HCENR coordinated the first climate change-related activities in Sudan, Sudan’s First National Communication under the UNFCCC, a multi-year effort to develop the country’s first greenhouse gas inventory, an initial assessment of the vulnerability of water resources, agriculture, and public health to climate change; and an analysis of greenhouse gas mitigation strategies. (1998-2003).

- The Sudan NAPA identified agriculture, water and health as the highest priority sectors where urgent and immediate action is needed. Submitted to the UNFCCC in July 2007, the NAPA identified urgent adaptation initiatives in these sectors to reduce the increasing vulnerability of the rural communities to current and future climatic risks. Consistent with guidance for the LDCF (GEF/C.28/18, 2006), the NAPA process also yielded a consensus that the highest priority NAPA follow-up interventions should be a programme of adaptation-focused interventions in five distinct areas with a major focus on the enhancement of food security by building the adaptive capacities of the rural population, particularly of rainfed farm and pastoral communities. The project is also aligned with funds earmarked for strengthening local adaptive capacity, institutions and policies for managing climate related threats and for financing pilot demonstration activities.

## Sustainability

- Sustainability has been an important part of project design from its inception. Sustainability means the ongoing, development and expansion of the project activities after the LDCF project support has phased out and project duration is over. The essential parties responsible for project sustainability include: the State-level Ministries of Agriculture, Animal Wealth and Irrigation, the State Ministry of Finance and Economic Development, state credit institutions (agricultural bank, farmers bank), small finance corporation, community revolving funds bodies, donors, locality government authorities, beneficiaries and other bodies and partners.

- Each of the five sites has a specific approach to sustainability that reflects the site-specific contexts in which the project will be implemented. At the local level, project sustainability requires technical backstopping at the level of the locality that is administrated by the extension and community development team. Sustainability can be ensured through capacity building workshops that give extension workers and local community members the tools to address climate risks in daily life, and supporting community management of natural resources to encourage replication of successful activities.  The involvement of extension administration and local community leaders from project inception will help to ensure that maintenance of the adaptation sites are sustained beyond the project end date and encourage replication of these successful activities.

## Replicability

- By its simultaneous focus on enhancing food security, improving rural household livelihoods, lowering climate risks, and implementing appropriate location-specific, adaptation measures, the project brings together the crucial elements needed for both targeted effectiveness and potential replicability. Scripted into each project are strategies for documenting lessons learned, and training workshops and programs- once established- can easily be transferred to other locations.

- Extension of similar project to other locations will be done primarily by the State Government in collaboration with vulnerable groups. For example, in southern Darfur, the State’s 5-year development plan already includes the replication of NAPA follow-up project activities in different locations. Each of the five areas’ replicability strategy is also summarized in Annex A.

- The third outcome of the NAPA follow-up project is a better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level. The lessons learned are targeted for contribution to UNDP’s Adaptation Learning Mechanism where knowledge can be shared both internally within Sudan and externally for replication in other countries and areas should the implemented strategies prove successful.

Part III: Management Arrangements

### Implementing Agency

- The United Nations Development Program (UNDP) will be the Implementing Agency for the project. The UNDP is well positioned to assist Sudan in design and implementation of the project. UNDP will support coordination efforts to implement climate risk management activities at various levels including at the community and relevant national and sub-national institutions. UN Support will be in the areas of food security, sustainable agriculture, water harvesting, and natural resources management.

- The NAPA follow-up proposal builds on UNDP’s existing in-country strategy elaborated in its 2002-2006 Country Cooperation Framework and  Common Country Assessment (CCA). The proposed project is aligned with UNDP’s comparative advantage in improving capacity building, providing technical and policy support as well as expertise in project design and implementation in relevant are such as sustainable land management and water governance at the global level and in Sudan in particular. Through its network of technical staff, in additional to operational expertise in designing similar GEF Council approved projects in arid regions of Africa (Niger, Burkina Faso, Kenya, Mozambique, Zimbabwe and Ethiopia), UNDP is well positioned to assist Sudan to provide oversight support during the implementation of the project.

- UNDP is able to draw on its experience of conducting almost all the NAPA processes in the Arab and sub-Saharan Africa and on the technical assistance from the Drylands Development Centre (DDC), which specializes in assisting countries to fight poverty and encourage development in the drier parts of the world, as well as the Water Governance Facility, which specializes in helping countries to mainstream environmental concerns into national planning frameworks with a special focus on dryland issues.

## Executing Arrangements

- The Higher Council for Environment and Natural Resources (HCENR) will be the main executing agency, or implementing partner, of this project during the implementation phase. The HCENR is the technical arm of Sudan’s Ministry of Environment and Physical Development and is the government coordinating body concerned with integrating the environment into national development activities. The HCENR is the focal point of many MEAs, including Rio conventions, and works closely with federal and state level government institutions.

- At the regional level, where project activities will be implemented across 5 distinct locations, the HCENR will set up cooperative arrangements with the specific national institutions that have been identified and recruited during the project preparatory phase to be the main implementing partner for all activities. The respective state-level Ministry of Agriculture, Animal Resources and Irrigation will serve in this role for project activities in the Nile River State, Northern Kordofan State, Gedarif State, and Southern Darfur State. For Central Equatorial State, a comparable state-level institution – the Ministry of Agriculture, Forestry, Animal Resources and Fisheries – will serve this role.

## National and regional level project management and coordination

- Project Steering Committee:  A Project Steering Committee (PSC) will oversee the implementation of project and make any needed adjustments (in line with UNDP Rules and Regulations) to achieve project objectives and milestones. The PSC is responsible for ensuring coordination and that feedback take place on a regular basis to identify, and recommend any adjustments to project activities. It will also ensure that approaches adopted for complementary activities are consistent with the technical feasibility of the project and the realization of project benefits from the perspective of project beneficiaries.  The PSC should be constituted with key national stakeholders from the Ministry of the Environment and Physical Development, the HCENR, the Ministry of Agriculture, Animal Resources and Irrigation, the Sudanese Environment Conservation Society, the Ministry of Health, the Planning Administration within the Ministry of Finance, and the Range and Pasture Administration. Other GEF Implementing Agencies and Executing Agencies will also be consulted.

- Project Manager:  A Project Manager (PM) will be recruited to manage the overall project and coordinate the implementation of all regional activities. The PM is appointed by the PSC and will have the authority to run the project on a day-to-day basis on behalf of the PSC within the constraints laid down by the PSC.  When management tolerances (i.e. constraints normally in terms of time and budget) have been exceeded, the PC consults the PSC for decisions.

- Regional Project Coordinators: Five Regional Project Coordinators (RPC) will be recruited to manage the implementation of regional activities. The RPCs are nominated by the PC based on a transparent professional recruitment process (following UNDP procedures) submitted to the PSC for review and approval. The RPCs will report directly to the PC and will have the responsibility to run the regional components of project on a day-to-day basis on behalf of the PC within the constraints laid down by the PC.

- The above project management structure can be illustrated as follows:

## Collaborative arrangements with related projects

- This project is aligned with priorities in Sudan’s Initial National Communication as well as consistent with planned activities in its Second National Communication (SNC), which is currently under preparation. The proposed project has direct linkages to NAPA findings regarding the integration of climate risks into productive activities in Sudan, reducing the impact of climate change vulnerability in priority sectors especially in water sector and agriculture sub-sectors, and the building of adaptive capacity in livelihood diversification opportunities.

- In addition to the Ministry of the Environment and Physical Development and the HCENR which will serve in implementation capacities, the project concept has been discussed at length with key stakeholder entities in the Government of Sudan (i.e., Ministry of Finance and Economic Planning, Ministry of Health, Ministry of International Cooperation) as well as with regional administrations (i.e., Excellencies the Walis and the State Ministries of the River Nile, El Gedarif, South Darfur, North Kordofan and Central Equatorial States), and the beneficiary communities, various research and academic institutions, and UNDP country office and other UN agencies, donors and NGOs involved in NAPA and project preparation activities.

- The adaptation activities will be undertaken in close syngery with the National Council for Strategic Planning, which coordinates development efforts in a 5-year plan (2007-2011), builds on the 2004 Comprehensive Peace Agreement, the Country Programme Docment 2009-2012, and is closely aligned to the 2008-2011 Agriculture Revival Plan (ARP). The NAPA identified 10 key adaptation needs in the agricultural sector all of which are well accounted for in the agricultural revival programme. One of the major outcomes of the CPD is poverty reduced by 2012 and increased equitable economic growth through improvement in livelihood, food security, sustainable natural resources management and self reliance. This outcome is also a strategic objective in the ARP. Much if not all of the programmes included in the ARP support and fulfil CPD, MDG, and NAPA objectives.

- Opportunities to make the best use of complementary resources and technical capacity will be explored with the relevant stakeholders. Capacity building activities and backstopping that are relevant to this proposed project and other related projects will be identified and designed jointly, including a strategy for training in common areas. Lessons learned in the process of implementation will be shared as a mechanism to learn from each other. UNDP continues to work in close collaboration with the governments of North and South Sudan; however, capacity constraints within the GoNU and GoSS institution significantly affected program efficiency. Past experience shows the importance of continued efforts to enhance the institutional and human capacity of the government and public sector in Sudan.

- Opportunities for UN joint programming were also identified in the development process of the CPAP. For UNDP, the most immediate opportunities identified are in the field of support to the achievement of the MDGs, notably through private sector development, as well as conflict prevention and peace building.

- Moreover, there are a number of ongoing Governmental programmes and policies containing measures that can be considered to have a facilitating link with adequate adaptation to climate change in several socio-economic sectors. Some of these initiatives are listed below:

- The Government has formulated its approach to sustainable development through a recently completed 25-year Comprehensive National Strategy Outline;

- Major portions of Sudan’s Interim Poverty Reduction Strategy Paper (IPRSP, 2004-2009) focus on agriculture, water resources, and public health—the same sectors identified by the NAPA process. The IPRSP of the Government of the state of Sudan is an important document which creates synergy of adaptation to CC to all vulnerable livelihoods of poverty in the country;

- At the State level, many Environmental Councils have been established. By virtue of the broad NAPA consultation process, many of these councils have recently begun to formally proposed potential adaptation measures in their sectoral policy discussions;

- Sudan has a long experience in combating desertification, which is the major environmental challenge in the State, and Sudan was one of the first States to sign and ratify the UNCCD.  Sudan’s National Action Plan for the UNCCD contains project profiles which are case activity for synergy to adaptation to CC;

- The NBSAP of CBD, finalized in May 2000, has major goal of the overall biodiversity of Sudan restored, conserved and managed so that it provides environmental services & natural resources that contribute to sustainable & socially-fair national economic development. Many biodiversity interventions recognize the role of climate variability, such as drought spells and fluctuations in rainfall and temperature, in loss of diversity and complete crop failure;

- There are a number of research institutions that address environmental problems in their area of interest, though they need institutional strength & human capacity development;

- A number of the governmental institutions have established environmental units

## PART IV: Monitoring and Evaluation Plan and Budget

- Results-based management mechanisms will be systematically integrated into the management of the project. In this context, the Results and Resource Framework (RRF) has been agreed with the government and other key stakeholders. The UNDP Country Office’s evaluation plan is in line with the UNDAF monitoring and evaluation plan. The latter include key outcome, mid-term and end-term evaluations in close collaboration with government and other stakeholders. To the extent possible, data will be gender disaggregated.

- UNDP will closely monitor the critical risks which may affect the country programme results, including any uncertain political situations or political decisions affecting the implementation of the CPA and other peace agreements, particularly in the Southern Darfur regional project component. The risk mitigation strategies will focus on strengthening communication with national counterparts; enhancing national and UNDP capacities to rapidly respond to political changes.

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures and will be provided by the project team and the UNDP Country Office (UNDP-CO) with support from UNDP/GEF.  The Results and Resources Framework provides performance and impact indicators for project implementation along with their corresponding means of verification. These will form the basis on which the project's Monitoring and Evaluation system will be built.

- The following sections outline the principle components of the Monitoring and Evaluation Plan and indicative cost estimates related to M&E activities. The project's Monitoring and Evaluation Plan will be presented and finalized at the Project's Inception Report following a collective fine-tuning of indicators, means of verification, and the full definition of project staff M&E responsibilities.

Monitoring and Reporting

- A Project Inception Workshop will be conducted with the full project team, relevant government counterparts, co-financing partners, the UNDP-CO and representation from the UNDP-GEF Regional Coordinating Unit, as well as UNDP-GEF (HQs) as appropriate. The objective of the Inception Workshop is to assist the project team to understand and take ownership of the project’s goals and objectives, as well as finalize preparation of the project's first annual work plan on the basis of the project's results and resources framework (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise finalize the Annual Work Plan (AWP) with precise and measurable performance indicators, and in a manner consistent with the expected outcomes for the project.

- Other objectives of the Inception Workshop are to: (i) introduce project staff with the UNDP-GEF expanded team (i.e., PC and RPCs) which will support the project during its implementation, namely the CO and responsible Regional Coordinating Unit staff; (ii) detail the roles, support services and complementary responsibilities of UNDP-CO vis à vis the project team; (iii) provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the Annual Project Implementation Reviews (PIRs) and related documentation, the Annual Project Report (APR), Tripartite Review Meetings, as well as mid-term and final evaluations. Equally, the Inception Workshop will provide an opportunity to inform the project team on UNDP project related budgetary planning, budget reviews, and mandatory budget revisions.

- Monitoring responsibilities and events will be outlined early in the project through email or other correspondence. A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for Tripartite Reviews, Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities.

- Day to day monitoring of implementation progress in the five project locations will be the responsibility of the PC, in coordination with the RPCs, and based on the project's Annual Work Plan and its indicators. The Project Team will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The Project Manager and the Project GEF Technical Advisor will fine-tune the progress and performance/impact indicators of the project in consultation with the full project team at the Inception Workshop with support from UNDP-CO and assisted by the UNDP-GEF Regional Coordinating Unit. Specific targets for the first year implementation progress indicators together with their means of verification will be developed at this Workshop. The regional implementing institutions will also take part in the Inception Workshop in which a common vision of overall project goals will be established. Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the project team.

- Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities. UNDP Country Offices and UNDP-GEF RCUs as appropriate, will conduct yearly visits to the regional projects, or more often based on an agreed upon scheduled to be detailed in the project's Inception Report / Annual Work Plan to assess first hand project progress. Any other member of the PSC can also accompany. A Field Visit Report will be prepared by the CO and circulated no less than one month after the visit to the project team, all SC members, and UNDP-GEF.

- Annual Monitoring will occur through the Tripartite Review (TPR). This is the highest policy-level meeting of the parties directly involved in the implementation of a project. The project will be subject to Tripartite Review (TPR) at least once every year. The first such meeting will be held within the first twelve months of the start of full implementation. The project proponent will prepare an Annual Project Report (APR) and submit it to UNDP-CO and the UNDP-GEF regional office at least two weeks prior to the TPR for review and comments.

- The terminal tripartite review (TTR) will be held in the last month of regional project operations. The PC is responsible for coordination of the Terminal Report for all project activities and making sure it is submitted it to the UNDP-CO and GEF's Regional Coordinating Unit. It shall be prepared in draft at least two months in advance of the TTR in order to allow review, and will serve as the basis for discussions in the TTR. The terminal tripartite review considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective. It decides whether any actions are still necessary, particularly in relation to sustainability of project results, and acts as a vehicle through which lessons learnt can be captured to feed into other projects under implementation of formulation.

- Project Monitoring Reporting will take place at regular interval throughout the project. The Project Manager in conjunction with the UNDP-GEF extended team will be responsible for the preparation and submission of the following reports that form part of the monitoring process.

- Inception Report (IR): A Project Inception Report will be prepared immediately following the Inception Workshop. It will include a detailed Firs Year/ Annual Work Plan divided in quarterly time-frames detailing the activities and progress indicators that will guide implementation during the first year of the project. This Work Plan would include the dates of specific field visits, support missions from the UNDP-CO or the Regional Coordinating Unit (RCU) or consultants, as well as time-frames for meetings of the project's decision making structures.  The Report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months time-frame.

- Annual Project Report (APR): The APR is a UNDP requirement and part of UNDP’s Country Office central oversight, monitoring and project management. It is a self -assessment report by project management to the CO and provides input to the country office reporting process, as well as forming a key input to the Tripartite Project Review.  An APR will be prepared on an annual basis prior to the Tripartite Project Review, to reflect progress achieved in meeting the project's Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The format of the APR is flexible but should include the following:

- An analysis of project performance over the reporting period, including outputs produced and, where possible, information on the status of the outcome

- The constraints experienced in the progress towards results and the reasons for these

- The three (at most) major constraints to achievement of results

- Clear recommendations for future orientation in addressing key problems in lack of progress

- Project Implementation Review (PIR): The PIR is an annual monitoring process mandated by the GEF. Once the project has been under implementation for a year, a Project Implementation Report must be completed by the CO together with the project. The PIR can be prepared any time during the year (July-June) and ideally prior to the TPR.  The PIR should then be discussed in the TPR so that the result would be a PIR that has been agreed upon by the project, the executing agency and the UNDP CO.

- Project Terminal Report: During the last three months of the project the project team will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the Project, objectives met, or not achieved, structures and systems implemented, etc. and will be the definitive statement of the Project’s activities during its lifetime.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the Project’s activities.

Independent Evaluation

- The project will be subjected to at least two independent external evaluations as follows:

- Mid-term Evaluation: An independent Mid-Term Evaluation will be undertaken at the end of the second year of implementation. The Mid-Term Evaluation will determine progress being made towards the achievement of outcomes and will identify course correction if needed. It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management. Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document. The Terms of Reference for this Mid-term evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.

- Final Evaluation: An independent Final Evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on the same issues as the mid-term evaluation.  The final evaluation will also look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals.  The Final Evaluation should also provide recommendations for follow-up activities. The Terms of Reference for this evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.

- Finally, the Government will provide the Resident Representative with certified periodic financial statements, and with an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in the Programming and Finance manuals.   The Audit will be conducted by the legally recognized auditor of the Government, or by a commercial auditor engaged by the Government.

### Learning and Knowledge Sharing

- Results from the project will be disseminated within and beyond the project intervention zone through a number of existing information sharing networks and forums.  In addition:

- The project will participate, as relevant and appropriate, in UNDP/GEF sponsored networks, organized for Senior Personnel working on projects that share common characteristics. UNDP/GEF has established a number of networks that will largely function on the basis of an electronic platform to which this project’s lessons learned will be contributed e.g. the Adaptation learning Mechanism.

- The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned.

- The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects. Identify and analyzing lessons learned is an on- going process, and the need to communicate such lessons as one of the project's central contributions is a requirement to be delivered not less frequently than once every 12 months. UNDP/GEF shall provide a format and assist the project team in categorizing, documenting and reporting on lessons learned. To this end a percentage of project resources will need to be allocated for these activities.

Annual Work Plan Budget Sheets

- Budget details for the project are summarized in the tables below.

| Table 7: Implementing NAPA Priority Interventions to Build Resilience in the Agriculture and Water Sectors to the Adverse Impacts of Climate Change in Sudan |
| --- |
| Project Components | Indicative LDCF Financing | Indicative Co-financing |  |
|  | (US$) | % | ($) | % | Total (US$) |
| 1. On-the-ground adaptation measures | 2,300,000 | 47.4% | 2,550,000 | 52.6% | 4,350,000 |
| 2. Institutional capacity strengthening | 400,000 | 57.1% | 300,000 | 42.9% | 600,000 |
| 3. Knowledge management | 300,000 | 50% | 300,000 | 50% | 450,000 |
| 4. Project management | 300,000 | 46.2% | 350,000 | 53.8% | 600,000 |
| Total project costs | 3,300,000 | 49% | 3,500,000 | 51% | 6,800,000 |

| Table 8: Indicative financing plan summary for the project (US$) |
| --- |
|  | Project Preparation | Project | Agency Fee | Total |
| Grant | 100,000 | 3,300,000 | 340,000 | 3,410,000 |
| Co-financing | 60,000 | 3,500,000 |  | 3,060,000 |
| Total | 160,000 | 6,800,000 | 340,000 | 6,470,000 |

| Table 9: Indicative Co-financing for the project (including project preparation) by source and by name (in parenthesis) if available, (US$) |
| --- |
| Sources of Co-financing | Type of Co-financing | Amount |
| Project Government Contribution (In Kind) |  | 3,000,000 |
| UNDP Sudan (Cash) |  | 500,000 |
| Total co-financing |  | 3,500,000 |

## PART V: Legal Context

- This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement between the Government of Sudan and the United Nations Development Programme, signed by the parties on [date]. The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

- The UNDP Resident Representative in Sudan is authorized to effect in writing the following types of revision to this Project Document, provided that he/she has verified the agreement thereto by the UNDP-GEF Unit and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document

# SECTION II: STRATEGIC RESULTS FRAMEWORK (SRF)

Strategic Results Framework, SRF (formerly GEF Logical Framework) Analysis

- The project has three (3) major outcomes which result from adaptation activities undertaken in 5 distinct and non-contiguous locations to meet urgent and immediate adaptation needs as identified through the NAPA process and the project preparation phase. The Results and Resources Framework is provided in the following pages for each outcome of the project, as summarized below:

| Expected Outcomes | Expected Outputs |
| --- | --- |
| 1) Resilience of food-production systems and food-insecure communities enhanced in the face of climate change through the implementation of pilot adaptation measures in demonstration sites | Measures, such as borehole irrigation, rainfall and water catchment basins introduced to enhance communal water storage systems , water supply and reduce vulnerability to water scarcity (and flash-flood frequency) in the River Nile State, Northern Kordofan State, Gedarif State, Southern Darfur State, and Central Equatoria State A set of measures, such as modification of livestock size and profile to improve animal production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State A set of measures, such as introduction of drought resistant varieties and integrated pest management techniques to improve crop production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State A set of measures, such as re-introduction of stress resistant rangeland seedling varieties to enhance rangelands productivity in the Northern Kordofan State; Gedarif State A set of measures, such as sand stabilization to combat sand dune encroachment on arable lands in the Northern Kordofan State and Southern Darfur State A micro-credit, revolving loan and livestock fund established in target communities to build adaptive capacity and livelihood resilience in Northern Kordofan State |
| 2) Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened by capacity building to incorporate short term climate change risks into ongoing and future national development planning among local, regional and national NGOs, technical cooperation, Ministry of Agriculture, local governments and communities. | Output 2.1 Integrate climate change awareness and risk management into extension programs to strengthen local capacity to address climate risks into livelihood activities. Output 2.2 Participatory Early Warning Mechanism designed and tested in the selected pilot regions. Output 2.3 Establish local leadership councils and/or Resource Users Association to facilitate stakeholder engagement and ownership of pilot adaptation projects to be implemented under Outcome 1 |
| 3) A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level by providing important lessons on what does and does not work in improving resilience of vulnerable communities in Sudan to increased climatic variability and climate change | National menu of best practices available for replication Preparation of a national adaptation policy, including budgets for country-wide up-scaling Lessons codified and disseminated through the ALM Lessons codified and disseminated throughout Sudanese government |

For the overall project, there are three major outcomes as outlined below:

| Project Strategy | Indicator | Baseline value | Target | Sources of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
| Overall Goal: Contribute to the reduction of vulnerability and increase the adaptive capacity of Sudan’s agricultural and water sectors to the impacts of climate change |
| Objective: To implement an urgent set of priority adaptation measures for improving food security in the face of climate change in five vulnerable zones in Sudan are implemented covering 414,980 ha | Food security policy has been modified to fully integrate climate change adaptation measures (e.g. climate-resilient crop and livestock production, and climate risk-sensitive rangeland and water resource management strategies) 50% change in vulnerability of food security to rainfall variability established via perception-based stakeholder survey such as VRA | Comprehensive report that summarized local needs of five acutely vulnerable areas; scoping documents for project implementation in these same five areas. To a degree, communities are autonomously adapting to climate variability; added pressures on livelihoods due to climate change have rendered current coping mechanisms in effective and mal-adapted to long-term changes. | 10% of village population in which pilot measures are implemented are engaged and adopted adaptation measures. A local leadership councils established in each village targeted in the project to support community management of natural resources in the face of climate change; lessons-learned through implementation inform national food security policy resilient and adaptive to climate change | VRA report; APR/PIR Mid term evaluation report; Final evaluation report; | local communities are willing to undertake adaptation measures and modify their current farming and pastoralist practices; local governments are supportive and engaged in implementation process; Extension workers, farmers, pastoralists are willing to participate in the training workshops and recognise the benefits in engaging in EWS to ensure food security. |
| Outcome 1: Resilience of food-production systems and food-insecure communities enhanced in the face of climate change in five (5) specific rural areas, identified as being the hardest hit by recurring food insecurity issues: River Nile state (e.g. areas of lower River Atbara); North Kordofan State (e.g. areas of Bara, Gabrat Alsheikh and Sawdery); Gedarif State (e.g. area. of Butana); South Darfur State (e.g. areas of Shairiah, Muhagriah, Malam, Darbat, Marshung); Central Equatorial State (e.g. area of Juba County). | Innovative coping mechanisms and practices with respect to adaptation to climate change risks to food security, e.g. rainwater harvesting, improved irrigation techniques, climate-resilient cropping and grazing systems, livelihood diversification, will be field- tested and adopted in 5 high-risks agro-ecological zones 50% of farmers and pastoralists of the North Kordofan State have access to local MFI to finance adaptation options or to transfer rainfall related risks | The country’s inherent vulnerability may best be captured by the fact that food security in Sudan is mainly determined by rainfall, particularly in rural areas, where 70% of the total population lives; coupled with the fact that changes in temperature and precipitation could cause shifts in the precarious distribution of these ecological zones, in the productive capacity of rainfed agriculture, and thus, in the security of the nation’s food supply. Sudan’s farmer and pastoralist communities rely on mal-adapted practices to increasing climatic variability and have limited capacity and resources to modify their current land and water management practices that are viable under the changing climatic conditions. | The following adaptation measures in five agro-climatic zones are implemented: Measures to enhance communal water storage systems, water supply and reduce vulnerability to water scarcity (and flash-flood frequency) measures to improve animal production and to increase adaptive capacity to climatic change measures to improve crop production and to increase adaptive capacity to climatic change measures to enhance rangelands productivity measures for sand stabilization to combat sand dune encroachment on arable lands A micro-credit, revolving loan and livestock fund established in target communities to build adaptive capacity and livelihood resilience 2,000 applications for credit have been satisfied; Sales of base capital for rainfall based index insurance reaches 60% | Farmer surveys; PIRs; | local communities are willing to undertake adaptation measures and modify their current farming and pastoralist practices; Local governments are supportive of identified adaptation priorities; |
| Outcome 2: Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened. | EWS for climate change risks to food security functional; National and sub-national organizations have access to climate change impact information and adaptation options at the national level and in five pilot areas | Policy issue briefs (water, livelihoods, food security, agriculture) and comprehensive report that identifies capacity needs and shortcomings. We need to state at least some of the needs and shortcomings identified during the project formulation (mission and consultations; In addition to this, there is a lack of awareness, technical capacities and knowledge to make informed decisions. | At staff from least 2 organizations that provide extension services attend training workshops held in each of the five vulnerable zones for extension staff; At least 10% of the project site’s farmers and pastoralists population received targeted training on climate change risks and adaptation options methods for rainfall estimations used for EWS for food security | PIRs; Trainings and awareness workshops documentation including notes, presentations and summary report | Key target Ministries, extension services and other target organisations are willing to participate in project activities and modify their policies and programmes in response to identified climate change risks |
| Outcome 3: A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level. | Food security policies and programmes modified to scale-up tested adaptation measures under the Outcomes #1 and #2; development of national policy for food security in the face of climate change | NAPA-process identified adaptation strategies for implementation. However, there is limited knowledge and understanding of the good practices of applying these measures into practice. Information on innovative practices of water harvesting, rural land water management, or climate resilient agronomic measures are very limited | At least five knowledge products containing critical lessons learned and good adaptation practices from the five pilot agro-ecological zones | PIRs, number of lessons learned; ALM postings | All involved parties have been solicited for input/ feedback; availability of stakeholders; |
| Outputs: Measures, such as borehole irrigation, rainfall and water catchment basins introduced, to enhance communal water storage systems, water supply and reduce vulnerability to water scarcity (and flash-flood frequency) in the River Nile State, Northern Kordofan State, Gedarif State, Southern Darfur State, and Central Equatoria State A set of measures, such as modification of livestock size and profile to improve animal production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State A set of measures, such as introduction of drought resistant varieties and integrated pest management techniques to improve crop production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State A set of measures, such as re-introduction of stress resistant rangeland seedling varieties to enhance rangelands productivity in the Northern Kordofan State; Gedarif State A set of measures, such as sand stabilization to combat sand dune encroachment on arable lands in the Northern Kordofan State and Southern Darfur State A village level micro-finance institutions (revolving, risk absorption, livestock fund,) established in target communities to build adaptive capacity and livelihood resilience in Northern Kordofan State Integrate climate change awareness and risk management into extension programs to strengthen local capacity to address climate risks into livelihood activities. Participatory Early Warning Mechanism designed and tested in the selected pilot regions Establish local leadership councils and/or Resource Users Association to facilitate stakeholder engagement and ownership of pilot adaptation projects to be implemented under Outcome 1 National menu of best practices available widely and mainstreamed into national development planning Preparation of a national food security policy in the face of climate change, including budgets for a country-wide up-scaling Lessons codified and disseminated through the ALM Lessons codified and disseminated through throughout Sudanese institutions |

| Award ID: | 00057783 |
| --- | --- |
| Award Title: | PIMS 3925 CC FSP: Implementing NAPA Priority Interventions to Build Resilience in the Agriculture and Water Sectors to the Adverse Impacts of Climate Change in Sudan |
| Business Unit: | SDN10 |
| Atlas Project ID | 00071514 |
| Project Title: | PIMS 3925 CC FSP: Implementing NAPA Priority Interventions to Build Resilience in the Agriculture and Water Sectors to the Adverse Impacts of Climate Change in Sudan |
| Implementing Partner (Executing Agency) | Higher Council for Environment and Natural Resources (HCENR) |

# SECTION III: TOTAL BUDGET AND WORKPLAN

| GEF Outcome/Atlas Activity | Responsible Party / Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Year 1 (USD) | Year 2 (USD) | Year 3 (USD) | Year 4 (USD) | Total (USD) | Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Resilience of food-production systems and food-insecure communities enhanced in the face of climate change | HCENR | 62160 | LDCF | 71200 | International Consultants | 40,000 | 40,000 | 40,000 | 40,000 | 160,000 | 1 |
|  |  |  |  | 71300 | Local Consultants | 17,500 | 17,500 | 17,500 | 17,500 | 70,000 | 2 |
|  |  |  |  | 71600 | Travel | 10,500 | 10,500 | 9,000 | 5,000 | 35,000 | 3 |
|  |  |  |  | 72100 | Contractual services | 400,000 | 680,000 | 450,000 | 333,000 | 1,863,000 | 4 |
|  |  |  |  | 72200 | Equipment and furniture | 20,000 | 10,000 | 5,000 | 5,000 | 40,000 | 5 |
|  |  |  |  | 72500 | Supplies | 8,000 | 8,000 | 8,000 | 8,000 | 32,000 | 6 |
|  |  |  |  | 75700 | Trainings, meetings & Workshops | 30,000 | 30,000 | 20,000 | 20,000 | 100,000 | 7 |
|  |  |  |  |  | Subtotal LDCF | 526,000 | 796,000 | 549,500 | 428,500 | 2,300,000 |  |
| OUTCOME 2: Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened | HCENR | 62160 | LDCF | 71200 | International Consultants | 20,000 | 60,000 | 60,000 | 20,000 | 160,000 | 8 |
|  |  |  |  | 71300 | Local Consultants | 17,500 | 17,500 | 17,500 | 17,500 | 70,000 | 9 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 10 |
|  |  |  |  | 72100 | Contractual services | 25,000 | 28,000 | 30,000 | 29,000 | 112,000 | 11 |
|  |  |  |  | 72500 | Supplies | 4,500 | 4,500 | 4,500 | 4,500 | 18,000 | 12 |
|  |  |  |  | 74500 | Miscellaneous | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 13 |
|  |  |  |  |  | Subtotal LDCF | 77,000 | 120,000 | 122,000 | 81,000 | 400,000 |  |
|  |  | 4000 | UNDP | 72100 | Contractual services | 10,000 | 30,000 | 20,000 | 12,000 | 72,000 | 14 |
|  |  |  |  | 72200 | Equipment and furniture | 50,000 | 5,000 | 5,000 | 5,000 | 65,000 | 15 |
|  |  |  |  | 72500 | Supplies | 7,000 | 5,000 | 3,000 | 3,000 | 18,000 | 16 |
|  |  |  |  | 75700 | Trainings, meetings & Workshops | 20,000 | 10,000 | 10,000 | 5,000 | 45,000 | 17 |
|  |  |  |  |  | Sub-total UNDP | 87,000 | 50,000 | 38,000 | 25,000 | 200,000 |  |
| OUTCOME 3: A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level | HCENR | 62160 | LDCF | 71200 | International Consultants | 20,000 | 40,000 | 40,000 | 60,000 | 160,000 | 18 |
|  |  |  |  | 71300 | Local Consultants | 5,000 | 10,000 | 15,000 | 17,200 | 47,200 | 19 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 20 |
|  |  |  |  | 72500 | Supplies | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 21 |
|  |  |  |  | 74500 | Miscellaneous | 4,500 | 4,500 | 4,500 | 4,500 | 18,000 | 22 |
|  |  |  |  | 74100 | Professional services | 5,000 | 5,000 | 15,000 | 9,800 | 34,800 | 23 |
|  |  |  |  |  | Subtotal LDCF | 44,500 | 69,500 | 84,500 | 101,500 | 300,000 |  |
|  |  | 4000 | UNDP | 72100 | Contractual services | 5,000 | 15,000 | 10,000 | 5,000 | 35,000 | 24 |
|  |  |  |  | 74500 | Miscellaneous | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 25 |
|  |  |  |  | 74100 | Professional services | 5,000 | 10,000 | 5,000 | 5,000 | 25,000 | 26 |
|  |  |  |  | 75700 | Trainings, meetings & Workshops | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 27 |
|  |  |  |  |  | Sub-total UNDP | 20,000 | 35,000 | 25,000 | 20,000 | 100,000 |  |
| Project Management | HCENR | 62160 | LDCF | 71300 | Local Consultants | 68,750 | 68,750 | 68,750 | 68,750 | 275,000 | 28 |
|  |  |  |  | 71600 | Travel | 6,250 | 6,250 | 6,250 | 6,250 | 25,000 | 29 |
|  |  |  |  |  | Subtotal Project Management (sub-total) | 75,000 | 75,000 | 75,000 | 75,000 | 300,000 |  |
|  |  | 4000 | UNDP | 71400 | Contractual services / individual | 27,250 | 27,250 | 27,250 | 27,250 | 109,000 | 30 |
|  |  |  |  | 72200 | Equipment and furniture | 20,000 | 10,000 | 10,000 | 5,000 | 45,000 | 31 |
|  |  |  |  | 73100 | Rental & Maintenance of Premises | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 32 |
|  |  |  |  | 74500 | Miscellaneous | 1,500 | 1,500 | 1,500 | 1,500 | 6,000 | 33 |
|  |  |  |  |  | Sub-total UNDP | 58,750 | 48,750 | 48,750 | 43,750 | 200,000 |  |
|  |  |  |  |  | Project Total | 888,250 | 1,194,250 | 942,750 | 774,750 | 3,800,000 |  |
| Summary of Funds |  |  | Year 1 (USD) | Year 2 (USD) | Year 3 (USD) | Year 4 (USD) | Total (USD) |  |
|  |  | GEF | 722,500 | 1,060,500 | 831,000 | 686,000 | 3,300,000 |  |
|  |  | UNDP cash | 165,750 | 133,750 | 111,750 | 88,750 | 500,000 |  |
|  |  | GOS | 737,500 | 995,000 | 715,500 | 552,000 | 3,000,000 |  |
|  |  | Total | 1,625,750 | 2,189,250 | 1,658,250 | 1,326,750 | 6,800,000 |  |

Budget Notes:

- This budget line partially covers the costs of the “lead international expert” to provide overall guidance, expert advisory services and technical assistance to the Project Manager and the other project experts. At the outset of the project, the lead consultant’s input will be on a semi-permanent basis, and it will be gradually reduced in the subsequent stages as internal project capacity grows. The short-term international consultancies necessary for advice on rangeland rehabilitation, water harvesting and other proposed livelihood and food security adaptation measures, will be covered within this budget line.

- The national consultancies will be used to provide an advice on how to implement proposed adaptation measures in the five sites. Technical support is needed regarding evaluation of local varieties of vegetation, demarcation of implementation sites, design of pilot activities, and organizing community stakeholder engagement. The national consultancies will also be used to support the implementation of pilot activities as well as to support activities to increase the capacity of farmers and herders to reduce their vulnerability to the impacts of climate change, and adapt to the changing climatic conditions. The terms of reference will be prepared by the Project Manager during the implementation of the project.

- This budget line covers travel expenses, including travel of international consultants, and local travels for site visits, etc.

- The companies will be contracted to implement pilot projects in the previously identified villages. The main element of contractual services will be the installation of pilot adaptation measures targeted at reducing food insecurity in the vulnerable communities. Specific services will be identified during the inception phase of the project and the detailed description of services will be developed afterwards. The companies will be selected on competitive and transparent basis based on UNDP rules and regulations. The contracts will be performance-based.

- This budget line covers purchase of equipment related to the implementation of the project and does not relate to management tasks.

- This budget line covers office supplies related to the implementation of the project.

- Workshops and training activities in support of climate-proofing tools/methods will be held throughout the project duration. The agenda and workshop design will be prepared by the Project Manager and assisted by relevant international consultants during the implementation of the project.

- This budget line partially covers the costs of a lead international expert as per budget note #1. International technical expertise will be contracted to build the capacity on application of the MFIs at the village level; to design various financial services packages varied from micro credit for adaptation practices (purchase of stress resistant varieties, water harvesting works, sand stabilizing planting works, etc); design of rainfall-based weather index contracts. This budget line will also cover travel expenses, including travel of international consultants, and local travels for site visits, etc.

- The local consultancies will be used for review of relevant policies, legislation and regulatory framework as well as to support capacity building programs within relevant government entities. The national consultancies will be used to support training activities in support of climate-proofing extension services. The terms of reference will be prepared by the Project Manager and assisted by relevant international consultants during the implementation of the project.

- This budget line covers travel expenses, including travel of international consultants, and local travels for site visits, etc.

- The companies and NGOs will be contracted in support of training, development of research/information, and other activities to increase national capacities. Specific including workshop venue costs, information technology costs and any other support-related services identified during the inception phase of the project, Companies will be selected on a competitive and transparent basis consistent with UNDP rules and regulations. The contracts will be performance-based.

- This budget line covers office supplies related to the implementation of the project.

- This budget line is to cover miscellaneous expenses occurring during implementation of the project.

- The companies and NGOs will be contracted in support of training, development of research/information, and other activities to increase national capacities. Specific including workshop venue costs, information technology costs and any other support-related services identified during the inception phase of the project, Companies will be selected on a competitive and transparent basis consistent with UNDP rules and regulations. The contracts will be performance-based.

- This budget line is for the purchase of one (1) car to monitor implementation of on-the-ground measures and travel between pilot sites and well as to/from Khartoum. $1,000 (USD)/ year after the first year has been included to cover estimated to fuel and maintenance costs.

- This budget line covers office supplies related to the implementation of the project.

- Workshops and training activities in support of climate-proofing tools/methods will be held throughout the project duration. The agenda and workshop design will be prepared by the Project Manager and assisted by relevant international consultants during the implementation of the project.

- This budget line partially covers the costs of a lead international expert as per budget note #1. International technical expertise will be contracted to provide overall guidance, expert advisory services and technical assistance to the Project Manager and the other project experts regarding M&E and the synthesis of lessons learned from the pilot adaptation activities. The budget line also covers travel expenses, including travel of international consultants, and local travels for site visits, etc.

- The national consultancies will be used to provide an advice on M&E for relevant agencies involved as well as for strategies to disseminate the lessons learned from the project into national institutions and agencies. The consultancies will be used to support of training activities, stakeholder discussions, public awareness materials, and development of information systems. The companies will be selected on competitive and transparent basis based on UNDP rules and regulations. The contracts will be performance-based.

- This budget line covers travel expenses, including travel of international consultants, and local travels for site visits, etc.

- This budget line covers office supplies related to the implementation of the project

- This budget line covers miscellaneous expenses occurring during implementation of the project.

- Professional services refer to the costs for financing the midterm and final evaluations in addition to the annual audits. $40,000USD in Year 2 and $100,000USD in Year 4 have been allocated to cover the mid-term and final evaluation respectively.

- The companies and NGOs will be contracted in support of training, development of research/information, and other activities to increase national capacities. Specific including workshop venue costs, information technology costs and any other support-related services identified during the inception phase of the project, Companies will be selected on a competitive and transparent basis consistent with UNDP rules and regulations. The contracts will be performance-based.

- This budget line covers miscellaneous expenses occurring during implementation of the project.

- Professional services refer to the costs for financing the midterm and final evaluations in addition to the annual audits. $40,000USD in Year 2 and $100,000USD in Year 4 have been allocated to cover the mid-term and final evaluation respectively.

- Workshops and training activities in support of climate-proofing tools/methods will be held throughout the project duration. The agenda and workshop design will be prepared by the Project Manager and assisted by relevant international consultants during the implementation of the project.

- The line will cover the salary of the Project Manager, Regional Project Coordinators, Project Assistant and Project Accountant.

- The line will cover the travel expenses necessary for the proper project management and monitoring throughout the project implementation

- The individual contractors will be contracted in support the training and capacity building programs for continuous learning programs, materials and specific training on financial resource mobilization. Contractors will be selected on a competitive and transparent basis consistent with UNDP rules and regulations. The contracts will be performance-based.

- The line will be used to purchase necessary computers, printers and other office equipment for publications and awareness and stakeholder consultation workshops.

- This budget line will be used for renting meeting places for stakeholder consultation and workshops both in Khartoum and in the regional governorates.

- This budget line covers miscellaneous expenses by the PMU.

| Work Plan Budget Sheet | 2010 | 2011 | 2012 | Planned Budget |
| --- | --- | --- | --- | --- |
| EXPECTED OUTPUTS | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Responsible party | Funding Source | Budget Description | Amount (USD) |
| Outcome 1. Resilience of food-production systems and food-insecure communities enhanced in the face of climate change |
| Output 1.1. Measures introduced to enhance communal water storage systems , water supply and reduce vulnerability to water scarcity (and flash-flood frequency) in the River Nile State, Northern Kordofan State, Gedarif State, Southern Darfur State, and Central Equatoria State |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | Investment; technical assistance | $1,553,571 |
| Output 1.2. A set of measures to improve animal production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | Investment; technical assistance | $621,429 |
| Output 1.3. A set of measures to improve crop production and to increase adaptive capacity to climatic change implemented in the Nile State and Southern Darfur State |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | Investment; technical assistance | $621,429 |
| Output 1.4. A set of measures to enhance rangelands productivity in the Northern Kordofan State; Gedarif State |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | Investment; technical assistance | $621,429 |
| Output 1.5. A set of measures for sand stabilization to combat sand dune encroachment on arable lands in the Northern Kordofan State and Southern Darfur State |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | Investment; technical assistance | $621,429 |
| Output 1.6. A village level micro-finance institutions (revolving, risk absorption, livestock fund,) established in target communities to build adaptive capacity and livelihood resilience in Northern Kordofan State |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | Investment; technical assistance | $310,714 |
| Outcome 2. Institutional and individual capacities to implement climate risk management responses in the agriculture sector strengthened |
| Output 2.1. Integrate climate change awareness and risk management into extension programs to strengthen local capacity to address climate risks into livelihood activities. |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOE | technical assistance , technical assistance | $250,000 |
| Output 2.2. Participatory Early Warning Mechanism designed and tested in the selected pilot regions |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOE | Investment, technical assistance | $200,000 |
| Output 2.3. Establish local leadership councils and/or Resource Users Association to facilitate stakeholder engagement and ownership of pilot adaptation projects to be implemented under Outcome 1 |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOE | Investment, technical assistance | $150,000 |
| Outcome 3. A better understanding of lessons learned and emerging best practices, captured and up-scaled at the national level |  |  |  |
| Output 3.1. National menu of best practices available widely and mainstreamed into national development planning |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | technical assistance | $152,500 |
| Output 3.2. Successful pilot mechanisms and measures institutionalized |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | technical assistance | $72,500 |
| Output 3.3. Lessons codified and disseminated through the ALM |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | technical assistance | $122,500 |
| Output 3.4. Lessons codified and disseminated through the Sudanese institutions |  |  |  |  |  |  |  |  |  |  |  |  | Project staff; local contractors | GEF, GOS | technical assistance | $102,500 |

SECTION IV: ADDITIONAL INFORMATION

## PART I: Other agreements

## PART II: Terms of References for key project staff and main sub-contracts

| Position Titles | Estimated person weeks | US $/ person week | Tasks to be performed |
| --- | --- | --- | --- |
| For Project Management (only local; no international consultants) |
| Project Manager (local) | 170 | 900 | Supervise and coordinate the project to ensure its results are in accordance with the Project Document and the rules and procedures established in the UNDP Programming Manual; Ensure adequate information flow, discussions and feedback among the various stakeholders of the project; Ensure adherence to the project’s work plan, prepare revisions of the work plan, if required; Prepare GEF quarterly project progress reports, as well as any other reports requested by the Executing Agency and UNDP; Guide the work of consultants and subcontractors and oversee compliance with the agreed work plan; Maintain regular contact with UNDP Country Office and the National Project Director on project implementation issues of their respective competence; Assume overall responsibility for the meeting financial delivery targets set out in the agreed annual work plans, reporting on project funds and related record keeping; Liaise with project partners to ensure their co-financing contributions are provided within the agreed terms; Assume overall responsibility for reporting on project progress vis-à-vis indicators in the logframe; Undertake any other actions related to the project as requested by UNDP or the National Project Director. |
| 5 Regional Project Coordinators - River Nile State - North Kordofan State - Gegarif State - Southern Darfur - Equatorial State | 5 x 125 | 400 | Organize and coordinate all local activities of the project; Supervise the implementation and ensure that results are delivered according to the Project Document and the rules and procedures established in the UNDP Programming Manual; Under the overall responsibility and guidance of the Project Manager, assume responsibility for the delivery of all project activities locally, in the respective state; Liaise with all project partners locally and ensure wide participation of key stakeholders, especially communities of farmers and pastoralists; Maintain regular contact with the Project Manager and report on progress, challenges and emerging opportunities, including operational issues or risks to project results; Contribute to the Annual Project Reports (PIRs) and project risk management strategy; Organize field missions of the technical teams to the state; Assume responsibility for compiling all existing data or generating new information or data for the analysis and baseline data for M&E; Closely monitor implementation of all locally defined components of the project; Disseminate information about project activities and achievements through local channels of communication and to all partners; Maintain partnership and regular contact with the local authorities and ensure that the in-kind co-financing materializes; Assume the responsibility for building new partnerships, seeking synergies with other related initiatives and resource mobilization; |
| Accountant | 208 | 185 | Under supervision of project manager, responsible for all aspects of project financial management Organize control of budget expenditures by preparing payment documents, and compiling financial reports; Maintain the project’s disbursement ledger and journal; Control the usage non expendable equipment (record keeping, drawing up regular inventories); |
| Project Assistant (local) | 208 | 160 | Provide general administrative support to ensure the smooth running of the project management unit; Project logistical support to the Project manager and project consultants in conducting different project activities (trainings, workshops, stakeholder consultations, etc.); During the visits of foreign experts, organize visa support, transportation, hotel accommodation etc; Keep files with project documents, expert reports; Keep regular contact with project experts and consultants to inform them about the project details and changes; Provide English translation as required; Draft correspondence and documents; finalize correspondence of administrative nature; edit reports and other documents for correctness of form and content; Arrange duty travel; Act on telephone inquiries, fax, post and e-mail transmissions, and co-ordinate appointments; Organize and coordinate the procurement of services and goods under the project. Perform any other administrative duties as requested by the Project Manager. |
| For technical assistance (Local) |
| National Technical Specialist | 208 | 900 | Provide technical backstopping and guidance to the FSP Project Manager and to the national team of experts in methods, approaches, tools, data etc needed for the implementation of the FSP components. Provide inputs to local community mobilization techniques adequate for the context of Sudan; Design vulnerability reduction assessment questionnaire / survey to capture the key indicators of vulnerability amongst the target communities at the project inception and track the progress against these indicators throughout the project. Help employ VCA (vulnerability and capacity assessment) and other tools for vulnerability and adaptive capacity assessments; Design community based adaptation options for the farming and pastoralist systems to achieve greater food security in the face of climate change related risks Monitor, analyse and provide recommendations to the FSP Project Manager on the adequacy and content of the technical reports, project deliverables and on the status of the implementation of the relevant activities to be carried out for the achievement of the project outcomes/outputs. Provide substantive support to the FSP Project Manager in identifying and recruiting the motivated and competent staff, formulating their responsibilities as well as appraising their performance. Provide substantive support in the development and monitoring of the FSP work plan; Coordinate the development of networking and information system activities relevant to the FSP implementation; Search for, collect, analyse and synthesize the necessary technical information during the project implementation. Develop a database of the sources of the information relevant to the implementation of the FSP technical components; Liaise and cooperate with relevant authorities and representatives of the programs/project under the implementation and work to ensure the achievement of project objective; Liaise with similar project teams (at least those implemented as LDCFs), share information, lessons learnt and good practices; |
|  |  |  | Provide substantive technical support to the consultative process, workshops, and other meetings to be organized on different aspects relevant to the FSP implementation; prepare briefing notes, background papers; make presentations; and guide the national experts in performing their assignment; Participate in the planning, review and preparation of the FSP budgets and prepare related documents; Participate and facilitate the development of follow-up or/and other adaptation projects on relevant issues as necessary. Perform other duties as required |
| For technical assistance (International) |
| International Consultant | 120 | 3000 | Provide inputs at the inception phase, and after, in areas such as finalization of the project inception report, annual work plans, drafting of Terms of Reference for national experts, TORs for subcontracts and required tender documents Provide technical backstopping and training on technical issues such as: identification of adaptation measures in the project site; methods and tools to be applied in community based, participatory vulnerability assessment and adaptation planning; Provide support in designing MFI based on local conditions of the target regions / villages, needs and feasibility of locally managed shock absorption, revolving, or livestock funds; Assess the feasibility of utilizing existing or newly established village level MFIs for delivery of weather index based insurance; Provide guidance for capacity building for local extension services to the farmers and pastoralists that provide adaptation advice; Provide inputs in designing and delivering targeted training for local and national stakeholders in climate risk management to minimize food insecurities; Provide support to the project manager in ensuring the quality of the project deliverables by reviewing and providing feedback on the work of contracted individual experts and companies |
| Short Term International Consultant on Rangeland Management | 20 | 3000 | Provide an in-depth assessment of key vulnerabilities of pastoralist communities and rangelands; Collect key socio-economic data to establish the key vulnerabilities and analyze underlying causes as well as barriers to more sustainable rangeland practices in Sudan; Analyze current tenure related issues and advice on feasible solutions based on extensive consultations at national and local levels; Assess current vulnerabilities of rangelands to reoccurring drought and other climatic hazards; Based on existing analysis and stakeholder consultations assess key anticipated impacts of climate change in the near decades; Undertake field visits for rangeland community consultation and participatory vulnerability assessment and adaptation planning; Provide advice on sustainable rangeland practices that could be applicable in the context of Sudan in the face of climate change; Help design adaptation measures in close consultation with the local pastoralist communities |
| Short Term International Consultant on Farming Systems | 20 | 3000 | Provide an in-depth assessment of key vulnerabilities of farmers in selected states in Sudan; Compile an analysis on natural-resource based conflicts in Sudan and the options to minimize such conflicts; Collect key socio-economic data and analyze current food security conditions in Sudan, including underlying causes and barriers to address food insecurity on sustainable basis; Based on existing analysis and stakeholder consultations assess key anticipated impacts of climate change in the near decades; Design, in fully participatory manner, key agronomic measures that could help farmers in climate risk reduction and improve yield productivity; Assess the conditions of water access and options of water harvesting, storage and distribution across the farming plots in the target regions; Assess market access and economic opportunities for farmers that could help accumulate necessary assets for shock absorption and adaptation; |

* Provide dollar rate per person weeks or months as applicable; **  Total person weeks/months needed to carry out the tasks.

Project Manager (full time)

Duties and responsibilities:

Operational project management in accordance with the project document and the UNDP guidelines and procedures for nationally executed projects, including:

- General coordination, management and supervision of project implementation;

- Set up and manage the project office, including staff facilities and services, in accordance with the project work plan;

- Prepare and update project work plan, and submit these to the UNDP environmental focal point and DRR for clearance and ensure their implementation consistent with the provisions of the project document.

- Assume direct responsibility for managing the procurement and the project budget on behalf of the Climate Change Programme Manager, under the supervision of the Executing Agency and with support from UNDP to ensure that:

  - Project funds are made available when needed, and are disbursed properly;

  - Accounting records and supporting documents are kept;

  - Required financial reports are prepared;

  - Financial operations are transparent and financial procedures/regulations for NEX projects are applied;

  - The project is ready to stand up to audit at any time.

  - Local and international experts are involved in a timely fashion

  - Organization of training and public outreach, purchase of required equipment etc. are carried out in accordance with UNDP rules and procedures;

- Ensure the timely mobilization and utilization of project personnel, subcontracts, training and equipment inputs, whether these are procured by the Executing Agent itself or by other implementing agents:

  - Identify potential candidates, national and international, for posts under the project

  - Prepare the ToR, in consultation with the implementing agent and subcontractors;

  - Prepare training programmes (in consultation with the implementing agents) designed for staff, with particular emphasis on developing an overall training plan.

  - Draw up specifications for the equipment required under the project; procure such equipment according to Government and UNDP rules and procedures governing such procurement.

  - Ensure that they mobilize and deliver the inputs in accordance with their implementation agreement and contract, and

  - Provide overall supervision and/or coordination of their work to ensure the production of the corresponding project outputs.

- With respect to project review cycle:

  - Ensure timely preparation and submission of required reports, including technical, financial, and study tour/fellowship reports;

  - Submission of annual Project Implementation Reviews and other required progress reports to the PMU, Executing Agency and the UNDP in accordance with the section “Monitoring and Evaluation” of the project document;

  - Act as a principal representative of the project during review meetings, evaluations and in discussions and, hence, be responsible for preparation of review and evaluation reports such as the Annual Project Report (APR/PIR) for the consideration of the UNDP CO focal point.

- With respect to project communication:

  - Ensuring effective dissemination of and access to information on project activities and results, (including an regularly updated project website);

  - Communicating with international investors and financial organizations to define fields  of cooperation and attracting additional financing in order to fulfil the project objectives;

  - Report regularly to and keeps the Climate Change Programme Manager/Executing Agency and UNDP CO up-to-date on project progress and problems, if any.

- Ensuring successful completion of the project in accordance with the stated outcomes and performance indicators summarized in the project’s logframe matrix and within the planned schedule and budget otherwise.

- Perform others coordinating tasks as appropriate for the successful implementation of the project in accordance with the project document

Expected Qualifications:

- Advance university degree and at least 15 years of professional experience in the specific areas the project is dealing with, including good knowledge of the international experiences, state of the art approaches and best practices in coastal zone management and adaptation to sea level rise and their implementation (by engaging appropriate stakeholders (local and national government agencies).

- Experience in managing projects of similar complexity and nature, including demonstrated capacity to actively explore new, innovative implementation and financing mechanisms to support community-based development in Sudan;

- Demonstrated experience and success on the engagement of and working with the local authorities and communities, creating partnerships and leveraging financing for activities of common interest;

- Good analytical and problem solving skills and the related ability to adaptive management with prompt action on the conclusion and recommendations coming out from the project’s regular monitoring and self assessment activities as well as from periodical external evaluations;

- Ability and demonstrated success to work in a team, to effectively organize its work and to motivate its members and other project counterparts to effectively work towards the project’s objective and expected outcomes.

- Good communication skills and competence in handling project’s external relations at all levels;

- Fluency in English and Arabic languages.

- Familiarity and prior experience with the specific UNDP and GEF requirements are considered as assets

Regional Project Coordinator:

Duties and responsibilities:

- Organize and coordinate implementation of all local activities of the project in the respective state;

- Supervise the implementation and ensure that results are delivered according to the Project Document and the rules and procedures established in the UNDP Programming Manual;

- Under the overall responsibility and guidance of the Project Manager, assume responsibility for the delivery of all project activities locally, in the respective state;

- Liaise with all project partners locally and ensure wide participation of key stakeholders, especially communities of farmers and pastoralists;

- Maintain regular contact with the Project Manager and report on progress, challenges and emerging opportunities, including operational issues or risks to project results;

- Contribute to the Annual Project Reports (PIRs) and project risk management strategy;

- Organize field missions of the technical teams to the state;

- Assume responsibility for compiling all existing data or generating new information or data for the analysis and baseline data for M&E;

- Closely monitor implementation of all locally defined components of the project;

- Disseminate information about project activities and achievements through local channels of communication and to all partners;

- Maintain partnership and regular contact with the local authorities and ensure that the in-kind co-financing materializes;

- Assume the responsibility for building new partnerships, seeking synergies with other related initiatives and resource mobilization

Expected Qualifications:

- University degree and at least 10 years of professional experience in the specific areas the project is dealing with, including good knowledge of local conditions in the respective state (region) of Sudan.

- Experience in managing projects and familiarity of all international aid and development programmes in the respective state;

- Demonstrated experience and success on the engagement of and working with local authorities and communities, creating partnerships and leveraging financing for activities of common interest;

- Good analytical and problem solving skills and the related ability to adaptive management with prompt action on the conclusion and recommendations coming out from the project’s regular monitoring and self assessment activities as well as from periodical external evaluations;

- Ability and demonstrated success to work in a team, to effectively organize its work and to motivate its members and other project counterparts to effectively work towards the project’s objective and expected outcomes.

- Good communication skills and competence in handling project’s external relations at all levels;

- Fluency in English and Arabic languages.

- Familiarity and prior experience with the specific UNDP requirements are considered as assets

Project Assistant (full time)

Duties and responsibilities:

Supporting the project manager in the implementation of the project, including:

- Responsibility for logistics and administrative support of the project implementation, including administrative management of the project budget, required procurement support, and preparation of internal and external travel arrangements for project personnel,  etc.

- Maintaining the business and financial documentation up to date, in accordance with UNDP and other project reporting requirements;

- Managing the projects files and supporting the project manager in preparing the required financial and other reports required for monitoring and supervision of the project progress, including:

  - Maintain the project documentation up-to-date and in perfect order;

  - Prepare all payment requests, financial record-keeping and preparation of financial reports required in line with NEX financial rules and procedures

  - Provide support to project audits;

  - Assist the Project Manager and UNDP in all financial matters related to the project, observing the set deadlines

  - Maintain the project financial records in an impeccable way

  - Ensure strict observation of UNDP financial planning and reporting

  - Ensure that UNDP’s procurement procedures are adhered to

- Assist the Project Manager in

  - elaborating the project work plans;

  - elaborating the project reports as per the applicable UNDP Egypt procedures;

  - organization of in-country training activities, ensuring logistical arrangements

  - the organization of project events (workshops, working group meetings, local stakeholder consultations, management/steering committee meetings, etc.);

  - in managing the contracts, in organizing correspondence and in ensuring effective implementation of the project otherwise

  - the recruitment and procurement processes, checking the conformity with UNDP and the Government rules and procedures

- Facilitate project communications (telephone, fax, e-mail, post, etc.), including :

  - Liaise with individual and corporate project sub-contractors;

  - Routine translation/interpretation drafting of correspondence as required

  - Draft correspondence and documents; finalize correspondence of administrative nature; edit reports and other documents for correctness of form and content;

  - Supporting the project outreach and PR activities in general, including keeping of the project web-site up to date;

- During project meetings, workshops, and trainings:

  - Maintain project equipment ledgers , contract logs and other data base for the project as well as elaborate rosters of potential consultants and sub-contractors

  - Keep attendance records in an impeccable way;

  - Draft minutes of meetings;

  - Routine translation/interpretation during projects meetings

Expected Qualifications:

- Fluent in English and Arabic

- Demonstrated experience and success of work in a similar position

- Good administration and interpersonal skills

- Ability to work effectively under pressure

- Good computer skills

# Annex A: Description of priority areas selected for the implementation of the project

There are five acutely vulnerable areas identified during the Sudan NAPA consultative processes have been selected for NAPA follow-up activities. These are listed here in context of the map at right and followed thereafter by full-descriptions of the ecological and socio-economic contexts of each project area.

1) River Nile state (e.g. areas of lower River Atbara)

2) North Kordofan State (e.g. areas of Bara, Gabrat Alsheikh and Sawdery).

3) Gedarif State (e.g. area. of Butana).

4) South Darfur State (e.g. areas of Shairiah, Muhagriah, Malam, Darbat, Marshung)

5) Central Equatorial State (e.g. area of Juba County).

River Nile State

The River Nile State, in the far northern part of the country, has highly arid ecosystems. These areas represent over 25% of total land area or about 60 million hectares. The project area is a priority vulnerable in the River Nile state and is located along Atbara River downstream of the Khashmel Girba dam. The area lies in the eastern fringes of the state between latitudes 17-18N and longitude35-34 E (Figure).  Adarama, on the East Bank, is included in Figure  below as the only identifiable village on Google Earth.

The project initially targeted 19 villages that cover a total flooded area of roughly 300,000 feddan. The River Atbara divides the project area into northern and southern bank settlements: 10 villages lying on the northern bank and 9 villages on the southern bank. However, according to state prioritization and consultative meetings just four areas have been selected. The selected villages are indicated in

Table 1:

Table 1. River Nile project implementation villages

| Name | Location | Irrigable area (acres) |
| --- | --- | --- |
| Adarama Salalat Shababeet Morzooga | East bank East bank West bank West bank | 83,000 35,000 |
| Total |  | 118,000 |

The Atbara River is characterized by high velocity, steep slope, high amount of sediments carried in suspension and creeping sand.  The high variations in discharge volume and flow duration create hard condition for local settlements in terms of flood washing of villages and loss of properties. Food shortage during the flood season and water borne diseases frequently takes place.  Flood-irrigation is concentrated mainly around River Atbara, however, the high variations in discharge volume and flow duration create hard conditions for local settlements in terms of flood washing of villages and loss of property. Recently the annual rate of the River Atbara flood has been decreasing, and has led to deterioration of crop and animal production. This is also exacerbated by land constraints as it has become difficult and costly to cultivate terraced land, which represents about 90% of the agricultural land. Food shortage during the flood season and water borne diseases are frequent. Water resources constitute the most critical determinant in the performance of all efforts involving water management.

The River Nile State is inhabited by 950,000 citizens and over 80% rely on agriculture for their livelihoods – both farmers and herders. The demographic composition of River Atbara communities can be divided into two major groups: 1) settled tribes i.e. Besharien, kamalab, Nefedab, Manassir, Gallien, Rubatab, and Hudendwa; and 2) nomadic tribes i.e. Rashida, Amarar, and some areas of Busharien and Manaseer. The total population is an estimated 16,200 households totaling 65,000 persons. Of these 65,000 people, the two main occupations are farmers (70%), Animal raisers (20%), another 10% generate their income from other activities (see map of livelihood systems in Figure ).

Major cultivated lands are located around the River Nile and Atbara banks. Farmers grow staple crops (sorghum and fodders) as well as economic crops (vegetables). Throughout Sudan, winter is the main agricultural season given its short and warm characteristics. However, the River Nile State has relatively cold and long winters, which makes the State an ideal area for winter crops e.g. wheat, maize, legumes, vegetables, fruits, spices and medicinal plants.

Herders depend on access to natural grazing areas during the rainy season (July- Sep). Pastoralists later migrate with their animals to North Botana to avoid conflicts during the River Atbara communities’ growing season, and later return to the area during the dry season to graze on crop residues and make use of available water ponds in the valley. Settled households raise animals for domestic use; however, in both nomadic and settled groups animal production is characterized by: low productivity in both milk and meat, high cost of fodder, and poor marketing strategies.  The local animal population is estimated as 1.5 million heads however of poor quality and health.

North Kordofan State

North Kordofan State is predominantly semi-arid areas and the project areas selected for the NAPA follow-up adaptation activities are located in the woodland savanna (poor savanna on sand). The State represents over 20% of total area of Sudan at about 65 million hectares. North Kordofan State lies between latitude 11˚15’ - 16˚45` N and longitude 27˚05’ - 32˚15` E, in the central part of the country.

The NAPA consultation process revealed that the most vulnerable groups in the state are those who live in Bara, Sodari and Gabrat Elsheikh localities.  Consultations with stakeholders revealed that, of these, Bara is the most vulnerable locality (see Figure ). The following communities near the Bara locality were identified to be the direct beneficiaries of the NAPA follow-up project: El Bashiri, El Humara, El Hidaid, Um Nabag, Shag-elnom, Abu Dalam Elmofatih, Abu Dalam Elaama, Um Rub, Mashga, Goz Khalefa, Abu Gayda, Moga, Foja, Hasheiti and El Raeila.

The North Kordofan State is part of the Sudano-Sahelian region, which, over the past several decades has been affected by cycles of frequent droughts. After the well known famine in the mid-1980’s and severe food shortages and food insecurity in the early-1990’s, people of North Kordofan continue to face a number of challenges. Among these are critical environmental issues, including land degradation and desertification, as well as climatic changes that threaten people’s abilities to sustainably manage resources and ensure both food and water security.

Extreme fluctuation of rainfall (75-450 mm/year) and increased of frequency of drought have led to an increase in crop failure and soil degradation. Severe climatic conditions and land mismanagement (over grazing, over cropping, deforestation) have caused vegetation cover in the region to became very poor and have contributed to the loss of many once dominant endemic species. Dry conditions encourage the spread of wildfires that cause substantial damage to natural vegetation. Furthermore, as the region borders the desert zone, there is a persistent threat associated with shifting sand dunes and desertification. Aerial surveys in 1975 have shown that, compared to the desert limit set in 1958 during previous studies, desert conditions have advanced southward 5-6 km per year (Sudan Country Study on Biodiversity 2001).

Sheikan, Bara and most of Um Ruwaba are covered with sand-dunes, which makes collection of surface water limited if not impossible. Natural and man-made hafirs (water reservoir) are scattered all over the area where soil condition permits. Luckily, the State is endowed with underground water; its storage capacity is estimated as 2 billion m3. The main sources of recharge are rainwater, are surface runoffs of seasonal streams and groundwater inflow from the Nubian basin lying north of the area. As precipitation declines and becomes more erratic, groundwater recharge becomes less reliable.

The agriculture sector is the source of the livelihood and employment for the majority of the population as about 79% of the populations make their living from agriculture. The livelihoods practiced (farming, herding, forestry, gum collection) are part of traditional rainfed sector (Figure). In North Kordofan State, poverty is defined in terms of crop production, livestock ownership, and availability of off- farm income generating activities, cost and access to water. It is clearly important, especially in the complex, diverse, risk-prone agriculture, which characterize this food insecure region, to assume that increasing food production is the only necessary condition for improving food security. However, variety of factors such as technology, availability of capital, land tenure arrangements, and gender and other social relations influenced production. Although agriculture can provide a considerable proportion of the people’s income, it is not enough by itself to provide a secured living when taking into account the high risk environmental set up and the lack of investment to increase production. Moreover, traditional farmers are highly vulnerable to climatic changes.

Rangelands are the backbone of the livelihood of pastoralists and agro-pastoralists through provision of needed feed resources, where it supplies about 80% of the total feed requirement for herd; also provides soil and water protection/conservation, bio-diversity and ecological balance. As rangelands became deteriorated from overgrazing, nutrient-poor species have replaced the favourable nutritive species. Consequently, grazers have been forced to move to the rich savannah zone. During drought cycles, herders lost most of their livestock (left only with goats) and were forced to shift from animal husbandry to agriculture in greatly marginalized lands. Many people were not able to survive and were forced to migrate to towns or switch to irrigated agricultural schemes. Some range areas were under-utilized during the dry season given water shortages while others were overgrazed due to intensive water supply.

Gedarif State

The project area in Gedarif State is essentially savannah-based ecosystems underlain by clayey soils and typified by low rainfall. The area represents about 5% of total area with about 12 million hectares. The selected area is made up of four villages for which Al Sadda village is the market place, and is located at latitude 15˚13'59.5'' and Lat 35oo2' 10.4''. The area is located 140 km north west of Gedarif city and 40 km east of Sobbakh town. The area of the site is about 10 km2 with agriculture allocations of about 4500 acres. The climate is hot and dry summer, and warm and dry winters. Rainfall is highly variable both seasonally and yearly, with typical rainfall of 200 – 300 mm/year. Soil is clay loam, medium in drainage and infiltration characteristics. Based on last census, population estimate is about 5300 people distributed between 650 households in 4 villages.

Transhumance pastoralists is also practiced in the area with about 16,000 pastoralists (and families) with up to 2 million livestock visit the area during the rainy season. In terms of quantity of livestock raised, there are about 1000 heads of cattle, 200,000 sheep (desert type), 100,000 goats (Nubian), and about 1000 camel of (Arabian). The population cultivates sorghum and applies indigenous water harvesting technology (truce) over typically 5 acres per household. Wadi cultivation is also practiced up to 20 acres per household (Figure 3).

The area is lacking ground water basins due to the presence of Basement Complex Rocks. There are four surface wells depths 25 to 40 meters deep with water level between 25 to 30 meters. Water is drawn manually using buckets and ropes (sometime camels are used to pull the water). The area also has a 75 km long creek (wadi) that flows from areas Surrog Manana located to the Southwest of Al Sadda village. There are also 3 reservoirs (Hafirs) each with capacity of 3000 meters3. Two reservoirs are reserved for human consumption and the third for livestock. Usually late in the dry season water resources in the reservoirs and wells are drained and quality is deteriorated.

The impacts of climate change are clearly felt by inhabitants of the region. Challenges faced by the village populations are reflected in declined productivity, increased cost of food and energy. The area experienced several years of low rainfall and high temperature. Such period of drought and high temperature are frequently occurring with compounded impacts on vegetation cover, soil erosion.

Due to deteriorated range resources, over grazing is taking place with evident impact on range resources conflicts over range resources became more frequent. Loss of palatable range species is occurring. Coping mechanisms included selling of animals and changing the herd composition. The impact on human population is declining nutrition and health and increased poverty.

State of Southern Darfur

The identified area is located between Lat. 12 and 27 39' North and Longitudes 24o 50' East, with estimated area of 8400 km2. A limited part of the area identified has been selected for implementation of a pilot project: latitudes 12 o12’ – 26’ and longitudes 24 o7’ and 25 -10.

Southern Darfur is overwhelmingly savannah-based ecosystems underlain by sandy soils. These areas are typified by low rainfall and the prevalence of sandy soils; they represent about 3% of total area with about 8 million hectares. Rainfall in the project area is the lowest rainfall in Southern Darfur at 250 to 350 mm/year, and is highly variable in both seasonality and spatial extent. Decline and variability in rainfall during rainy season and changes in seasonality and spatial distribution have been well documented. The subsequent impacts on groundwater have also been well documented with negative implications for the living standards of local communities.

The area is traversed with several seasonal creeks flowing from Jebel Marra as well as supported by two main groundwater basins. Even with a large basin and catchment area of 5000 km2 most of this water is not utilized. Establishment of dams will enhance water availability and contribute to recharging of ground basins. Intensifying water harvesting is the best strategy for climate adaptation and for poverty reduction.

The project area population is an estimated 22,000 individuals from several tribes (Dago, Fur, Birgid, Messairia, Zhagawa, Berti and Burnu) in 15 villages (listed in

Table 2). Most of the population practice traditional agriculture and pastoralism; 25% of the population depends on animal husbandry as the major livelihood source. Rainfed agriculture is widely practiced to produce food and cash crops; irrigated agriculture is practiced to a lesser extent along creeks (wadis) and in small areas irrigated by hand-dug wells.

Table 2. Villages involved

| No. | Village | Lat. | Long | No. | Village | Lat. | Long |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Yara | 12o 26 - 00 | 24o 42 - 56 | 9. | Abu Uddam | 12o 10 - 19 | 25o 06 – 58 |
| 2. | Addawa | 12o 31 - 19 | 24o 51 - 86 | 10. | Bashoum | 12o 07 - 19 | 25o 10 – 62 |
| 3. | Damaa | 24o 58 - 75 | 24o 58 - 75 | 11. | Ushma | 12o 02 - 64 | 25o 08 – 58 |
| 4. | Attash | 12 o 23 - 40 | 25o 05 - 14 | 12. | Baba | 12o 05 - 54 | 24o 59 – 69 |
| 5. | Marier | 12o 25 - 80 | 25o 07 - 36 | 13. | Gad Al Habob | 12o 05 - 95 | 24o 56 – 23 |
| 6. | Domaia tamid | 12o 19 - 02 | 25o 04 – 23 | 14. | Amakessara | 12o 11 - 51 | 24o 44 – 25 |
| 7. | Fasha | 12o 13 - 34 | 25o 02 - 74 | 15. | Gerrt | 12o 33 - 37 | 25o 01 – 23 |
| 8. | Ander | 12o 10 - 83 | 24o 58 – 22 |  |  |  |  |

Vulnerability is expected to increase due to human population growth, migration of people from more vulnerable areas in the north to less vulnerable areas in the south, limited government interventions, limited technical packages to help in adaptation in agriculture and animal production, and limited knowledge in water harvesting and improved use of surface water. Public services for education, health and security are also very weak or lacking. Given these challenges, the main goal of the proposed project is to enhance the resilience of local communities in the drought-prone areas through water harvesting measures.

Among the project beneficiaries, there is a growing community acceptance and interest in adaptation innovations. Stakeholders and beneficiaries from the 15 villages generally agreed that water projects are the most important to them whether these are traditional (reservoirs, or hand dug wells) or improved wells equipped with hand-pumps, dams and reservoirs. Such projects will greatly enhance traditional activities in agriculture and animal production.

Central Equatoria State

Much of land in the Central Equatoria State is flood-prone due to an annual rainfall over 1000 mm per year, according to historical data. These areas are located below latitude 10o N and represent about 3% of the country’s total area with about 8.5 million hectares.  The major city near the project areas is Juba, located at 4°50'59.64"N, 31°36'12.60"E. (See FigureFigure 11. Farming systems in Central Equatoria (source: FAO).

The Equatoria Climate Zone typically experiences an annual rainfall of 900 – 1000 mm per year during the year based on historical data from 1950-1970.  The area is dominated by highly fertile, sandy-clay soil. Seasonal streams yield many ponds that retain water for long periods into the dry season. The Kudda stream, for example, starts from central mountain zone and ends up in River Nile near Jebel Lado villages. Most of the rain occurs during rainy seasons from April/May to September/October with humidity levels is considered very high. The average annual temperature is 29˚C.

Climate change impacts the natural resource potential of the area due to increase in temperature, draw-down of the local water table, soil erosion, reduced rainfall, and lower agricultural and fisheries productivity. Reduced livelihood productivity means heightened vulnerability of the rural population. Climate impacts are exacerbated by chronic drought and water-insecurity, lack of adequate potable water, poor rural marketing strategies, and lack of awareness about climate changes.  Rampant deforestation has also induced drastic change in the local climate resulting in raised in temperatures, lowered humidity levels and rainfall, and drought.

All these changes had leads to poor adaptation activities for livelihood improvements, as a results the community in west of Juba specially. Assessments made by NAPA Team in Central Equatoria have identified the area west of Juba town as highly vulnerable and seriously affected by climate change. The target communities for adaptation interventions in Central Equatoria are Kudda, Legge and Tigore, which are situated 25 – 80 miles west of Juba town (See Figure 4 ).

The people in the areas are Nilotics, Para-Nilotic, and Sudanic.  Most people in the identified areas are below national poverty levels, and primarily due to environmental factors; as the rainy season became shorter and dry period became dominant/longer since 1970, the implicated areas have experienced serious water shortages. These changes in climate have led to migration of the affected community members from their rural villages to Juba town to earn money and send remittances home to improve their families’ livelihood statuses. Most of the people taking refuge from climate change in the town are agro-pastoralists e.g. Bari, Nyangwara, and Pojulo, in addition to the Mundari that depended on water from Kudda stream for traditional irrigation, and livestock watering.

# SIGNATURE PAGE

Country: Sudan

UNDAF Outcome(s)/Indicator(s):

Expected Outcome(s)/Indicator (s): Outcome 1:

Expected Output(s)/Indicator(s): Output 1.1 –

Implementing partner:

United Nations Development     __________________________________                       _________

Programme                                                                                                                            Date

Ministry of Environment 	___________________________________  		_________

Date

Higher Council for Environment  __________________________________                      _________

and Natural Resources 	                                                                                                        Date

# Footnotes

United Nations, 2007 Sudan Common Country Analysis, November 2007,  p.8

United Nations, Sudan Common Country Analysis 2007, November 2007,  p.52

Major portions of Sudan’s Interim Poverty Reduction Strategy Paper (IPRSP, 2004-2009) focus on agriculture, water resources, and public health—the same sectors identified by the NAPA process. The IPRSP is an important document that creates synergy of adaptation to climate change to all vulnerable livelihoods in the country.

El Bashir, A. and Ahmed, A., 2006. Food Security Policies In Sudan, Khartoum Food Aid Forum, 6-8 June

As determined by a review of government statistics regarding the effects of drought on migration, livestock deaths, crop failure, and loss of human lives.

In particular, Outcome no. 8 of the UNDAP Sudan Country Cooperation Framework Bridging Programme (2007-2008) which strengthens natural resource management for sustainable development.

The DDC is currently supporting the ongoing UNDP Sudan Reduction of Resource Based Conflict project through Danish funding.

Vulnerability Reduction Assessment (VRA) is a type of qualitative survey in which vulnerability factors are determined through stakeholder consultations, and stakeholders rate their vulnerability on a scale of 1-10 at the beginning, periodically throughout the project or programme, and at the end. Food security in relation to drought may vary from household to household, but the VRA approach allows the comparison of perceived changes despite this variability in terms or unit or % change in vulnerability scores.

# Text boxes

)

Figure 11. Farming systems in Central Equatoria (source: FAO)

project

Location of pilot villages as indicated by project scoping team

Figure 10. Location of villages and project area in S. Darfur, Sudan

Figure 9.  Project area (from State scoping document)

Figure 3. livelihood systems (source: FAO)

Figure 7. Reference map of implementation area

Figure 6. farming systems (source: FAO)

Figure 5. Bara(h) locality, Northern Kordofan. (GoogleEarth)

Figure 2. reference map of implementation area, satellite image (left) from GoogleEarth.

Figure 3. Livelihood systems in the River Nile State (FAO).

Atbarah River

Programme Period: 2009-2013

Programme Component: Climate Change

Project Title: Sudan

Project ID: PIMS # 3925

Atlas Award: 00057783

Atlas Project ID: 00071514

Project Duration:	 4 years

Management Arrangement: NEX

Brief Description

The goal of this project is to contribute to reduce the vulnerability and increase the adaptive capacity of Sudan’s agriculture sector to climate change impacts. Following the completion of the National Program of Action (NAPA) for Sudan, the highest priority area for follow-up intervention are those that contribute towards food security under climate change. The objective of the project is to reduce the impact of climate change on food insecurity of small-scale farmers and pastoralists. The project, if successfully implemented,will reduce the vulnerability of rural communities to additional pressures from climate change, including variability. The project focuses on building resilience and adaptive capacity of rural communities relative to their agricultural and water resource management practices, and relative to current and future climate risks. More specifically, the project will target five critical agro-ecological zones in Sudan in order to encompass complexity of productive systems and modify current coping strategies that are being undermined by increasing climate variability and reoccuring climatic hazards (such as droughts and floods). Project will introduce, concrete innovative adaptation measures, such as water capture, borehole irrigation, in-situ re-introduction of more stress resistent breeds and crop variaties, sand stabilisation and other land management and agronomic techniques. These will help increase robustness and resilience of highly vulnerable rainfed farming and pastoralist systems to climate change risks. By demonstrating viable and cost-effective adaptation options the project will also assist the government of Sudan to improve its food security policies and address critical social vulnerabilities that often underpin resource-based conflicts, aggrevating human security conditions.

This summary is a tad weak. Lots of very generic stuff—can we make it more concrete, direct?

Figure 2. Reference map of implementation area, satellite image from GoogleEarth

Figure 1: Acutely vulnerable areas in Sudan identified during the NAPA consultative process.

Figure 1. Acutely vulnerable areas in Sudan chosen for implementation of pilot projects

32 km/~20 miles

Figure 4. roughly 25-80 miles west of juba where the NAPA follow-up communities are situated.

ional

reg

State

PC (Equatorial

R

)

ional project

reg

State

Darfur

n

RPC (Souther

)

project

ional

reg

State

RPC (Gegarif

)

ional project

reg

Kordofan State

RPC (North

)

project

ional

State reg

River Nile

RPC (

(PMU)

Project Management Unit

(PSC)

Project Steering Committee

Total budget:		 US$	6,800,000

Allocated resources (cash):

- GEF		US$  	3,300,000

- UNDP 		US$          500,000

- Government		US$

In kind contributions:

- UNDP		US$

- Government		US$ 	3,000,000

Agency Fee:		US$

G