GEFSEC Project ID: 2614

UNDP Project ID: 3341

Country: Senegal, Cape Verde, The Gambia, Guinea Bissau, Mauritania

Project Title: Adaptation to Climate Change – Responding to Coastline Change and its Human Dimensions in West Africa.

other project Executing Agency (ies): IOC of UNESCO

GEF Focal Area: Climate Change

GEF Operational Program: SPA

Starting Date: November 2005

Estimated Date of operational closure: 1st May 2007

Estimated Date of financial closure: 30 June 2008

pdf/ppg status report

A- Summary of actual achievements of preparatory phase (outputs and outcomes), and explanation of any deviations from expected outcomes

During the implementation of the PDF-B phase of the project the following outcomes and related outputs have been achieved:

Outcome 1: 	Learning mechanism for generating and applying methodological tools for assessing coastal vulnerability, its impacts, causes and trends in participating countries

- Guidance document on Coastal Zone Vulnerability has been prepared and disseminated in all 5 countries (at the technical level)

- 5 national reports on Inventory of coastal resources vulnerable to climate and shoreline changes completed

- 5 national reports on Situation Analysis, Site identification, adaptive capacity assessment and project strategy, completed

- Hot spots and sensitive areas have been identified in each countries

- Pilot/demonstration sites identified for the Full Size Project based on environmental and socio-economic criteria

Outcome 2: 	Institutional mechanisms in place and capacity needs defined for adaptation strategies

- Lessons from other adaptation project (CPACC) identified and integrated in Prodoc;

- Institutional and capacity constraints to implementation of ICAM identified (this has been integrated in the national reports under Outcome 1)

- Existing ICAM legal instruments reviewed and recommendations formulated for improved capacity (this has been integrated in the national reports under Outcome 1)

One of the expected outputs, i.e. the Chapter on Coastal Zone and Climate Change Adaptation for the APF Vol. II did not get produced as originally planned. With a reduced implementation phase in order to submit the project under GEF-3, the priority has been placed on the development and finalization of the FSP prodoc.

Outcome 3:	Support and coordinating mechanism for PDFB Project activities in place

- coordinating and Implementation mechanism established at national and regional level, such as :	- Project coordination unit established in Dakar

- two meetings of the project steering committee have taken place

- two meetings of the national committee (for each country)

- Project Team established (Project coordinator, assistants, national coordinators, international consultants, local consultants hired);

- Co-financing resources mobilized;

- Stakeholder consultations implemented (2 national stakeholders meeting per country);

- Full Project Proposal completed and endorsed by participating countries;

- Complementary SCCF PDF-B project document drafted;

- Communication and public awareness materials produced and disseminated (website, brochure, posters).

Table 1: Completion status of Project Activities

| Approved | Actuals |
| --- | --- |
| Proposed Activities at Approval | GEF Financing | Co-financing | Completion status | GEF financing | Co-financing | Uncommitted GEF funds |
| OUTCOME 1 |  |  |  |  |  |  |
| Activity 2: Inventory of coastal resources and use vulnerable to climate and shoreline change | 105,000 |  | Completed | 105,000 |  | 0 |
| Activity 3: Assessment of the environmental and socio-economic impacts, causes and projected future trends of shoreline change (APF, TP6 – Chapter 3,4,5) | 103,000 | 53,619 | Completed | 103,000 |  | 0 |
| Activity 4: Prioritisation of hotspots and/or sensitive areas, and the (preliminary) identification of pilot/demonstration sites (APF TP 8) | 90,000 |  | Completed | 90,000 |  | 0 |
| OUTCOME 2 |  |  |  |  |  |  |
| Activity 5: Assessment of existing constraints to ICAM implementation, and review of lessons learned (APF TP9) | 88,000 |  | Completed | 88,000 |  | 0 |
| Activity 5: APF Chapter on Climate Change and Coastal Zone/CPACC review | 22,000 |  | APF chapter Not completed | 22,000 |  | 0 |
| OUTCOME 3 |  |  |  |  |  |  |
| Activity 1: Project coordination | 246,000 | 11,381 | Completed | 246,000 | 60,027 | 0 |
| Activity 6: Resource Mobilization | 23,000 |  | Completed | 23,000 |  | 0 |
| Activity 7: Preparation of Project Brief, and supporting documentation | 23,000 |  | Completed | 23,000 |  | 0 |
| Total | 700,000 | 65,000 |  | 700,000 | 60,027 | 0 |

B – Record of Stakeholder Involvement in project preparation

The project has been designed to ensure broad stakeholder participation in all components. The PDF-B process included a series of stakeholder consultations in each country (at the community as well as policy level) to validate and obtain information identified through initial desk reviews.

Specific stakeholders who have been consulted during the country specific consultations through national workshops (reports available on request), consultations at the pilot sites and other project meetings have been listed in Annex A1 of the PRODOC. It suffices here to state that representatives of all stakeholder groups, including government institutions, NGO’s, CBO’s, international development partners, private sector, media and academics, have been involved to greater or lesser extent in all participating countries.

##### PART II  - PDF financial delivery

##### Table 2 – PDF Input Budget – Approvals and commitments

| Input Description* | Approved | Committed |
| --- | --- | --- |
|  | Staff weeks | GEF funds | Co-finance | Staff weeks | GEF funds | Co-finance |
| Personnel |  |  |  |  |  |  |
| Local consultants | 715 weeks | 357,664 |  | 715 weeks | 357,664 |  |
| International consultants | 47 weeks | 93,836 | 6,408 | 57 weeks | 93,836 | 20,000 |
| Training |  |  |  |  |  |  |
| Travel |  | 74,000 | 4,973 |  | 74,000 | 40,027 |
| Office equipment |  | 44,000 |  |  | 44,000 |  |
| Misc |  | 130,500 | 53,619 |  | 130,500 |  |
| Total |  | 700,000 | 65,000 |  | 700,000 | 60,027 |

At this date, the PDF delivery rate (funds disbursed at time of operational closure as percentage of total GEF allocation) is 54%.

It is therefore expected that a subsequent amount of unspent PDF funds should be available at the time of financial closure. The main deviation related to the number of international consultants that were hired. With a shortened implementation period of 6 months (originally the PDFB was to last 18 months), additional man power had to be brought in. In addition, the project coordinator was hired as an International Consultant rather than as an appointment of limited duration.

Table 3: Actual PDF co-financing

| Co-financing Sources for Project Development Preparation (PDF) |
| --- |
| Name of Co-financier (source) | Classification | Type | Amount |
|  |  |  | Expected ($) | Actual ($) |
| UNESCO/IOC | Exec. Agency |  | 65,000 | 60027 |
| UNESCO/IOC | Exec. Agency | In kind | 95,000 | 95000 |
| Cape Verde | National Govt | In kind | 20,000 | 20,000 |
| Gambia | National Govt | In kind | 20,000 | 20,000 |
| Guinea Bissau | National Govt | In kind | 20,000 | 20,000 |
| Mauritania | National Govt | In kind | 20,000 | 20,000 |
| Senegal | National Govt | In kind | 20,000 | 20,000 |
| UNDP/GEF | Implem. Agency | In kind | 10,000 | 10,000 |
| Total co-financing | 270,000 | 265,027 |

# Footnotes

To the extent possible, these reviews drew on ongoing work in National Communications, the very preliminary NAPA consultations and National Capacity Self-Assessments.

# Text boxes

Report submitted by:

Name				Title					Date

________________		UNDP				June 12, 2007