## Slide 1: UNDP CIRDA Country Program Managers Workshop 25-27 August 2015 Addis Ababa, Ethiopia
Reports from Strengthening National Climate Information / Early Warning System (CI/EWS) Projects
Zambia
Chibesa Pensulo
Project Manager
Notes: Instructions: Complete items in red italics

## Slide 2: Outline
Introduction of Zambian delegates
Key agencies involved in CIEWS in Zambia
Project implementation progress
Challenges
Future plans

## Slide 3: Zambian delegates
Mr Mukufute Mukelabai, Principal Meteorologist – Applied Services, Zambia Meteorological Department
Mr Chongo Simpasa, Programme Associate – Environment, UNDP Zambia
Ms Chibesa Pensulo, Project Manager, CIEWS project

## Slide 4: Key agencies involved in CIEWS in Zambia
Cabinet Office
Ministry of Agriculture and Livestock
Ministry of Finance
Ministry of Transport, Works, Supply and Communications
Ministry of Mines, Energy and Water Development
Zambia Meteorological Department
Department of Water Affairs / Water Resources Management Authority
Interim Inter-Ministerial Climate Change Secretariat
Office of the President
Office of the Vice President
Disaster Management and Mitigation Unit
Ministry of Lands, Natural Resources and Environmental Protection
Environment and Natural Resources Management Department

## Slide 5: Zambia Meteorological Department
Government Department under the Ministry of Transport, Works, Supply and Communications
ZMD provides the following products and services:
No. | Products and Services | Frequency
1 | Seasonal Rainfall Forecast | Issued September
2 | Seven-Day Weather Forecasts | Issued on Mondays and Fridays
3 | Zambia Evening Weather Forecast | Issued daily
4 | Ten-Day Crop-Weather Bulletin | Every 10 days, during rainy season
5 | Aviation Forecasts | Daily
6 | Climate Databank Service | Data supplied on request
7 | Technical Reports/Publications | Occasional
8 | Severe Weather Warnings | Occasional

## Slide 6: Disaster Management and Mitigation Unit
Unit under office of the Vice President
Coordinates disaster management committees at national, provincial, district and satellite (community) levels
Has no monitoring equipment of its own; relies on ZMD for meteorological data and DWA for hydrological data
Practices disaster response rather than disaster risk reduction

## Slide 7: Project implementation progress 1. Training
1-week computer training course for 30 ZMD staff, December 2014 - training for users of the 30 computers procured by the project
2-week refresher course in Meteorology for 22 ZMD staff and 8 MAL staff, December 2014 – training in AWS maintenance and weather data coding
1-week enumerator training for CIEWS baseline survey, April 2015 – trained meteorological assistants to conduct the CIEWS baseline survey
Sponsorship for 12 ZMD staff to study Diploma in Meteorology at Zambia Air Services Training Institute, January 2015 - December 2017 – raising them from senior meteorological assistants to forecasters
Sponsorship of 4 ZMD staff to study BSc in Climatology at Mulungushi University, September 2015 to June 2018 – raising them from forecasters to climatologists

## Slide 8: 2. CIEWS national task team
Purpose: To enhance collaboration on climate information and early warning systems among the project partners – ZMD, DMMU, MAL, MoH, DWA, WaRMA, ICCS, ENRMD and ZCCN
1st meeting: 8-9 January 2015 – annual workplan development
2nd meeting: 15-16 April 2015 – review of project activities and outputs, review of questionnaires for baseline survey
3rd meeting: 2 September 2015 – presentation of baseline study findings

## Slide 9: 3. Private sector engagement
Held meetings with Airtel and Zamtel in March 2015 (weather information dissemination and sensor hosting on telecoms towers)
Held meetings with NICO Insurance and Madison Insurance in May 2015 (weather-index insurance)
Participated in study visit to MeteoGroup and the Weather Philippines Foundation in August 2015

## Slide 10: 4. CIEWS Baseline study (April - August 2015)
Review of project activities and outputs
Household survey in 30 districts (3 per province)
DDMC survey in 10 districts (1 per province)
PDMC survey in 9 provinces (except Lusaka)
Survey of 8 businesses in mining, energy, construction, insurance and agribusiness sectors
Capacity assessment of ZMD and DMMU

## Slide 11: 5. Communication
1st CIEWS brochure published
Communications consultant selected to:
  develop a CIEWS communications strategy and action plan
  conduct training for meteorological officers in community engagement
  develop CIEWS brochures in English, Lozi, Nyanja and Tonga
  facilitate the following meetings:
    Parliamentary briefing session
    House of Chiefs briefing session
    National Climate Outlook Forums in Lusaka, Mambwe, Gwembe and Sesheke districts

## Slide 12: 6. Procurement
New instruments for 39 manual weather stations – supplier has been selected by UNDP CO, pending approval from RSC
Delivery timeline: 14 weeks
28 Automatic Weather Stations – to make use of an existing long-term agreement with Adcon Telemetry
Delivery timeline: 12 weeks

## Slide 13: Future plans
Identify and prepare sites for the 28 AWSs
Pursue a PPP with at least one mobile company, for weather information dissemination (and hosting of weather sensors on telecoms towers)
Procure the remaining technical components of an early warning system
Modernise the forecasting centre
Develop tailored weather and climate products
Enhance engagement of end-users, through the communications campaign